# ONTARIO FUSION GENERATION
ACTUAL SITE WORK HISTORY — REV W3

PHYSICAL EXECUTION • WORKFRONTS • INSTALLATION • TURNOVER • COMMISSIONING
CONTROL CUT: 19 APRIL 2031

# Control statement

This revision corrects the previous W1/W2 mistake: the controlling object is the workfront and the physical asset history, not the project phase. The narrative below is built from the 22,647-row controlled asset register and the 128,986-row master event timeline, then constrained by the Rev N/Rev3 narrative canon. 106,302 through-cut lifecycle events are site-physical events (arrival, installation/mobilization, mechanical completion, turnover, commissioning/operation, or removal/demobilization).

Working-dataset dates are not silently treated as canon. The asset register contains 802 installation-before-arrival anomalies and 1,294 turnover-before-mechanical-completion anomalies; affected rows are explicitly quarantined in the machine-readable history. The narrative chronology uses source-controlled period facts and only uses register dates as examples where the sequence is not quarantined.

Every workfront is interpreted through six separate chains: construction/constructor control, EPC field engineering, design/technical authority, owner/licensee oversight, commissioning/work-control custody, and supplier/OEM support. A named employer in the asset register is not treated as proof of the individual craft person who touched an item.

# How to read this history

| Layer | Meaning in this volume |
| --- | --- |
| Physical workfront | The actual place and object being changed: excavation, building, system, train, equipment, connection, support, cable, valve, instrument or temporary plant. |
| Execution chain | Who plans/releases/directs field execution: typically Bechtel constructor/package chain and the named installing contractor before turnover. |
| Technical chain | Who can answer/design/disposition the technical problem: E&C discipline/SCE, HMS for protected HFRP basis, OPG where owner/licensing basis applies. |
| Quality/evidence chain | CWP/IWP/ITP, inspections, surveys, weld/NDE, torque/alignment, redlines, NCRs, completion dossiers and as-built/configuration evidence. |
| Custody/work-control chain | After turnover, OPG Commissioning/receiving organization controls access, isolation, PTW and post-turnover re-entry. |
| Knowledge state | What is visible to craft, supervision, field engineering, QA, commissioning, project controls, management, finance/government at that date. |

# Dataset execution synopsis

| Year | Commissioning/Operation | Installation/Mobilization | Mechanical Completion | Removal/Demobilization | Site Arrival | Turnover |
| --- | --- | --- | --- | --- | --- | --- |
| 2025 | 4 | 120 | 4 | 0 | 1159 | 0 |
| 2026 | 32 | 68 | 32 | 0 | 760 | 0 |
| 2027 | 15 | 16 | 15 | 277 | 215 | 15 |
| 2028 | 2 | 1642 | 2 | 120 | 4362 | 2 |
| 2029 | 369 | 18646 | 1215 | 104 | 16030 | 999 |
| 2030 | 16667 | 388 | 19138 | 622 | 121 | 18172 |
| 2031 | 2891 | 0 | 302 | 501 | 0 | 1275 |

# 2025 — The site becomes a production system

Working-dataset physical-event volume: Site Arrival: 1,159, Installation/Mobilization: 120, Commissioning/Operation: 4, Mechanical Completion: 4.

Highest-volume recorded workfront/building locations: Sitewide (338); Sitewide / Defined Lift Zones (180); Sitewide / Early Works (171); Construction Support (152); Excavation Zones (140); Site Services / Sitewide (130); Excavations (80); Construction Production Area (66); Main Logistics Gate (16); Lake Ontario / Marine Works (14).

## May–August 2025

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| Z08 / sitewide enabling works | Temporary earthworks fleet, site-service vehicles, construction production equipment, temporary utilities, dewatering and controlled lifting/access equipment begin entering the site. The work is not 'pre-project housekeeping': haul roads, drainage, laydown, warehousing, utilities and material-control areas are prerequisites for every later permanent workfront. | Bechtel constructor/preconstruction organization with Bird and early-work contractors; E&C interfaces design/logistics; OPG oversight. | survey control; early works CWP/IWP; temporary-utility inspections; equipment certifications; environmental permits/monitoring; as-builts. |

## September 2025 FID

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| Z08 ~60% temporary establishment; Z06 marine works; Z01–Z05 survey/control networks | Bechtel assumes the full construction-management organization. Permanent nuclear construction has not yet begun, but the site has roads, security/access, field offices, material control, laydown and construction utilities sufficient to support production. | OPG owner/licensee; E&C EPC/integrator; Bechtel constructor; specialist early-work contractors. | construction readiness; execution plans; survey network; temporary works records; material/logistics control. |

## October–December 2025

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| Future Z01–Z05 excavations / heavy haul corridors | Shoring wall installation, dewatering wells, groundwater monitoring, rock anchors/piles where required, haul-road strengthening, stripping and excavation-ramp development. Permanent survey monuments are established outside future settlement zones. No safety-significant nuclear concrete is yet poured. | Bechtel construction management; civil contractors; E&C civil/structural; OPG oversight. | blasting/excavation permits; survey controls; shoring/dewatering inspections; environmental records; daily production records. |

# 2026 — Excavation, undergrounds and irreversible interfaces

Working-dataset physical-event volume: Site Arrival: 760, Installation/Mobilization: 68, Mechanical Completion: 32, Commissioning/Operation: 32.

Highest-volume recorded workfront/building locations: Fabrication Shops / Workfronts (310); Sitewide (280); Major concrete workfronts (72); Intake Tunnel (64); Outfall Tunnel (64); Marine Terminal / Heavy Haul Route / Laydown (56); Sitewide / Defined Lift Zones (46).

## January–April

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| Z01, Z02, Z03, Z04 plus buried utilities | Z01 Tokamak/Assembly excavation accelerates, Z02 Hot Cell/Tritium follows, Z03 heat-transport excavation opens behind Z01, while the shallower turbine island advances more quickly. Rock work generates blasting, scaling, rock bolts, drainage, sump pumping and temporary access. Permanent storm, sanitary, fire-water, ductbank, grounding-grid, utility-water and selected drain systems are installed before later structures close access. | Bechtel + civil/package contractors; E&C civil/structural and underground utilities; OPG construction oversight. | survey; excavation acceptance; blast/vibration logs; underground inspection/test records; buried-line as-builts; embed/penetration interface registers. |

## May

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| Z01 foundation / licensing gate | Licence to Construct allows safety-significant permanent construction subject to hold points. Foundation rock is accepted, followed by permanent drainage, waterproofing, foundation instrumentation and transfer of survey control into the final construction network. | OPG licensee controls licence commitments; Bechtel executes construction; E&C controls integrated design; QA witnesses/reviews defined points. | foundation-rock acceptance; geotechnical verification; drainage/waterproofing inspection; survey-control transfer; hold-point releases. |

## June–August

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| F101 basemat workfront | Rebar and couplers, machine/equipment embeds, anchor sleeves, electrical grounds, embedded conduits, waterstops and construction joints are verified before each irreversible placement. Pour cards and QA hold-point releases control the sequence. | Concrete/rebar civil contractor under Bechtel; E&C civil/structural and discipline interfaces; OPG oversight/QA as required. | pre-pour checklist; embed/penetration register; survey; material certificates; concrete batch/delivery tests; hold/witness releases. |

## September

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| F101 first safety-significant major concrete | First major fusion-island safety-significant concrete is placed in controlled placements. Delivered temperature, slump, air, strength cylinders, internal mass-concrete temperature and thermal differential are monitored. | Constructor/civil crews + concrete QA laboratory + E&C civil/structural + OPG oversight. | pour card; batch records; concrete test results; temperature monitoring; NCRs if any; post-pour survey. |

## October–December

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| Z01–Z07 parallel permanent works | Z01 basemat completes; Z02 basemats follow; Z03 heat-transfer foundations begin; Z04 turbine pedestal begins; Z05 cryogenic compressor and power-conversion foundations begin; Z06 intake/discharge shafts progress; Z07 switchyard earth grid, foundations and drainage progress. | Multiple contractor packages under Bechtel with E&C discipline ownership; OPG owner oversight. | civil completion records; structural surveys; underground as-builts; interface/punch records. |

# 2027 — Vertical construction, permanent cranes and first machine cargo

Working-dataset physical-event volume: Removal/Demobilization: 277, Site Arrival: 215, Installation/Mobilization: 16, Mechanical Completion: 15, Turnover: 15, Commissioning/Operation: 15.

Highest-volume recorded workfront/building locations: Sitewide / Early Works (171); E-101/E-102/E-103/E-104/E-105 (147); Excavation Zones (74); Marine Terminal / Heavy Haul Route / Laydown (36); F-106/F-101 (35); F-106 Assembly Hall (30); F-101 Tokamak Building (18); Intake Tunnel (16); Excavations (16); F-106 Assembly Hall / F-101 (10).

## Q1

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| Z01–Z05 lower structures | Z01 lower shielding walls, machine-support foundations, cryostat-base support, lower galleries and equipment vaults rise. Z02 hot-cell shielding, Tritium Building basement and radwaste vaults progress. Z03 pump/HX foundations and pipe-gallery structures develop. Z04 turbine pedestal, condenser pit and hall columns advance. Z05 compressor-hall steel, power-conversion slabs and permanent electrical rooms take shape. | Bechtel + Aecon/Kiewit/E.S. Fox/Bird package chain; E&C discipline engineers; OPG oversight. | rebar/formwork/structural steel inspection; embeds/anchors; concrete/weld records; surveys; access/opening controls. |

## Q2

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| F106 Assembly Hall and F101 machine-support workfront | Main bridge-crane girders, auxiliary cranes, assembly stands and metrology monuments are installed. Permanent gravity-support structures enter the Tokamak pit and lower machine supports are surveyed. Two main bridge cranes in the working register arrive 4 Feb and 24 Feb 2027, begin installation 21 Feb and 13 Mar, reach MC 1 Jul, turnover 1 Aug and commission 15 Aug. | Kiewit/OEM crane erection and specialized rigging under Bechtel; E&C/constructor lifting engineering; HMS machine-interface review as required. | crane erection IWP; structural/weld/NDE; proof-load plan/results; survey/metrology; certification; turnover. |

## Q3

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| Z06 marine gateway / heavy component route / laydown | The purpose-built marine terminal becomes a project-cargo gateway. Early HFRP cargo includes lower cryostat/base structures, PF coils, sector tooling, major machine supports, cryogenic cold-box shells, large heat exchangers and main transformers. Receipt is a controlled work process: offload, dimensional/condition inspection, preservation, shock-recorder review, customs/security release and SPMT movement to controlled laydown or installation. | Bechtel logistics/material control; E&C logistics/package engineering; OEM/vendor field reps; QA; heavy-haul contractor. | shipping release; customs; receiving inspection; dimensional survey; shock recorder; preservation; lift/haul study; storage location. |

## Q4

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| F106 production equipment | Bridge-crane proof loading completes and four sector-assembly stations become available. The Assembly Hall is now a production facility, not merely a completed building. | Constructor/assembly team + OEM specialists + E&C/HMS integration/metrology. | fixture acceptance; metrology baseline; tool calibration; crane certification; readiness review. |

# 2028 — Peak construction and parallel production lines

Working-dataset physical-event volume: Site Arrival: 4,362, Installation/Mobilization: 1,642, Removal/Demobilization: 120, Mechanical Completion: 2, Turnover: 2, Commissioning/Operation: 2.

Highest-volume recorded workfront/building locations: Plant Buildings (617); Plantwide (596); F-103 (524); H-101 (470); W-101/W-103 (379); U-101/U-104 (368); F-101 (236); T-101 (216); E-101/E-102/E-103/E-104/E-105 (189); C-101/C-102 (156).

## January–December

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| F106 -> F101 16-sector erection front | SS-01 through SS-12 are placed monthly during 2028. Each sector lift is released through the same controlled production cycle: fixture release, verified shipping/as-built mass and COG, crane configuration, metrology, obstruction walkdown, temporary-support and rigging inspection, test/critical lift, pit set, stabilization and as-set survey. The next sector can advance while previous interfaces enter joining. | Kiewit/MHI/HMS machine-assembly organization within Bechtel site control; E&C integration; HMS reference assurance; metrology and NDE specialists. | critical-lift record; rigging certification; metrology; temporary-support inspection; as-set survey; release-to-join record. |

## Rolling behind the lift front

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| F101 toroidal joints | Adjacent-sector geometry is measured; closure/splice pieces are fitted or machined; tack sequence, structural/vacuum welding, NDE, leak testing and dimensional resurvey proceed as a second production line. A typical site state can have SS-10 entering the pit while one crew closes SS-06/07 and another NDE team inspects SS-05/06. | Welding contractor/craft + machine assembly supervision + E&C/HMS engineering + QA/NDE. | fit-up survey; WPS/PQR/welder identity; weld traveller; NDE; leak test; post-weld survey; deviation/NCR if geometry exceeds allowance. |

## Throughout 2028

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| H-101 / Z03 | Four blanket heat-transport pump foundations are accepted; primary HX/steam generators, pressurizer, hot/cold headers, divertor cooling HXs and primary pump casings are installed. Large-bore piping begins. Permanent equipment remains under preservation until flushing/system readiness. | E.S. Fox/BWXT and package suppliers under Bechtel; E&C mechanical/process/thermal-hydraulic engineering; HMS where HFRP interfaces are implicated. | foundation acceptance; soleplate/alignment/grout records; equipment receiving; nozzle/interface survey; piping weld/NDE; preservation records. |

## Throughout 2028

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| T-101/T-102 / Z04 | Turbine hall crane becomes operational. Condenser modules, HP/LP turbine casings, generator stator/rotor, deaerator and feedwater heaters arrive and are erected in conventional sequence. Register examples: HP turbine arrives 16 May, installs 16 Jun; LP1/2/3 arrive 31 May, 15 Jun, 30 Jun and install 1/16/31 Jul; generator installation starts 15 Aug. | Kiewit/E.S. Fox/OEM with Arabelle package support; Bechtel constructor; E&C conventional-island engineering. | heavy-lift/erection records; pedestal/interface survey; alignment; preservation; vendor inspection; completion records. |

## Throughout 2028

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| C-101/C-102 and electrical / Z05 | Helium compressors, oil-removal skids, intercoolers, cold boxes, helium/nitrogen storage, converter transformers, magnet power converters, dump resistors and initial MV switchgear are installed. Electrical and cryogenic work begins to impose cleanliness, segregation and future energization constraints on surrounding construction. | E.S. Fox/IHI/GE-qualified suppliers and electrical contractors under Bechtel; E&C electrical/cryogenic disciplines; HMS magnet/cryogenic assurance. | equipment setting/alignment; pressure-boundary cleanliness; cable/bus installation; insulation/megger tests; vendor data; preservation. |

## Throughout 2028

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| F-103 / Z02 | JGC tritium-process modules arrive and are mechanically set: exhaust-processing, gas cleanup, isotope-separation cold boxes, hydride storage, water-detritiation and atmospheric-detritiation packages. These are physical installation states only; no tritium service occurs. | JGC/vendor specialists + installation contractor + E&C/HMS tritium/process integration under Bechtel. | receiving; module set/alignment; piping/interface records; cleanliness; confinement/penetration interfaces; no D-T operating record. |

# 2029 — Integration, systemization, energization and first turnover

Working-dataset physical-event volume: Installation/Mobilization: 18,646, Site Arrival: 16,030, Mechanical Completion: 1,215, Turnover: 999, Commissioning/Operation: 369, Removal/Demobilization: 104.

Highest-volume recorded workfront/building locations: Plantwide (4,303); H-101 (3,970); F-103 (3,952); C-101/C-102 (2,055); F-101 (1,924); T-101 (1,680); T-102 (1,223); U-101/H-101 (1,188); Controlled Buildings (1,080); Commissioning Workfronts (995).

## January–April

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| F106/F101 machine front | SS-13 through SS-16 complete the monthly pit-placement campaign. Field joining, vacuum-boundary welding/NDE/leak work and survey dominate the machine critical path. The last sector does not mean the machine is 'finished'; closure reduces adjustment freedom and converts many open erection interfaces into configuration gates. | Machine assembly/weld/NDE/metrology production lines under Bechtel; E&C/HMS technical authority. | critical-lift/as-set records; closure fit-up; weld/NDE; leak test; final toroidal survey. |

## H1

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| F101 machine integration | Central-solenoid erection, remaining PF work and machine structural interfaces advance. Register examples: PF5 installation starts 13 Jan and PF6 23 Apr; all six PF coils reach MC 1 Aug. Central-solenoid modules arrive from Nov 2028 through Mar 2029 and install 9 Jul–13 Aug, reaching common MC 27 Sep. | Kiewit/MHI/HMS package chain; E&C integration; HMS magnet reference authority; QA/metrology. | lift/assembly records; electrical/cryogenic interface preservation; alignment/preload evidence; MC dossier. |

## July 2029–May 2030 campaign

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| F101 upper/maintenance ports | Blanket installation becomes a repetitive remote-handling/precision production line: 80 replaceable segment assemblies are inserted through future maintenance routes, connected, surveyed and accepted. BLK-S01-I1 in the working register arrives 6 Mar 2029 and begins installation 13 Jul. | Kiewit/HMS remote-handling team + MHI/HMS-qualified supplier chain; E&C/HMS integration; OPG future receiving/commissioning interface. | module pedigree; lift/RH tooling; interface metrology; coolant/service connection evidence; leak/pressure/flow test; remote disconnect/reconnect demonstration. |

## November 2029–June 2030 campaign

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| F101 lower ports | Divertor cassette installation begins through lower-port access. The sequence is explicitly coupled to pumping, supports and service installation so that one workfront does not close another. DIV-S01-C1 arrives 8 Jun 2029 and begins installation 19 Nov. | Kiewit/HMS remote-handling team + qualified suppliers; E&C/HMS; Bechtel workface coordination. | cassette pedigree; lower-port access release; tooling/handling; alignment; cooling/service connections; acceptance evidence. |

## Q2

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| Selected electrical buildings and distribution | Permanent electrical backfeed enters designated buildings. The physical campus now has live electrical rooms beside ordinary construction. Access, temporary construction power, grounding, LOTO and work authorization become system/boundary questions instead of general site rules. | OPG Commissioning begins assuming controlled boundaries; E&C/Bechtel construction remains active elsewhere; electrical contractor/GE suppliers. | energization package; clearance/tagging; boundary drawings; approved switching/test steps; access-control changes. |

## Q3

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| Earliest utilities | Service water, demineralized water, instrument air, fire water, selected electrical distribution and selected HVAC reach MC and enter first formal turnovers. Geography stops being the primary organizing principle: one building can contain construction-owned, commissioning-owned and shared-interface workfronts. | E&C Systems Completion/Turnover + Bechtel/completion contractors -> OPG Commissioning receiving organization. | MC certificate; punch categorization; turnover dossier; joint walkdown; as-built/configuration; baseline inspection; preservation/open work; custody transfer. |

## Q4

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| Machine structural closure / dense MEP | Toroidal closure, PF/CS integration, final vessel joints, vacuum-boundary completion and dense electrical/I&C work continue. Ordinary field-fit, cable termination, access, vendor-document and rework issues accumulate and consume margin; First Plasma is rebaselined from 31 Mar to 31 May 2031 without changing readiness criteria. | OPG/E&C/HMS/Bechtel/OEMs/project controls; construction-to-commissioning interface agreement governs overlap. | field-change/RFI/TQ/NCR/DCN/ECN records; completion database; updated IMS; turnover and re-entry authorizations. |

# 2030 — Completion production gives way to live-system state management

Working-dataset physical-event volume: Mechanical Completion: 19,138, Turnover: 18,172, Commissioning/Operation: 16,667, Removal/Demobilization: 622, Installation/Mobilization: 388, Site Arrival: 121.

Highest-volume recorded workfront/building locations: F-103 (6,686); H-101 (6,143); Plantwide (5,763); C-101/C-102 (2,806); T-101 (2,716); F-101 (2,304); U-101/U-104 (1,884); U-101/H-101 (1,763); Controlled Buildings (1,716); T-102 (1,675).

## Q1

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| Electrical/utilities | Permanent power expands and switchgear becomes live. Commissioning work management becomes fully operational. More utility systems transfer from Construction to Commissioning; outstanding construction now increasingly occurs inside or beside controlled live boundaries. | OPG Commissioning/work control; E&C completions/field engineering; Bechtel residual construction; OEM/vendor support. | energization and turnover records; PTW/LOTO; post-turnover work requests; punch/NCR closure; restoration evidence. |

## Q2

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| Cooling/HVAC/fire/DCS | Main cooling water, component cooling water and chilled water operate; HVAC pressure zones are established; fire protection reaches permanent configuration; control-room activity shifts from temporary panels to permanent DCS. These systems are now supporting other commissioning work rather than merely being construction deliverables. | OPG Commissioning/Operations Readiness + E&C support + system vendors. | functional test reports; setpoint/configuration records; maintenance history; deficiency/CAP; operations-support acceptance. |

## Q2–Q3

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| T-101/T-102 | Turbine auxiliaries enter pre-/functional commissioning: lube oil, turning gear, condensate/feedwater and condenser auxiliaries. Major turbine assets in the register reach turnover around Apr–May 2030 and commissioning from June onward. There is still no fusion steam or grid synchronization. | OPG Commissioning + E&C conventional-island support + Arabelle/OEM field service. | pre-commissioning flush/cleanliness; lube-oil acceptance; alignment/barring/turning-gear tests; auxiliary-system test reports. |

## Q3

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| C-101/C-102 and F101 vacuum | Cryoplant reaches sustained operation; torus rough-pumpdown/leak campaigns intensify; individual cryogenic circuits and machine I&C enter integrated testing. Temporary construction infrastructure is being retired while configuration-controlled commissioning skids, hoses, jumpers and temporary test boundaries proliferate. | OPG Commissioning + E&C/HMS + IHI/OEM/vacuum vendors; residual contractors under controlled access. | test prerequisites; temporary modification records; vacuum leak data; cryogenic operating/test logs; calibration/configuration records. |

## 14 May–12 Oct

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| H-101 / BHT-401 temporary recirculation workfront | A need for supplemental BHT circulation becomes a configuration-controlled temporary plant lifecycle: need 14 May; Rev A 12 Jun; HMS technology screen 19 Jun; FAT 18 Aug; site receipt 3 Sep; installation 22 Sep; MC 28 Sep; turnover 11 Oct; first controlled campaign 12 Oct. The skid is not 'rental equipment sitting nearby'; it becomes a tagged plant object with support/load path, boundary, custody and evidence obligations. | E&C commissioning/process/mechanical/field engineering; HMS assurance; E.S. Fox / OPG commissioning interface; supplier/fabricator; QA; OPG receiving/work control after turnover. | TEMP-SYS-REQ; temporary design drawing; HMS screen; PO/asset record; FAT; receiving inspection; IWP; MC; turnover dossier; commissioning procedure. |

## Q4

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| F101 machine | Magnet cooldown begins. Late access and repairs now carry cryogenic/vacuum state consequences; work that was once a construction task may require warm-up, venting, isolation, commissioning approval and requalification. The project has become a state-management problem. | OPG Commissioning + HMS/E&C magnet/cryogenic engineering + OEMs + authorized residual construction. | cooldown plan/log; QPS/configuration tests; access/isolation plans; deviations; restoration/requalification. |

# 2031 through 19 April — Residual construction inside an integrated commissioning plant

Working-dataset physical-event volume: Commissioning/Operation: 2,891, Turnover: 1,275, Removal/Demobilization: 501, Mechanical Completion: 302.

Highest-volume recorded workfront/building locations: F-101 (689); C-101/C-102 (533); H-101 (503); F-104 (438); Plantwide (369); Fabrication Shops / Workfronts (305); F-101/F-103 (304); T-102 (275); F-105 (248); F-101/F-102 (234).

## January

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| F101/H-101 and transferred systems | Central solenoid commissioning starts in the working register 15 Jan. BHT-401 temporary spools are removed 6 Jan for permanent BHT modification, temporary configuration is revised to Rev C on 16 Jan, and the skid is reconnected/returned to controlled service on 24 Jan under commissioning work control. | OPG Commissioning/work control -> authorized contractor/field team; E&C design/configuration; HMS assurance where reference limits are implicated. | WO-BHT401-2031-011; revised temporary drawing; post-turnover permit; inspection/restoration; configuration confirmation. |

## February–March

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| Plantwide commissioning workfronts | Magnet energization, vacuum/bakeout/pumpdown, cryogenic operation, machine protection, gas injection/fuelling without tritium, ECH dummy-load/functional work, diagnostics and degraded-mode/integrated control testing progress. Residual construction exists only under defined authorization inside transferred areas. | OPG Commissioning and operations-readiness organization; E&C/HMS/OEM technical support; authorized Bechtel/subcontractor re-entry. | commissioning procedures/reports; deficiency lists; temporary modifications; CAP; maintenance/work orders; readiness evidence. |

## 17 March

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| H-101 / CRS-01 | An operator records vibration higher than remembered; no limit is exceeded. It is a weak field observation, not a deterministic defect finding. | OPG operator/commissioning chain; subsequent engineering/work-management route. | OPLOG-2031-03-17-BHT; local shift knowledge first, then whatever routing the work process creates. |

## 20 March

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| H-101 / CRS-01 | Follow-up walkdown identifies no immediate defect but recommends inspection. The system remains in controlled service; the observation becomes a work-management/configuration antecedent rather than an emergency. | OPG commissioning + E&C field/technical support; HMS depending technical routing. | WALK-BHT401-0320; recommendation/work backlog; any resulting work order. |

## 10 April

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| H-101 / CRS01-RST-L2 | Routine photographic baseline captures restraint geometry/witness marks. Its later forensic importance is not yet known. | Field/commissioning/QA personnel according to photo-survey task. | PHOTO-BHT401-0410, indexed visual evidence. |

## 11 April

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| H-101 / CRS01-RST-L2 | M-88217 is indexed as lateral-restraint inspection/adjustment and CLOSED/APPROVED. At the story cut, the electronic status exists but the authoritative supporting execution package—performer/sign-on, as-found/as-left, parts, dimensions, torque/tension, QC witness and configuration confirmation—cannot be treated as established merely from status. | Work-management/records chain; exact initiator, supervisor, performer and QC identities remain OPEN until evidence establishes them. | M-88217 header/status plus expected but unavailable/uncertain execution evidence. Do not invent a performer. |

## 12 April

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| H-101 / BHT-401 loaded circulation | CRS-01 experiences lateral movement outside the expected envelope. Several hundred kilograms move while an operator is within a potential crushing zone. No injury, radiological release, environmental consequence or loss of licensed safety function occurs. Equipment is isolated and the scene becomes evidence-controlled. | OPG commissioning/work control/HSE; E&C field/engineering; Bechtel interface; QA; relevant contractor/OEM according to scope. | event log; isolation; photographs; witness accounts; test state; configuration identity; evidence preservation. |

## 13–19 April

| Where / workfront | Physical work performed | Execution / authority chain | Primary evidence generated |
| --- | --- | --- | --- |
| Site + records repositories + Toronto/Japan support | Extent-of-condition inspections and evidence reconstruction compare physical restraint condition, photographs, design revisions, work authorization, maintenance history, supplier/vendor information, similar equipment and configuration records. The physical plant and evidence plant are reconstructed separately. No later inquiry conclusion may be projected into this period. | E&C/HMS engineering and assurance; OPG; QA/records; contractor/OEM evidence holders. Yuji operates inside this chain but does not possess project-wide or future knowledge. | EOC records; evidence index; repository searches; technical calculations; interviews/witness information; interim issue logs; readiness/status compression. |

# Monthly field-production ledger derived from the controlled asset/event dataset

These monthly tables are working-dataset reconstructions, not independent canon. They are included because they make the site executable for fiction: they show which buildings/systems and installation organizations are active in the same month. Quarantined lifecycle sequences are excluded from scene-critical inference.

## 2025-05

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z08 | Sitewide / Early Works | EARTHWORKS | Site Arrival | Bird/Bechtel | 141 | TMP-EW-ADT-001; TMP-EW-CMP-001; TMP-EW-DOZ-001; TMP-EW-EXC-001; TMP-EW-FLT-001; TMP-EW-GRD-001; TMP-EW-LDR-001 | 0 |
| Z08/ALL | Site Services / Sitewide | SITE-SERVICES | Site Arrival | Site services | 43 | TMP-VEH-AMB-001; TMP-VEH-BUS-001; TMP-VEH-FIR-001; TMP-VEH-PU-001; TMP-VEH-RES-001; TMP-VEH-SEC-001; TMP-VEH-VAN-001 | 0 |
| Z08/ALL | Construction Support | TEMP-SITE | Installation/Mobilization | Site services | 6 | TMP-FAC-OFF-001; TMP-FAC-OFF-002; TMP-FAC-OFF-003; TMP-FAC-OFF-004; TMP-FAC-OFF-005; TMP-FAC-OFF-006 | 0 |
| Z08/ALL | Construction Support | TEMP-SITE | Site Arrival | Site services | 6 | TMP-FAC-OFF-001; TMP-FAC-OFF-002; TMP-FAC-OFF-003; TMP-FAC-OFF-004; TMP-FAC-OFF-005; TMP-FAC-OFF-006 | 0 |

## 2025-06

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Sitewide | TEMP-UTIL | Site Arrival | Bechtel/site services | 208 | TMP-AIR-CMP-001; TMP-AIR-DRY-001; TMP-HTR-BLR-001; TMP-HVAC-AHU-001; TMP-HVAC-CHL-001; TMP-PWR-GEN-001; TMP-PWR-LGT-001 | 0 |
| Z08/ALL | Site Services / Sitewide | SITE-SERVICES | Site Arrival | Site services | 39 | TMP-VEH-BUS-010; TMP-VEH-PU-010; TMP-VEH-VAN-010; TMP-VEH-BUS-011; TMP-VEH-PU-011; TMP-VEH-VAN-011; TMP-VEH-BUS-012 | 0 |
| Z08 | Sitewide / Early Works | EARTHWORKS | Site Arrival | Bird/Bechtel | 30 | TMP-EW-ADT-018; TMP-EW-EXC-018; TMP-EW-ADT-019; TMP-EW-EXC-019; TMP-EW-ADT-020; TMP-EW-EXC-020; TMP-EW-ADT-021 | 0 |
| Z08/ALL | Construction Support | TEMP-SITE | Installation/Mobilization | Site services | 15 | TMP-FAC-OFF-007; TMP-FAC-OFF-008; TMP-FAC-OFF-009; TMP-FAC-OFF-010; TMP-FAC-OFF-011; TMP-FAC-OFF-012; TMP-FAC-OFF-013 | 0 |
| Z08/ALL | Construction Support | TEMP-SITE | Site Arrival | Site services | 15 | TMP-FAC-OFF-007; TMP-FAC-OFF-008; TMP-FAC-OFF-009; TMP-FAC-OFF-010; TMP-FAC-OFF-011; TMP-FAC-OFF-012; TMP-FAC-OFF-013 | 0 |
| Z08 | Construction Support | TEMP-SITE | Site Arrival | Site services | 10 | TMP-FAC-LCH-001; TMP-FAC-LCH-002; TMP-FAC-LCH-003; TMP-FAC-LCH-004; TMP-FAC-LCH-005; TMP-FAC-LCH-006; TMP-FAC-LCH-007 | 0 |
| Z08 | Construction Support | TEMP-SITE | Installation/Mobilization | Site services | 10 | TMP-FAC-LCH-001; TMP-FAC-LCH-002; TMP-FAC-LCH-003; TMP-FAC-LCH-004; TMP-FAC-LCH-005; TMP-FAC-LCH-006; TMP-FAC-LCH-007 | 0 |

## 2025-07

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Sitewide | TEMP-UTIL | Site Arrival | Bechtel/site services | 76 | TMP-PWR-LGT-031; TMP-PWR-PNL-031; TMP-PWR-SWB-031; TMP-PWR-TRF-031; TMP-PWR-LGT-032; TMP-PWR-PNL-032; TMP-PWR-SWB-032 | 0 |
| Z08/ALL | Construction Support | TEMP-SITE | Site Arrival | Site services | 16 | TMP-FAC-OFF-022; TMP-FAC-OFF-023; TMP-FAC-OFF-024; TMP-FAC-OFF-025; TMP-FAC-OFF-026; TMP-FAC-OFF-027; TMP-FAC-OFF-028 | 0 |
| Z08/ALL | Construction Support | TEMP-SITE | Installation/Mobilization | Site services | 15 | TMP-FAC-OFF-022; TMP-FAC-OFF-023; TMP-FAC-OFF-024; TMP-FAC-OFF-025; TMP-FAC-OFF-026; TMP-FAC-OFF-027; TMP-FAC-OFF-028 | 0 |
| Z08/ALL | Site Services / Sitewide | SITE-SERVICES | Site Arrival | Site services | 15 | TMP-VEH-PU-025; TMP-VEH-PU-026; TMP-VEH-PU-027; TMP-VEH-PU-028; TMP-VEH-PU-029; TMP-VEH-PU-030; TMP-VEH-PU-031 | 0 |
| Z06 | Lake Ontario / Marine Works | MARINE-CONSTRUCTION | Site Arrival | Bird/marine subcontractor | 14 | TMP-MAR-BRG-001; TMP-MAR-CRB-001; TMP-MAR-DIV-001; TMP-MAR-SCW-001; TMP-MAR-SPD-001; TMP-MAR-SUR-001; TMP-MAR-TUG-001 | 0 |
| Z08 | Main Logistics Gate | TEMP-SITE | Site Arrival | Logistics contractor | 4 | TMP-FAC-WBR-001; TMP-FAC-WBR-002; TMP-FAC-WBR-003; TMP-FAC-WBR-004 | 0 |
| Z08 | Main Logistics Gate | TEMP-SITE | Installation/Mobilization | Logistics contractor | 4 | TMP-FAC-WBR-001; TMP-FAC-WBR-002; TMP-FAC-WBR-003; TMP-FAC-WBR-004 | 0 |
| Z08 | Main Logistics Gate | TEMP-SITE | Mechanical Completion | Logistics contractor | 3 | TMP-FAC-WBR-001; TMP-FAC-WBR-002; TMP-FAC-WBR-003 | 0 |

## 2025-08

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z01/Z02/Z03 | Excavation Zones | TEMP-DEWATER | Site Arrival | Bird/Bechtel | 74 | TMP-DW-DWP-001; TMP-DW-FLT-001; TMP-DW-SET-001; TMP-DW-SMP-001; TMP-DW-WLP-001; TMP-DW-WTS-001; TMP-DW-DWP-002 | 0 |
| ALL | Sitewide | TEMP-UTIL | Site Arrival | Bechtel/site services | 50 | TMP-PWR-LGT-062; TMP-PWR-PNL-062; TMP-PWR-LGT-063; TMP-PWR-PNL-063; TMP-PWR-LGT-064; TMP-PWR-PNL-064; TMP-PWR-LGT-065 | 0 |
| Z08 | Construction Production Area | CIVIL-PRODUCTION | Site Arrival | Bechtel/Aecon | 34 | TMP-CON-BP-001; TMP-CON-CP-001; TMP-CON-ICE-001; TMP-CON-LAB-001; TMP-CON-MIX-001; TMP-CON-SP-001; TMP-GRT-MIX-001 | 0 |
| Z08/ALL | Construction Support | TEMP-SITE | Installation/Mobilization | Site services | 16 | TMP-FAC-OFF-037; TMP-FAC-OFF-038; TMP-FAC-OFF-039; TMP-FAC-OFF-040; TMP-FAC-OFF-041; TMP-FAC-OFF-042; TMP-FAC-OFF-043 | 0 |
| Z08/ALL | Site Services / Sitewide | SITE-SERVICES | Site Arrival | Site services | 16 | TMP-VEH-PU-040; TMP-VEH-PU-041; TMP-VEH-PU-042; TMP-VEH-PU-043; TMP-VEH-PU-044; TMP-VEH-PU-045; TMP-VEH-PU-046 | 0 |
| Z08/ALL | Construction Support | TEMP-SITE | Site Arrival | Site services | 15 | TMP-FAC-OFF-038; TMP-FAC-OFF-039; TMP-FAC-OFF-040; TMP-FAC-OFF-041; TMP-FAC-OFF-042; TMP-FAC-OFF-043; TMP-FAC-OFF-044 | 0 |
| Z08 | Main Logistics Gate | TEMP-SITE | Commissioning/Operation | Logistics contractor | 1 | TMP-FAC-WBR-004 | 0 |
| Z08 | Main Logistics Gate | TEMP-SITE | Mechanical Completion | Logistics contractor | 1 | TMP-FAC-WBR-004 | 0 |

## 2025-09

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z01/Z02/Z03 | Excavation Zones | TEMP-DEWATER | Site Arrival | Bird/Bechtel | 32 | TMP-DW-DWP-017; TMP-DW-SMP-017; TMP-DW-WLP-017; TMP-DW-DWP-018; TMP-DW-SMP-018; TMP-DW-WLP-018; TMP-DW-DWP-019 | 0 |
| Z01/Z02/Z03 | Excavations | GROUNDWORKS | Installation/Mobilization | Aecon | 15 | TMP-GEO-DRL-001; TMP-GEO-DRL-002; TMP-GEO-DRL-003; TMP-GEO-DRL-004; TMP-GEO-RBL-001; TMP-GEO-DRL-005; TMP-GEO-RBL-002 | 0 |
| Z01/Z02/Z03 | Excavations | GROUNDWORKS | Site Arrival | Aecon | 15 | TMP-GEO-DRL-001; TMP-GEO-DRL-002; TMP-GEO-DRL-003; TMP-GEO-DRL-004; TMP-GEO-RBL-001; TMP-GEO-DRL-005; TMP-GEO-RBL-002 | 0 |
| Z08/ALL | Site Services / Sitewide | SITE-SERVICES | Site Arrival | Site services | 15 | TMP-VEH-PU-056; TMP-VEH-PU-057; TMP-VEH-PU-058; TMP-VEH-PU-059; TMP-VEH-PU-060; TMP-VEH-PU-061; TMP-VEH-PU-062 | 0 |
| Z08 | Construction Production Area | CIVIL-PRODUCTION | Site Arrival | Bechtel/Aecon | 14 | TMP-CON-CP-005; TMP-CON-MIX-005; TMP-GRT-MIX-005; TMP-RBR-CPL-005; TMP-CON-CP-006; TMP-CON-MIX-006; TMP-GRT-MIX-006 | 0 |
| Z08/ALL | Construction Support | TEMP-SITE | Installation/Mobilization | Site services | 12 | TMP-FAC-OFF-053; TMP-FAC-OFF-054; TMP-FAC-OFF-055; TMP-FAC-OFF-056; TMP-FAC-OFF-057; TMP-FAC-OFF-058; TMP-FAC-OFF-059 | 0 |
| Z08/ALL | Construction Support | TEMP-SITE | Site Arrival | Site services | 12 | TMP-FAC-OFF-053; TMP-FAC-OFF-054; TMP-FAC-OFF-055; TMP-FAC-OFF-056; TMP-FAC-OFF-057; TMP-FAC-OFF-058; TMP-FAC-OFF-059 | 0 |
| ALL | Sitewide | TEMP-UTIL | Site Arrival | Bechtel/site services | 4 | TMP-PWR-LGT-093; TMP-PWR-LGT-094; TMP-PWR-LGT-095; TMP-PWR-LGT-096 | 0 |

## 2025-10

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Sitewide / Defined Lift Zones | LIFTING-HANDLING | Site Arrival | Bechtel/Aecon/Kiewit | 100 | TMP-CRN-AT10-001; TMP-CRN-AT20-001; TMP-CRN-AT30-001; TMP-CRN-CC10-001; TMP-CRN-CC18-001; TMP-CRN-CC40-001; TMP-CRN-CC65-001 | 0 |
| Z01/Z02/Z03 | Excavation Zones | TEMP-DEWATER | Site Arrival | Bird/Bechtel | 24 | TMP-DW-DWP-032; TMP-DW-SMP-032; TMP-DW-DWP-033; TMP-DW-SMP-033; TMP-DW-DWP-034; TMP-DW-SMP-034; TMP-DW-DWP-035 | 0 |
| Z01/Z02/Z03 | Excavations | GROUNDWORKS | Site Arrival | Aecon | 16 | TMP-GEO-SHR-001; TMP-GEO-SHR-002; TMP-GEO-SHR-003; TMP-GEO-SHR-004; TMP-GEO-SHR-005; TMP-GEO-SHR-006; TMP-GEO-SHR-007 | 0 |
| Z01/Z02/Z03 | Excavations | GROUNDWORKS | Installation/Mobilization | Aecon | 14 | TMP-GEO-SHR-001; TMP-GEO-SHR-002; TMP-GEO-SHR-003; TMP-GEO-SHR-004; TMP-GEO-SHR-005; TMP-GEO-SHR-006; TMP-GEO-SHR-007 | 0 |
| Z08 | Construction Production Area | CIVIL-PRODUCTION | Site Arrival | Bechtel/Aecon | 6 | TMP-CON-MIX-011; TMP-CON-MIX-012; TMP-CON-MIX-013; TMP-CON-MIX-014; TMP-CON-MIX-015; TMP-CON-MIX-016 | 0 |
| Z08/ALL | Site Services / Sitewide | SITE-SERVICES | Site Arrival | Site services | 2 | TMP-VEH-PU-071; TMP-VEH-PU-072 | 0 |
| Z01/Z02/Z03 | Excavations | GROUNDWORKS | Installation/Mobilization | Aecon | 1 | TMP-GEO-RBL-008 | 0 |
| Z01/Z02/Z03 | Excavations | GROUNDWORKS | Site Arrival | Aecon | 1 | TMP-GEO-RBL-008 | 0 |

## 2025-11

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Sitewide / Defined Lift Zones | LIFTING-HANDLING | Site Arrival | Bechtel/Aecon/Kiewit | 48 | TMP-CRN-RT-012; TMP-MH-BML-012; TMP-MH-FLT-012; TMP-MH-MST-012; TMP-MH-SCI-012; TMP-MH-TLH-012; TMP-CRN-RT-013 | 0 |
| Z01/Z02/Z03 | Excavation Zones | TEMP-DEWATER | Site Arrival | Bird/Bechtel | 10 | TMP-DW-SMP-047; TMP-DW-SMP-048; TMP-DW-SMP-049; TMP-DW-SMP-050; TMP-DW-SMP-051; TMP-DW-SMP-052; TMP-DW-SMP-053 | 0 |
| Z01/Z02/Z03 | Excavations | GROUNDWORKS | Installation/Mobilization | Aecon | 10 | TMP-GEO-SHR-015; TMP-GEO-SHR-016; TMP-GEO-SHR-017; TMP-GEO-SHR-018; TMP-GEO-SHR-019; TMP-GEO-SHR-020; TMP-GEO-SHR-021 | 0 |
| Z01/Z02/Z03 | Excavations | GROUNDWORKS | Site Arrival | Aecon | 8 | TMP-GEO-SHR-017; TMP-GEO-SHR-018; TMP-GEO-SHR-019; TMP-GEO-SHR-020; TMP-GEO-SHR-021; TMP-GEO-SHR-022; TMP-GEO-SHR-023 | 0 |
| Z08 | Construction Production Area | CIVIL-PRODUCTION | Site Arrival | Bechtel/Aecon | 6 | TMP-CON-MIX-017; TMP-CON-MIX-018; TMP-CON-MIX-019; TMP-CON-MIX-020; TMP-CON-MIX-021; TMP-CON-MIX-022 | 0 |

## 2025-12

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Sitewide / Defined Lift Zones | LIFTING-HANDLING | Site Arrival | Bechtel/Aecon/Kiewit | 32 | TMP-MH-BML-022; TMP-MH-FLT-022; TMP-MH-SCI-022; TMP-MH-TLH-022; TMP-MH-BML-023; TMP-MH-FLT-023; TMP-MH-SCI-023 | 0 |
| Z08 | Construction Production Area | CIVIL-PRODUCTION | Site Arrival | Bechtel/Aecon | 6 | TMP-CON-MIX-023; TMP-CON-MIX-024; TMP-CON-MIX-025; TMP-CON-MIX-026; TMP-CON-MIX-027; TMP-CON-MIX-028 | 0 |

## 2026-01

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Fabrication Shops / Workfronts | FAB-NDE-MET | Site Arrival | Bechtel/Aecon/Kiewit/E.S. Fox | 200 | TMP-FAB-BEV-001; TMP-FAB-PBM-001; TMP-FAB-PSB-001; TMP-MET-LT-001; TMP-MET-PGM-001; TMP-MET-SCN-001; TMP-MET-TS-001 | 0 |
| ALL | Sitewide | TEMP-ACCESS | Site Arrival | Specialty contractor | 117 | TMP-ACC-MWP-001; TMP-ACC-SCF-001; TMP-ACC-TPL-001; TMP-ACC-TST-001; TMP-ACC-MWP-002; TMP-ACC-SCF-002; TMP-ACC-TPL-002 | 0 |
| ALL | Sitewide / Defined Lift Zones | LIFTING-HANDLING | Site Arrival | Bechtel/Aecon/Kiewit | 20 | TMP-MH-BML-032; TMP-MH-SCI-032; TMP-MH-BML-033; TMP-MH-SCI-033; TMP-MH-BML-034; TMP-MH-SCI-034; TMP-MH-BML-035 | 0 |
| Z01/Z02/Z03/Z04 | Major concrete workfronts | GROUNDWORKS | Site Arrival | Aecon | 16 | TMP-GEO-FRM-001; TMP-GEO-FRM-002; TMP-GEO-FRM-003; TMP-GEO-FRM-004; TMP-GEO-FRM-005; TMP-GEO-FRM-006; TMP-GEO-FRM-007 | 0 |
| Z01/Z02/Z03/Z04 | Major concrete workfronts | GROUNDWORKS | Installation/Mobilization | Aecon | 15 | TMP-GEO-FRM-001; TMP-GEO-FRM-002; TMP-GEO-FRM-003; TMP-GEO-FRM-004; TMP-GEO-FRM-005; TMP-GEO-FRM-006; TMP-GEO-FRM-007 | 0 |

## 2026-02

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Fabrication Shops / Workfronts | FAB-NDE-MET | Site Arrival | Bechtel/Aecon/Kiewit/E.S. Fox | 62 | TMP-MET-LT-017; TMP-MET-TS-017; TMP-NDE-PT-017; TMP-NDE-UT-017; TMP-WLD-GTA-017; TMP-WLD-ORB-017; TMP-WLD-PWHT-017 | 0 |
| ALL | Sitewide | TEMP-ACCESS | Site Arrival | Specialty contractor | 42 | TMP-ACC-SCF-032; TMP-ACC-TPL-032; TMP-ACC-TST-032; TMP-ACC-SCF-033; TMP-ACC-TPL-033; TMP-ACC-TST-033; TMP-ACC-SCF-034 | 0 |
| ALL | Sitewide / Defined Lift Zones | LIFTING-HANDLING | Site Arrival | Bechtel/Aecon/Kiewit | 17 | TMP-MH-BML-042; TMP-MH-SCI-042; TMP-MH-BML-043; TMP-MH-SCI-043; TMP-MH-BML-044; TMP-MH-SCI-044; TMP-MH-BML-045 | 0 |
| Z01/Z02/Z03/Z04 | Major concrete workfronts | GROUNDWORKS | Installation/Mobilization | Aecon | 14 | TMP-GEO-FRM-016; TMP-GEO-FRM-017; TMP-GEO-FRM-018; TMP-GEO-FRM-019; TMP-GEO-FRM-020; TMP-GEO-FRM-021; TMP-GEO-FRM-022 | 0 |
| Z01/Z02/Z03/Z04 | Major concrete workfronts | GROUNDWORKS | Site Arrival | Aecon | 14 | TMP-GEO-FRM-017; TMP-GEO-FRM-018; TMP-GEO-FRM-019; TMP-GEO-FRM-020; TMP-GEO-FRM-021; TMP-GEO-FRM-022; TMP-GEO-FRM-023 | 0 |

## 2026-03

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Sitewide | TEMP-ACCESS | Site Arrival | Specialty contractor | 31 | TMP-ACC-SCF-060; TMP-ACC-SCF-061; TMP-ACC-SCF-062; TMP-ACC-SCF-063; TMP-ACC-SCF-064; TMP-ACC-SCF-065; TMP-ACC-SCF-066 | 0 |
| ALL | Fabrication Shops / Workfronts | FAB-NDE-MET | Site Arrival | Bechtel/Aecon/Kiewit/E.S. Fox | 30 | TMP-WLD-GTA-031; TMP-WLD-SMA-031; TMP-WLD-GTA-032; TMP-WLD-SMA-032; TMP-WLD-GTA-033; TMP-WLD-SMA-033; TMP-WLD-GTA-034 | 0 |
| ALL | Sitewide / Defined Lift Zones | LIFTING-HANDLING | Site Arrival | Bechtel/Aecon/Kiewit | 9 | TMP-MH-SCI-052; TMP-MH-SCI-053; TMP-MH-SCI-054; TMP-MH-SCI-055; TMP-MH-SCI-056; TMP-MH-SCI-057; TMP-MH-SCI-058 | 0 |
| Z01/Z02/Z03/Z04 | Major concrete workfronts | GROUNDWORKS | Installation/Mobilization | Aecon | 7 | TMP-GEO-FRM-030; TMP-GEO-FRM-031; TMP-GEO-FRM-032; TMP-GEO-FRM-033; TMP-GEO-FRM-034; TMP-GEO-FRM-035; TMP-GEO-FRM-036 | 0 |
| Z01/Z02/Z03/Z04 | Major concrete workfronts | GROUNDWORKS | Site Arrival | Aecon | 6 | TMP-GEO-FRM-031; TMP-GEO-FRM-032; TMP-GEO-FRM-033; TMP-GEO-FRM-034; TMP-GEO-FRM-035; TMP-GEO-FRM-036 | 0 |

## 2026-04

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Sitewide | TEMP-ACCESS | Site Arrival | Specialty contractor | 30 | TMP-ACC-SCF-091; TMP-ACC-SCF-092; TMP-ACC-SCF-093; TMP-ACC-SCF-094; TMP-ACC-SCF-095; TMP-ACC-SCF-096; TMP-ACC-SCF-097 | 0 |
| ALL | Fabrication Shops / Workfronts | FAB-NDE-MET | Site Arrival | Bechtel/Aecon/Kiewit/E.S. Fox | 18 | TMP-WLD-GTA-046; TMP-WLD-SMA-046; TMP-WLD-GTA-047; TMP-WLD-SMA-047; TMP-WLD-GTA-048; TMP-WLD-SMA-048; TMP-WLD-SMA-049 | 0 |

## 2026-05

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Sitewide | TEMP-ACCESS | Site Arrival | Specialty contractor | 31 | TMP-ACC-SCF-121; TMP-ACC-SCF-122; TMP-ACC-SCF-123; TMP-ACC-SCF-124; TMP-ACC-SCF-125; TMP-ACC-SCF-126; TMP-ACC-SCF-127 | 0 |
| Z06 | Intake Tunnel | TUNNEL-CONSTRUCTION | Site Arrival | Tunnel contractor | 4 | TMP-TBM-I-MAIN-01; TMP-TBM-I-CUT-01; TMP-TBM-I-DRV-01; TMP-TBM-I-THR-01 | 0 |

## 2026-06

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Sitewide | TEMP-ACCESS | Site Arrival | Specialty contractor | 29 | TMP-ACC-SCF-152; TMP-ACC-SCF-153; TMP-ACC-SCF-154; TMP-ACC-SCF-155; TMP-ACC-SCF-156; TMP-ACC-SCF-157; TMP-ACC-SCF-158 | 0 |
| Z06 | Intake Tunnel | TUNNEL-CONSTRUCTION | Site Arrival | Tunnel contractor | 7 | TMP-TBM-I-ERE-01; TMP-TBM-I-CON-01; TMP-TBM-I-SEP-01; TMP-TBM-I-SLR-01; TMP-TBM-I-SEG-01; TMP-TBM-I-GRS-01; TMP-TBM-I-VEN-01 | 0 |

## 2026-07

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z06 | Intake Tunnel | TUNNEL-CONSTRUCTION | Installation/Mobilization | Tunnel contractor | 13 | TMP-TBM-I-MAIN-01; TMP-TBM-I-CUT-01; TMP-TBM-I-DRV-01; TMP-TBM-I-THR-01; TMP-TBM-I-ERE-01; TMP-TBM-I-CON-01; TMP-TBM-I-SEP-01 | 0 |
| Z06 | Outfall Tunnel | TUNNEL-CONSTRUCTION | Site Arrival | Tunnel contractor | 8 | TMP-TBM-O-MAIN-01; TMP-TBM-O-CUT-01; TMP-TBM-O-DRV-01; TMP-TBM-O-THR-01; TMP-TBM-O-ERE-01; TMP-TBM-O-CON-01; TMP-TBM-O-SEP-01 | 0 |
| Z06 | Intake Tunnel | TUNNEL-CONSTRUCTION | Site Arrival | Tunnel contractor | 5 | TMP-TBM-I-TRN-01; TMP-TBM-I-LOC-01; TMP-TBM-I-RES-01; TMP-TBM-I-TRF-01; TMP-TBM-I-PMP-01 | 0 |

## 2026-08

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z06 | Intake Tunnel | TUNNEL-CONSTRUCTION | Mechanical Completion | Tunnel contractor | 16 | TMP-TBM-I-CON-01; TMP-TBM-I-CUT-01; TMP-TBM-I-DRV-01; TMP-TBM-I-ERE-01; TMP-TBM-I-GRS-01; TMP-TBM-I-LOC-01; TMP-TBM-I-MAIN-01 | 0 |
| Z06 | Outfall Tunnel | TUNNEL-CONSTRUCTION | Site Arrival | Tunnel contractor | 7 | TMP-TBM-O-SEG-01; TMP-TBM-O-GRS-01; TMP-TBM-O-VEN-01; TMP-TBM-O-TRN-01; TMP-TBM-O-LOC-01; TMP-TBM-O-RES-01; TMP-TBM-O-TRF-01 | 0 |
| Z06 | Outfall Tunnel | TUNNEL-CONSTRUCTION | Installation/Mobilization | Tunnel contractor | 6 | TMP-TBM-O-MAIN-01; TMP-TBM-O-CUT-01; TMP-TBM-O-DRV-01; TMP-TBM-O-THR-01; TMP-TBM-O-ERE-01; TMP-TBM-O-CON-01 | 0 |
| Z06 | Intake Tunnel | TUNNEL-CONSTRUCTION | Installation/Mobilization | Tunnel contractor | 3 | TMP-TBM-I-RES-01; TMP-TBM-I-TRF-01; TMP-TBM-I-PMP-01 | 0 |

## 2026-09

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z06 | Intake Tunnel | TUNNEL-CONSTRUCTION | Commissioning/Operation | Tunnel contractor | 16 | TMP-TBM-I-CON-01; TMP-TBM-I-CUT-01; TMP-TBM-I-DRV-01; TMP-TBM-I-ERE-01; TMP-TBM-I-GRS-01; TMP-TBM-I-LOC-01; TMP-TBM-I-MAIN-01 | 0 |
| Z06 | Outfall Tunnel | TUNNEL-CONSTRUCTION | Installation/Mobilization | Tunnel contractor | 10 | TMP-TBM-O-SEP-01; TMP-TBM-O-SLR-01; TMP-TBM-O-SEG-01; TMP-TBM-O-GRS-01; TMP-TBM-O-VEN-01; TMP-TBM-O-TRN-01; TMP-TBM-O-LOC-01 | 0 |
| Z06 | Outfall Tunnel | TUNNEL-CONSTRUCTION | Site Arrival | Tunnel contractor | 1 | TMP-TBM-O-PMP-01 | 0 |

## 2026-10

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z06 | Outfall Tunnel | TUNNEL-CONSTRUCTION | Commissioning/Operation | Tunnel contractor | 16 | TMP-TBM-O-CON-01; TMP-TBM-O-CUT-01; TMP-TBM-O-DRV-01; TMP-TBM-O-ERE-01; TMP-TBM-O-GRS-01; TMP-TBM-O-LOC-01; TMP-TBM-O-MAIN-01 | 0 |
| Z06 | Outfall Tunnel | TUNNEL-CONSTRUCTION | Mechanical Completion | Tunnel contractor | 16 | TMP-TBM-O-CON-01; TMP-TBM-O-CUT-01; TMP-TBM-O-DRV-01; TMP-TBM-O-ERE-01; TMP-TBM-O-GRS-01; TMP-TBM-O-LOC-01; TMP-TBM-O-MAIN-01 | 0 |

## 2026-12

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z06/Z08 | Marine Terminal / Heavy Haul Route / Laydown | HEAVY-LOGISTICS | Site Arrival | Bechtel logistics | 56 | TMP-LOG-FBT-001; TMP-LOG-LBT-001; TMP-LOG-PMT-001; TMP-LOG-PTR-001; TMP-LOG-SPMT-001; TMP-LOG-STR-001; TMP-LOG-YTR-001 | 0 |

## 2027-01

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z06/Z08 | Marine Terminal / Heavy Haul Route / Laydown | HEAVY-LOGISTICS | Site Arrival | Bechtel logistics | 22 | TMP-LOG-FBT-009; TMP-LOG-LBT-009; TMP-LOG-PTR-009; TMP-LOG-SPMT-009; TMP-LOG-YTR-009; TMP-LOG-FBT-010; TMP-LOG-LBT-010 | 0 |

## 2027-02

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z06/Z08 | Marine Terminal / Heavy Haul Route / Laydown | HEAVY-LOGISTICS | Site Arrival | Bechtel logistics | 7 | TMP-LOG-FBT-017; TMP-LOG-FBT-018; TMP-LOG-FBT-019; TMP-LOG-FBT-020; TMP-LOG-FBT-021; TMP-LOG-FBT-022; TMP-LOG-FBT-023 | 0 |
| Z01-A | F-106 Assembly Hall / F-101 | PERMANENT-HEAVY-LIFT | Site Arrival | Kiewit/OEM | 2 | LFT-F106-HBC-01; LFT-F106-HBC-02 | 0 |
| Z01-A | F-106 Assembly Hall | PERMANENT-HEAVY-LIFT | Site Arrival | Kiewit/OEM | 1 | LFT-F106-AUX-01 | 0 |
| Z01-A | F-106 Assembly Hall / F-101 | PERMANENT-HEAVY-LIFT | Installation/Mobilization | Kiewit/OEM | 1 | LFT-F106-HBC-01 | 0 |
| Z01-A | F-106 Assembly Hall | TOKAMAK-ASSEMBLY-TOOLING | Site Arrival | Kiewit/MHI/HMS assembly team | 1 | AST-SAF-01 | 0 |

## 2027-03

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z06/Z08 | Marine Terminal / Heavy Haul Route / Laydown | HEAVY-LOGISTICS | Site Arrival | Bechtel logistics | 7 | TMP-LOG-FBT-024; TMP-LOG-FBT-025; TMP-LOG-FBT-026; TMP-LOG-FBT-027; TMP-LOG-FBT-028; TMP-LOG-FBT-029; TMP-LOG-FBT-030 | 0 |
| Z01 | F-106/F-101 | TOKAMAK-ASSEMBLY-TOOLING | Site Arrival | Kiewit/HMS/MHI assembly team | 2 | AST-UPD-01; AST-UPD-02 | 0 |
| Z01 | F-106/F-101 | TOKAMAK-ASSEMBLY-TOOLING | Installation/Mobilization | Kiewit/HMS/MHI assembly team | 2 | AST-UPD-01; AST-UPD-02 | 0 |
| Z01-A | F-106 Assembly Hall | PERMANENT-HEAVY-LIFT | Installation/Mobilization | Kiewit/OEM | 1 | LFT-F106-AUX-01 | 0 |
| Z01-A | F-106 Assembly Hall | PERMANENT-HEAVY-LIFT | Site Arrival | Kiewit/OEM | 1 | LFT-F106-AUX-02 | 0 |
| Z01-A | F-106 Assembly Hall | TOKAMAK-ASSEMBLY-TOOLING | Site Arrival | Kiewit/MHI/HMS assembly team | 1 | AST-SAF-02 | 0 |
| Z01-A | F-106 Assembly Hall / F-101 | PERMANENT-HEAVY-LIFT | Installation/Mobilization | Kiewit/OEM | 1 | LFT-F106-HBC-02 | 0 |

## 2027-04

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z01 | F-106/F-101 | TOKAMAK-ASSEMBLY-TOOLING | Installation/Mobilization | Kiewit/HMS/MHI assembly team | 2 | AST-SLT-01; AST-DCHLB-01 | 0 |
| Z01 | F-106/F-101 | TOKAMAK-ASSEMBLY-TOOLING | Site Arrival | Kiewit/HMS/MHI assembly team | 2 | AST-SLT-01; AST-DCHLB-01 | 0 |
| Z01-A | F-106 Assembly Hall | TOKAMAK-ASSEMBLY-TOOLING | Installation/Mobilization | Kiewit/MHI/HMS assembly team | 2 | AST-SAF-01; AST-SAF-02 | 0 |
| Z01-A | F-106 Assembly Hall | TOKAMAK-ASSEMBLY-TOOLING | Site Arrival | Kiewit/MHI/HMS assembly team | 2 | AST-SAF-03; AST-SAF-04 | 0 |
| Z01-A | F-106 Assembly Hall | PERMANENT-HEAVY-LIFT | Installation/Mobilization | Kiewit/OEM | 1 | LFT-F106-AUX-02 | 0 |

## 2027-05

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z01 | F-106/F-101 | TOKAMAK-ASSEMBLY-TOOLING | Mechanical Completion | Kiewit/HMS/MHI assembly team | 2 | AST-UPD-01; AST-UPD-02 | 0 |
| Z01 | F-106/F-101 | TOKAMAK-ASSEMBLY-TOOLING | Installation/Mobilization | Kiewit/HMS/MHI assembly team | 1 | AST-IPAT-01 | 0 |
| Z01 | F-106/F-101 | TOKAMAK-ASSEMBLY-TOOLING | Site Arrival | Kiewit/HMS/MHI assembly team | 1 | AST-IPAT-01 | 0 |
| Z01 | F-106/F-101 | TOKAMAK-ASSEMBLY-TOOLING | Turnover | Kiewit/HMS/MHI assembly team | 1 | AST-UPD-01 | 0 |
| Z01-A | F-106 Assembly Hall | TOKAMAK-ASSEMBLY-TOOLING | Installation/Mobilization | Kiewit/MHI/HMS assembly team | 1 | AST-SAF-03 | 0 |

## 2027-06

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z08 | Sitewide / Early Works | EARTHWORKS | Removal/Demobilization | Bird/Bechtel | 165 | TMP-EW-ADT-001; TMP-EW-CMP-001; TMP-EW-DOZ-001; TMP-EW-EXC-001; TMP-EW-FLT-001; TMP-EW-GRD-001; TMP-EW-LDR-001 | 0 |
| Z01 | F-106/F-101 | TOKAMAK-ASSEMBLY-TOOLING | Commissioning/Operation | Kiewit/HMS/MHI assembly team | 2 | AST-UPD-01; AST-UPD-02 | 0 |
| Z01 | F-106/F-101 | TOKAMAK-ASSEMBLY-TOOLING | Mechanical Completion | Kiewit/HMS/MHI assembly team | 2 | AST-SLT-01; AST-DCHLB-01 | 0 |
| Z01 | F-106/F-101 | TOKAMAK-ASSEMBLY-TOOLING | Installation/Mobilization | Kiewit/HMS/MHI assembly team | 2 | AST-PFLB-01; AST-PFLB-02 | 0 |
| Z01 | F-106/F-101 | TOKAMAK-ASSEMBLY-TOOLING | Site Arrival | Kiewit/HMS/MHI assembly team | 2 | AST-PFLB-01; AST-PFLB-02 | 0 |
| Z01 | F-106/F-101 | TOKAMAK-ASSEMBLY-TOOLING | Turnover | Kiewit/HMS/MHI assembly team | 2 | AST-UPD-02; AST-SLT-01 | 0 |
| Z01-A | F-106 Assembly Hall | PERMANENT-HEAVY-LIFT | Mechanical Completion | Kiewit/OEM | 2 | LFT-F106-AUX-01; LFT-F106-AUX-02 | 0 |
| Z01-A | F-106 Assembly Hall | TOKAMAK-ASSEMBLY-TOOLING | Installation/Mobilization | Kiewit/MHI/HMS assembly team | 1 | AST-SAF-04 | 0 |

## 2027-07

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z07/Z05 | E-101/E-102/E-103/E-104/E-105 | ELECTRICAL | Site Arrival | E.S. Fox/OEM | 59 | APS-821-TR-001; APS-822-SWG-001; APS-823-SWG-001; APS-824-MCC-001; DCP-841-BAT-001; DCP-842-CHR-001; DCP-843-UPS-001 | 0 |
| Z08 | Sitewide / Early Works | EARTHWORKS | Removal/Demobilization | Bird/Bechtel | 6 | TMP-EW-ADT-031; TMP-EW-ADT-032; TMP-EW-ADT-033; TMP-EW-ADT-034; TMP-EW-ADT-035; TMP-EW-ADT-036 | 0 |
| Z01-A | F-106 Assembly Hall | TOKAMAK-ASSEMBLY-TOOLING | Mechanical Completion | Kiewit/MHI/HMS assembly team | 3 | AST-SAF-01; AST-SAF-02; AST-SAF-03 | 0 |
| Z01 | F-106/F-101 | TOKAMAK-ASSEMBLY-TOOLING | Commissioning/Operation | Kiewit/HMS/MHI assembly team | 2 | AST-SLT-01; AST-DCHLB-01 | 0 |
| Z01 | F-106/F-101 | TOKAMAK-ASSEMBLY-TOOLING | Turnover | Kiewit/HMS/MHI assembly team | 2 | AST-DCHLB-01; AST-IPAT-01 | 0 |
| Z01-A | F-106 Assembly Hall / F-101 | PERMANENT-HEAVY-LIFT | Mechanical Completion | Kiewit/OEM | 2 | LFT-F106-HBC-01; LFT-F106-HBC-02 | 0 |
| Z01 | F-106/F-101 | TOKAMAK-ASSEMBLY-TOOLING | Mechanical Completion | Kiewit/HMS/MHI assembly team | 1 | AST-IPAT-01 | 0 |

## 2027-08

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z07/Z05 | E-101/E-102/E-103/E-104/E-105 | ELECTRICAL | Site Arrival | E.S. Fox/OEM | 34 | APS-822-SWG-006; APS-823-SWG-006; APS-824-MCC-006; DCP-842-CHR-006; DCP-843-UPS-006; SWY-811-CB-006; SWY-812-DS-006 | 0 |
| Z01-A | F-106 Assembly Hall | TOKAMAK-ASSEMBLY-TOOLING | Turnover | Kiewit/MHI/HMS assembly team | 3 | AST-SAF-01; AST-SAF-02; AST-SAF-03 | 0 |
| Z01-B | F-101 Tokamak Building | FUSION-MACHINE | Site Arrival | Kiewit/MHI/HMS | 3 | FUS-S01-TF; FUS-S01-TS; FUS-S01-VV | 0 |
| Z01 | F-106/F-101 | TOKAMAK-ASSEMBLY-TOOLING | Mechanical Completion | Kiewit/HMS/MHI assembly team | 2 | AST-PFLB-01; AST-PFLB-02 | 0 |
| Z01-A | F-106 Assembly Hall / F-101 | PERMANENT-HEAVY-LIFT | Turnover | Kiewit/OEM | 2 | LFT-F106-HBC-01; LFT-F106-HBC-02 | 0 |
| Z01-A | F-106 Assembly Hall | PERMANENT-HEAVY-LIFT | Commissioning/Operation | Kiewit/OEM | 2 | LFT-F106-AUX-01; LFT-F106-AUX-02 | 0 |
| Z01 | F-106/F-101 | TOKAMAK-ASSEMBLY-TOOLING | Turnover | Kiewit/HMS/MHI assembly team | 2 | AST-PFLB-01; AST-PFLB-02 | 0 |
| Z01-A | F-106 Assembly Hall | PERMANENT-HEAVY-LIFT | Turnover | Kiewit/OEM | 2 | LFT-F106-AUX-01; LFT-F106-AUX-02 | 0 |

## 2027-09

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z07/Z05 | E-101/E-102/E-103/E-104/E-105 | ELECTRICAL | Site Arrival | E.S. Fox/OEM | 27 | APS-823-SWG-010; APS-824-MCC-010; DCP-843-UPS-010; SWY-811-CB-010; SWY-812-DS-010; SWY-813-CT-010; SWY-814-VT-010 | 0 |
| Z01-A | F-106 Assembly Hall | TOKAMAK-ASSEMBLY-TOOLING | Commissioning/Operation | Kiewit/MHI/HMS assembly team | 3 | AST-SAF-02; AST-SAF-03; AST-SAF-04 | 0 |
| Z01-B | F-101 Tokamak Building | FUSION-MACHINE | Site Arrival | Kiewit/MHI/HMS | 3 | FUS-S02-TF; FUS-S02-TS; FUS-S02-VV | 0 |
| Z01 | F-106/F-101 | TOKAMAK-ASSEMBLY-TOOLING | Commissioning/Operation | Kiewit/HMS/MHI assembly team | 2 | AST-PFLB-01; AST-PFLB-02 | 0 |
| Z01-A | F-106 Assembly Hall | TOKAMAK-ASSEMBLY-TOOLING | Turnover | Kiewit/MHI/HMS assembly team | 1 | AST-SAF-04 | 0 |
| Z01-B | F-101 Tokamak Building | MAG-PF | Site Arrival | Kiewit/MHI | 1 | MAG-PF-01 | 0 |

## 2027-10

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z07/Z05 | E-101/E-102/E-103/E-104/E-105 | ELECTRICAL | Site Arrival | E.S. Fox/OEM | 12 | APS-824-MCC-015; SWY-812-DS-015; SWY-813-CT-015; APS-824-MCC-016; SWY-812-DS-016; SWY-813-CT-016; APS-824-MCC-017 | 0 |
| Z06 | Intake Tunnel | TUNNEL-CONSTRUCTION | Removal/Demobilization | Tunnel contractor | 10 | TMP-TBM-I-MAIN-01; TMP-TBM-I-CUT-01; TMP-TBM-I-DRV-01; TMP-TBM-I-THR-01; TMP-TBM-I-ERE-01; TMP-TBM-I-CON-01; TMP-TBM-I-SEP-01 | 0 |
| Z01-B | F-101 Tokamak Building | FUSION-MACHINE | Site Arrival | Kiewit/MHI/HMS | 3 | FUS-S03-TF; FUS-S03-TS; FUS-S03-VV | 0 |

## 2027-11

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z07/Z05 | E-101/E-102/E-103/E-104/E-105 | ELECTRICAL | Site Arrival | E.S. Fox/OEM | 8 | APS-824-MCC-019; SWY-812-DS-019; APS-824-MCC-020; SWY-812-DS-020; APS-824-MCC-021; SWY-812-DS-021; APS-824-MCC-022 | 0 |
| Z06 | Intake Tunnel | TUNNEL-CONSTRUCTION | Removal/Demobilization | Tunnel contractor | 6 | TMP-TBM-I-VEN-01; TMP-TBM-I-TRN-01; TMP-TBM-I-LOC-01; TMP-TBM-I-RES-01; TMP-TBM-I-TRF-01; TMP-TBM-I-PMP-01 | 0 |
| Z01-B | F-101 Tokamak Building | FUSION-MACHINE | Site Arrival | Kiewit/MHI/HMS | 3 | FUS-S04-TF; FUS-S04-TS; FUS-S04-VV | 0 |

## 2027-12

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z01/Z02/Z03 | Excavation Zones | TEMP-DEWATER | Removal/Demobilization | Bird/Bechtel | 74 | TMP-DW-DWP-001; TMP-DW-FLT-001; TMP-DW-SET-001; TMP-DW-SMP-001; TMP-DW-WLP-001; TMP-DW-WTS-001; TMP-DW-DWP-002 | 0 |
| Z01/Z02/Z03 | Excavations | GROUNDWORKS | Removal/Demobilization | Aecon | 16 | TMP-GEO-DRL-001; TMP-GEO-RBL-001; TMP-GEO-DRL-002; TMP-GEO-RBL-002; TMP-GEO-DRL-003; TMP-GEO-RBL-003; TMP-GEO-DRL-004 | 0 |
| Z07/Z05 | E-101/E-102/E-103/E-104/E-105 | ELECTRICAL | Site Arrival | E.S. Fox/OEM | 7 | APS-824-MCC-023; SWY-812-DS-023; APS-824-MCC-024; SWY-812-DS-024; APS-824-MCC-025; APS-824-MCC-026; APS-824-MCC-027 | 0 |
| Z01-B | F-101 Tokamak Building | FUSION-MACHINE | Site Arrival | Kiewit/MHI/HMS | 3 | FUS-S05-TF; FUS-S05-TS; FUS-S05-VV | 0 |
| Z01-B | F-101 Tokamak Building | MAG-PF | Installation/Mobilization | Kiewit/MHI | 1 | MAG-PF-01 | 0 |
| Z01-B | F-101 Tokamak Building | MAG-PF | Site Arrival | Kiewit/MHI | 1 | MAG-PF-02 | 0 |

## 2028-01

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Plant Buildings | PERMANENT-HANDLING | Site Arrival | Kiewit/E.S. Fox | 62 | LFT-PERM-JIB-001; LFT-PERM-MNR-001; LFT-PERM-JIB-002; LFT-PERM-MNR-002; LFT-PERM-JIB-003; LFT-PERM-MNR-003; LFT-PERM-JIB-004 | 0 |
| Z07/Z05 | E-101/E-102/E-103/E-104/E-105 | ELECTRICAL | Installation/Mobilization | E.S. Fox/OEM | 59 | APS-821-TR-001; APS-822-SWG-001; APS-823-SWG-001; APS-824-MCC-001; DCP-841-BAT-001; DCP-842-CHR-001; DCP-843-UPS-001 | 0 |
| Z01/Z02/Z03 | Excavation Zones | TEMP-DEWATER | Removal/Demobilization | Bird/Bechtel | 32 | TMP-DW-DWP-017; TMP-DW-SMP-017; TMP-DW-WLP-017; TMP-DW-DWP-018; TMP-DW-SMP-018; TMP-DW-WLP-018; TMP-DW-DWP-019 | 0 |
| ALL | Plant Buildings | PERMANENT-HANDLING | Site Arrival | Elevator contractor | 16 | LFT-PERM-FEL-001; LFT-PERM-FEL-002; LFT-PERM-FEL-003; LFT-PERM-FEL-004; LFT-PERM-FEL-005; LFT-PERM-FEL-006; LFT-PERM-FEL-007 | 0 |
| ALL | Plant Buildings | PERMANENT-HANDLING | Site Arrival | Kiewit/OEM | 16 | LFT-PERM-OHC-001; LFT-PERM-OHC-002; LFT-PERM-OHC-003; LFT-PERM-OHC-004; LFT-PERM-OHC-005; LFT-PERM-OHC-006; LFT-PERM-OHC-007 | 0 |
| Z08 | Site perimeter | ENV-MONITORING | Site Arrival | Environmental contractor | 16 | N103-GW-001; N103-GW-002; N103-GW-003; N103-GW-004; N103-GW-005; N103-GW-006; N103-GW-007 | 0 |
| Z06 | Lake / N-103 | ENV-MONITORING | Site Arrival | Environmental contractor | 12 | N103-WAT-001; N103-WAT-002; N103-WAT-003; N103-WAT-004; N103-WAT-005; N103-WAT-006; N103-WAT-007 | 0 |
| Z06 | Outfall / Lake | ENV-MONITORING | Site Arrival | Environmental contractor | 10 | N103-THM-001; N103-THM-002; N103-THM-003; N103-THM-004; N103-THM-005; N103-THM-006; N103-THM-007 | 0 |

## 2028-02

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Plant Buildings | PERMANENT-HANDLING | Site Arrival | Kiewit/E.S. Fox | 46 | LFT-PERM-JIB-032; LFT-PERM-MNR-032; LFT-PERM-JIB-033; LFT-PERM-MNR-033; LFT-PERM-JIB-034; LFT-PERM-MNR-034; LFT-PERM-JIB-035 | 0 |
| Z07/Z05 | E-101/E-102/E-103/E-104/E-105 | ELECTRICAL | Installation/Mobilization | E.S. Fox/OEM | 34 | APS-822-SWG-006; APS-823-SWG-006; APS-824-MCC-006; DCP-842-CHR-006; DCP-843-UPS-006; SWY-811-CB-006; SWY-812-DS-006 | 0 |
| Z01/Z02/Z03 | Excavation Zones | TEMP-DEWATER | Removal/Demobilization | Bird/Bechtel | 24 | TMP-DW-DWP-032; TMP-DW-SMP-032; TMP-DW-DWP-033; TMP-DW-SMP-033; TMP-DW-DWP-034; TMP-DW-SMP-034; TMP-DW-DWP-035 | 0 |
| ALL | Plant Buildings | PERMANENT-HANDLING | Site Arrival | Kiewit/OEM | 12 | LFT-PERM-OHC-017; LFT-PERM-OHC-018; LFT-PERM-OHC-019; LFT-PERM-OHC-020; LFT-PERM-OHC-021; LFT-PERM-OHC-022; LFT-PERM-OHC-023 | 0 |
| Z06 | Outfall Tunnel | TUNNEL-CONSTRUCTION | Removal/Demobilization | Tunnel contractor | 9 | TMP-TBM-O-MAIN-01; TMP-TBM-O-CUT-01; TMP-TBM-O-DRV-01; TMP-TBM-O-THR-01; TMP-TBM-O-ERE-01; TMP-TBM-O-CON-01; TMP-TBM-O-SEP-01 | 0 |
| Z08 | Site perimeter | ENV-MONITORING | Site Arrival | Environmental contractor | 8 | N103-GW-017; N103-GW-018; N103-GW-019; N103-GW-020; N103-GW-021; N103-GW-022; N103-GW-023 | 0 |
| Z03-A | H-101 BHT Annex | BHT-401 | Site Arrival | E.S. Fox/BWXT | 5 | BHT-401-P-101; BHT-401-SG-101; BHT-401-MOV-101; BHT-401-MOV-102; BHT-401-CV-103 | 0 |
| Z07/Z05 | E-101/E-102/E-103/E-104/E-105 | ELECTRICAL | Site Arrival | E.S. Fox/OEM | 4 | APS-824-MCC-032; APS-824-MCC-033; APS-824-MCC-034; APS-824-MCC-035 | 0 |

## 2028-03

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z07/Z05 | E-101/E-102/E-103/E-104/E-105 | ELECTRICAL | Installation/Mobilization | E.S. Fox/OEM | 24 | APS-823-SWG-010; APS-824-MCC-010; DCP-843-UPS-010; SWY-811-CB-010; SWY-812-DS-010; SWY-813-CT-010; SWY-814-VT-010 | 0 |
| Z05 | C-101/C-102 Cryogenic Plant | CRY-600 | Site Arrival | E.S. Fox/IHI | 21 | CRY-601-CMP-001; CRY-611-CBX-001; CRY-612-TCB-001; CRY-621-VB-001; CRY-622-HST-001; CRY-623-LN2-001; CRY-624-PUR-001 | 0 |
| Z01/Z02/Z03 | Excavation Zones | TEMP-DEWATER | Removal/Demobilization | Bird/Bechtel | 10 | TMP-DW-SMP-047; TMP-DW-SMP-048; TMP-DW-SMP-049; TMP-DW-SMP-050; TMP-DW-SMP-051; TMP-DW-SMP-052; TMP-DW-SMP-053 | 0 |
| Z06 | Outfall Tunnel | TUNNEL-CONSTRUCTION | Removal/Demobilization | Tunnel contractor | 7 | TMP-TBM-O-GRS-01; TMP-TBM-O-VEN-01; TMP-TBM-O-TRN-01; TMP-TBM-O-LOC-01; TMP-TBM-O-RES-01; TMP-TBM-O-TRF-01; TMP-TBM-O-PMP-01 | 0 |
| Z03-A | H-101 BHT Annex | BHT-402 | Site Arrival | E.S. Fox/BWXT | 6 | BHT-402-P-101; BHT-402-SG-101; BHT-402-MOV-101; BHT-402-MOV-102; BHT-402-CV-103; BHT-402-STR-101 | 0 |
| Z06 | W-101/W-103 | CWS-470 | Site Arrival | Bird/E.S. Fox | 6 | CWS-471-GV-004; CWS-471-P-004; CWS-471-SCR-004; CWS-471-TCW-004; CWS-471-GV-005; CWS-471-P-005 | 0 |
| Z08/Z05 | U-101/U-102 | PERM-UTILITIES | Site Arrival | E.S. Fox | 6 | UTL-201-RWP-001; UTL-201-RWP-002; UTL-201-RWP-003; UTL-201-RWP-004; UTL-201-RWP-005; UTL-201-RWP-006 | 0 |
| Z03-A | H-101 BHT Annex | BHT-401 | Installation/Mobilization | E.S. Fox/BWXT | 5 | BHT-401-P-101; BHT-401-SG-101; BHT-401-MOV-101; BHT-401-MOV-102; BHT-401-CV-103 | 0 |

## 2028-04

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z02 | F-103 Tritium Building | TRITIUM | Site Arrival | E.S. Fox/JGC | 21 | ADS-551-SKD-001; BTX-531-SKD-001; ISS-511-CD-001; TEX-501-SKD-001; TMA-561-MS-001; TMA-562-CAL-001; TSD-521-BED-001 | 0 |
| Z07/Z05 | E-101/E-102/E-103/E-104/E-105 | ELECTRICAL | Installation/Mobilization | E.S. Fox/OEM | 15 | APS-824-MCC-014; SWY-812-DS-014; SWY-813-CT-014; APS-824-MCC-015; SWY-812-DS-015; SWY-813-CT-015; APS-824-MCC-016 | 0 |
| Z05 | C-101/C-102 Cryogenic Plant | CRY-600 | Site Arrival | E.S. Fox/IHI | 11 | CRY-601-CMP-004; CRY-621-VB-004; CRY-622-HST-004; CRY-624-PUR-004; CRY-625-RCV-004; CRY-601-CMP-005; CRY-621-VB-005 | 0 |
| Z08 | U-102 | PERM-UTILITIES | Site Arrival | E.S. Fox | 8 | UTL-203-RO-001; UTL-204-EDI-001; UTL-203-RO-002; UTL-204-EDI-002; UTL-203-RO-003; UTL-204-EDI-003; UTL-203-RO-004 | 0 |
| Z03-A | H-101 BHT Annex | BHT-403 | Site Arrival | E.S. Fox/BWXT | 6 | BHT-403-P-101; BHT-403-SG-101; BHT-403-MOV-101; BHT-403-MOV-102; BHT-403-CV-103; BHT-403-STR-101 | 0 |
| Z03-E | H-101 | BHT-400 | Site Arrival | E.S. Fox | 5 | BHT-400-CHM-101; BHT-400-FLT-101; BHT-400-IX-101; BHT-400-MUT-101; BHT-400-PRZ-101 | 0 |
| Z03-A | H-101 BHT Annex | BHT-402 | Installation/Mobilization | E.S. Fox/BWXT | 5 | BHT-402-P-101; BHT-402-SG-101; BHT-402-MOV-101; BHT-402-MOV-102; BHT-402-CV-103 | 0 |
| Z07/Z05 | E-101/E-102/E-103/E-104/E-105 | ELECTRICAL | Site Arrival | E.S. Fox/OEM | 4 | APS-824-MCC-041; APS-824-MCC-042; APS-824-MCC-043; APS-824-MCC-044 | 0 |

## 2028-05

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Plant Buildings | PERMANENT-HANDLING | Installation/Mobilization | Kiewit/E.S. Fox | 62 | LFT-PERM-JIB-001; LFT-PERM-MNR-001; LFT-PERM-JIB-002; LFT-PERM-MNR-002; LFT-PERM-JIB-003; LFT-PERM-MNR-003; LFT-PERM-JIB-004 | 0 |
| Z01-D | F-101 Vacuum Galleries | VAC-260 | Site Arrival | E.S. Fox/OEM | 30 | VAC-260-RGA-001; VAC-260-VG-001; VAC-261-CP-001; VAC-261-GV-001; VAC-262-BP-001; VAC-262-GV-001; VAC-262-RP-001 | 0 |
| Z02 | R-101/R-102/R-103 | HOTCELL-RH | Site Arrival | Kiewit/E.S. Fox/OEM | 30 | CKS-911-AGV-001; CKS-911-CASK-001; DEC-931-SKD-001; HCL-921-CRN-001; HCL-922-MAN-001; HCL-923-RBT-001; HCL-924-WLD-001 | 0 |
| ALL | Plant Buildings | PERMANENT-HANDLING | Installation/Mobilization | Kiewit/OEM | 16 | LFT-PERM-OHC-001; LFT-PERM-OHC-002; LFT-PERM-OHC-003; LFT-PERM-OHC-004; LFT-PERM-OHC-005; LFT-PERM-OHC-006; LFT-PERM-OHC-007 | 0 |
| ALL | Plant Buildings | PERMANENT-HANDLING | Installation/Mobilization | Elevator contractor | 16 | LFT-PERM-FEL-001; LFT-PERM-FEL-002; LFT-PERM-FEL-003; LFT-PERM-FEL-004; LFT-PERM-FEL-005; LFT-PERM-FEL-006; LFT-PERM-FEL-007 | 0 |
| Z08 | Site perimeter | ENV-MONITORING | Installation/Mobilization | Environmental contractor | 16 | N103-GW-001; N103-GW-002; N103-GW-003; N103-GW-004; N103-GW-005; N103-GW-006; N103-GW-007 | 0 |
| Z06 | Lake / N-103 | ENV-MONITORING | Installation/Mobilization | Environmental contractor | 12 | N103-WAT-001; N103-WAT-002; N103-WAT-003; N103-WAT-004; N103-WAT-005; N103-WAT-006; N103-WAT-007 | 0 |
| Z06 | Outfall / Lake | ENV-MONITORING | Installation/Mobilization | Environmental contractor | 10 | N103-THM-001; N103-THM-002; N103-THM-003; N103-THM-004; N103-THM-005; N103-THM-006; N103-THM-007 | 0 |

## 2028-06

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Plant Buildings | HVAC-CONFINEMENT | Site Arrival | HVAC contractor | 90 | HVAC-AHU-001; HVAC-EF-001; HVAC-SF-001; HVAC-AHU-002; HVAC-EF-002; HVAC-SF-002; HVAC-AHU-003 | 0 |
| ALL | Plant Buildings | PERMANENT-HANDLING | Installation/Mobilization | Kiewit/E.S. Fox | 47 | LFT-PERM-JIB-032; LFT-PERM-MNR-032; LFT-PERM-JIB-033; LFT-PERM-MNR-033; LFT-PERM-JIB-034; LFT-PERM-MNR-034; LFT-PERM-JIB-035 | 0 |
| ALL | Utility/Controlled Buildings | UTILITIES | Site Arrival | E.S. Fox | 34 | CHW-461-CH-001; DRN-991-P-001; FPR-961-P-001; HVAC-O101-AHU-001; HVAC-R101-EXH-001; HVAC-T103-EXH-001; RAW-941-P-001 | 0 |
| ALL | Plantwide | DRAINAGE-EFFLUENT | Site Arrival | Bird/E.S. Fox | 30 | DRN-992-SMP-001; DRN-992-SMP-002; DRN-992-SMP-003; DRN-992-SMP-004; DRN-992-SMP-005; DRN-992-SMP-006; DRN-992-SMP-007 | 0 |
| Z05 | C-101/C-102 Cryogenic Plant | CRY-600 | Installation/Mobilization | E.S. Fox/IHI | 21 | CRY-601-CMP-001; CRY-611-CBX-001; CRY-612-TCB-001; CRY-621-VB-001; CRY-622-HST-001; CRY-623-LN2-001; CRY-624-PUR-001 | 0 |
| Z01-D | F-101 Vacuum Galleries | VAC-260 | Site Arrival | E.S. Fox/OEM | 18 | VAC-260-RGA-005; VAC-260-VG-005; VAC-261-CP-005; VAC-261-GV-005; VAC-262-BP-005; VAC-262-GV-005; VAC-262-RP-005 | 0 |
| Z01/Z02/Z03 | Excavations | GROUNDWORKS | Removal/Demobilization | Aecon | 15 | TMP-GEO-SHR-001; TMP-GEO-SHR-002; TMP-GEO-SHR-003; TMP-GEO-SHR-004; TMP-GEO-SHR-005; TMP-GEO-SHR-006; TMP-GEO-SHR-007 | 0 |
| Z08/Z06 | N-101 | DRAINAGE-EFFLUENT | Site Arrival | Bird | 15 | DRN-996-SWP-001; DRN-996-SWP-002; DRN-996-SWP-003; DRN-996-SWP-004; DRN-996-SWP-005; DRN-996-SWP-006; DRN-996-SWP-007 | 0 |

## 2028-07

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Plant Buildings | HVAC-CONFINEMENT | Site Arrival | HVAC contractor | 93 | HVAC-AHU-031; HVAC-EF-031; HVAC-SF-031; HVAC-AHU-032; HVAC-EF-032; HVAC-SF-032; HVAC-AHU-033 | 0 |
| ALL | Plantwide | DRAINAGE-EFFLUENT | Site Arrival | Bird/E.S. Fox | 18 | DRN-992-SMP-031; DRN-992-SMP-032; DRN-992-SMP-033; DRN-992-SMP-034; DRN-992-SMP-035; DRN-992-SMP-036; DRN-992-SMP-037 | 0 |
| Z06 | Lake Ontario / Marine Works | MARINE-CONSTRUCTION | Removal/Demobilization | Bird/marine subcontractor | 14 | TMP-MAR-BRG-001; TMP-MAR-CRB-001; TMP-MAR-DIV-001; TMP-MAR-SCW-001; TMP-MAR-SPD-001; TMP-MAR-SUR-001; TMP-MAR-TUG-001 | 0 |
| Z01-D | F-101 Vacuum Galleries | VAC-260 | Site Arrival | E.S. Fox/OEM | 12 | VAC-260-RGA-008; VAC-260-VG-008; VAC-261-GV-008; VAC-262-GV-008; VAC-260-RGA-009; VAC-260-VG-009; VAC-261-GV-009 | 0 |
| Z05 | C-101/C-102 Cryogenic Plant | CRY-600 | Installation/Mobilization | E.S. Fox/IHI | 11 | CRY-601-CMP-004; CRY-621-VB-004; CRY-622-HST-004; CRY-624-PUR-004; CRY-625-RCV-004; CRY-601-CMP-005; CRY-621-VB-005 | 0 |
| Z01/Z02/Z03 | Excavations | GROUNDWORKS | Removal/Demobilization | Aecon | 9 | TMP-GEO-SHR-016; TMP-GEO-SHR-017; TMP-GEO-SHR-018; TMP-GEO-SHR-019; TMP-GEO-SHR-020; TMP-GEO-SHR-021; TMP-GEO-SHR-022 | 0 |
| ALL | Utility/Controlled Buildings | UTILITIES | Site Arrival | E.S. Fox | 9 | DRN-991-P-007; RAW-941-P-007; DRN-991-P-008; RAW-941-P-008; DRN-991-P-009; DRN-991-P-010; DRN-991-P-011 | 0 |
| Z06 | W-101/W-103 | CWS-470 | Installation/Mobilization | Bird/E.S. Fox | 8 | CWS-471-GV-003; CWS-471-P-003; CWS-471-SCR-003; CWS-471-TCW-003; CWS-471-GV-004; CWS-471-P-004; CWS-471-SCR-004 | 0 |

## 2028-08

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Plantwide | FIRE-PROTECTION | Site Arrival | Fire contractor | 32 | FPR-963-MON-001; FPR-964-DLV-001; FPR-963-MON-002; FPR-964-DLV-002; FPR-963-MON-003; FPR-964-DLV-003; FPR-963-MON-004 | 0 |
| ALL | Sitewide | FIRE-PROTECTION | Site Arrival | Fire contractor | 31 | FPR-962-HYD-001; FPR-962-HYD-002; FPR-962-HYD-003; FPR-962-HYD-004; FPR-962-HYD-005; FPR-962-HYD-006; FPR-962-HYD-007 | 0 |
| Z02 | R-101/R-102/R-103 | HOTCELL-RH | Installation/Mobilization | Kiewit/E.S. Fox/OEM | 30 | CKS-911-AGV-001; CKS-911-CASK-001; DEC-931-SKD-001; HCL-921-CRN-001; HCL-922-MAN-001; HCL-923-RBT-001; HCL-924-WLD-001 | 0 |
| ALL | Plant Buildings | HVAC-CONFINEMENT | Site Arrival | HVAC contractor | 25 | HVAC-AHU-062; HVAC-EF-062; HVAC-SF-062; HVAC-AHU-063; HVAC-EF-063; HVAC-SF-063; HVAC-AHU-064 | 0 |
| Z02 | F-103 Tritium Building | TRITIUM | Installation/Mobilization | E.S. Fox/JGC | 21 | ADS-551-SKD-001; BTX-531-SKD-001; ISS-511-CD-001; TEX-501-SKD-001; TMA-561-MS-001; TMA-562-CAL-001; TSD-521-BED-001 | 0 |
| Z02 | R-104 | RADWASTE-DECON | Site Arrival | E.S. Fox | 19 | RAW-942-FLT-001; RAW-943-IX-001; RAW-946-CMP-001; RAW-942-FLT-002; RAW-943-IX-002; RAW-946-CMP-002; RAW-942-FLT-003 | 0 |
| Z04 | T-101/T-102 | TURBINE-BOP | Site Arrival | Kiewit/E.S. Fox | 18 | CFW-732-CEP-001; CFW-733-LPH-001; CFW-734-HPH-001; CFW-735-DEA-001; MSP-741-MSV-001; MSP-742-BPV-001; TUR-703-MSR-001 | 0 |
| Z08 | U-104 | PERM-UTILITIES | Installation/Mobilization | E.S. Fox | 10 | UTL-210-N2T-001; UTL-211-N2V-001; UTL-211-N2V-002; UTL-210-N2T-002; UTL-211-N2V-003; UTL-210-N2T-003; UTL-211-N2V-004 | 0 |

## 2028-09

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Sitewide | FIRE-PROTECTION | Site Arrival | Fire contractor | 30 | FPR-962-HYD-032; FPR-962-HYD-033; FPR-962-HYD-034; FPR-962-HYD-035; FPR-962-HYD-036; FPR-962-HYD-037; FPR-962-HYD-038 | 0 |
| ALL | Plantwide | FIRE-PROTECTION | Site Arrival | Fire contractor | 17 | FPR-963-MON-017; FPR-964-DLV-017; FPR-963-MON-018; FPR-964-DLV-018; FPR-964-DLV-019; FPR-964-DLV-020; FPR-964-DLV-021 | 0 |
| Z04 | T-101 | MAIN-STEAM | Site Arrival | E.S. Fox/OEM | 16 | MSP-743-SV-001; MSP-744-MSV-001; MSP-743-SV-002; MSP-744-MSV-002; MSP-743-SV-003; MSP-743-SV-004; MSP-744-MSV-003 | 0 |
| Z04 | T-101 | TURBINE-AUX | Site Arrival | Kiewit/E.S. Fox | 16 | CND-722-VP-001; TUR-704-LOP-001; TUR-705-EHP-001; CND-722-VP-002; TUR-704-LOP-002; TUR-705-EHP-002; CND-722-VP-003 | 0 |
| Z02 | R-101/R-102/R-103 | HOTCELL-RH | Installation/Mobilization | Kiewit/E.S. Fox/OEM | 14 | DEC-931-SKD-005; HCL-922-MAN-005; HCL-923-RBT-005; HCL-924-WLD-005; HCL-925-CUT-005; DEC-931-SKD-006; HCL-922-MAN-006 | 0 |
| Z02 | F-103 Tritium Building | TRITIUM | Installation/Mobilization | E.S. Fox/JGC | 8 | BTX-531-SKD-004; TMA-561-MS-004; TMA-562-CAL-004; TSD-521-BED-004; TMA-561-MS-005; TSD-521-BED-005; TMA-561-MS-006 | 0 |
| Z02 | R-104/R-105 | RADWASTE-DECON | Site Arrival | E.S. Fox | 8 | RAW-941-TK-009; RAW-941-TK-010; RAW-941-TK-011; RAW-941-TK-012; RAW-941-TK-013; RAW-941-TK-014; RAW-941-TK-015 | 0 |
| Z05 | C-101/C-102 Cryogenic Plant | CRY-600 | Installation/Mobilization | E.S. Fox/IHI | 6 | CRY-601-CMP-009; CRY-621-VB-009; CRY-601-CMP-010; CRY-621-VB-010; CRY-601-CMP-011; CRY-621-VB-011 | 0 |

## 2028-10

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Utility/Controlled Buildings | UTILITIES | Installation/Mobilization | E.S. Fox | 36 | CHW-461-CH-001; DRN-991-P-001; FPR-961-P-001; HVAC-O101-AHU-001; HVAC-R101-EXH-001; HVAC-T103-EXH-001; RAW-941-P-001 | 0 |
| ALL | Plantwide | DRN | Installation/Mobilization | E.S. Fox | 32 | DEV-DRN-MTR-001; DEV-DRN-PNL-001; DEV-DRN-MTR-002; DEV-DRN-PNL-002; DEV-DRN-MTR-003; DEV-DRN-PNL-003; DEV-DRN-MTR-004 | 32 |
| Z06 | W-101/W-103 | CWS | Installation/Mobilization | E.S. Fox | 32 | DEV-CWS-MTR-001; DEV-CWS-PNL-001; DEV-CWS-MTR-002; DEV-CWS-PNL-002; DEV-CWS-MTR-003; DEV-CWS-PNL-003; DEV-CWS-MTR-004 | 32 |
| Z08/Z05 | U-101/U-104 | UTL | Installation/Mobilization | E.S. Fox | 32 | DEV-UTL-MTR-001; DEV-UTL-PNL-001; DEV-UTL-MTR-002; DEV-UTL-PNL-002; DEV-UTL-MTR-003; DEV-UTL-PNL-003; DEV-UTL-MTR-004 | 32 |
| ALL | Plantwide | DRN | Site Arrival | E.S. Fox/package contractor | 31 | DEV-DRN-VLV-001; DEV-DRN-VLV-002; DEV-DRN-VLV-003; DEV-DRN-VLV-004; DEV-DRN-VLV-005; DEV-DRN-VLV-006; DEV-DRN-VLV-007 | 31 |
| ALL | Plantwide | DRAINAGE-EFFLUENT | Installation/Mobilization | Bird/E.S. Fox | 31 | DRN-992-SMP-001; DRN-992-SMP-002; DRN-992-SMP-003; DRN-992-SMP-004; DRN-992-SMP-005; DRN-992-SMP-006; DRN-992-SMP-007 | 0 |
| ALL | Plantwide | FPR | Site Arrival | E.S. Fox/package contractor | 31 | DEV-FPR-VLV-001; DEV-FPR-VLV-002; DEV-FPR-VLV-003; DEV-FPR-VLV-004; DEV-FPR-VLV-005; DEV-FPR-VLV-006; DEV-FPR-VLV-007 | 31 |
| Z01 | F-104 | NBI | Site Arrival | E.S. Fox/package contractor | 31 | DEV-NBI-VLV-001; DEV-NBI-VLV-002; DEV-NBI-VLV-003; DEV-NBI-VLV-004; DEV-NBI-VLV-005; DEV-NBI-VLV-006; DEV-NBI-VLV-007 | 0 |

## 2028-11

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Plantwide | DRN | Installation/Mobilization | E.S. Fox | 30 | DEV-DRN-INS-032; DEV-DRN-INS-033; DEV-DRN-INS-034; DEV-DRN-INS-035; DEV-DRN-INS-036; DEV-DRN-INS-037; DEV-DRN-INS-038 | 30 |
| ALL | Plantwide | DRN | Installation/Mobilization | E.S. Fox | 30 | DEV-DRN-MTR-017; DEV-DRN-PNL-017; DEV-DRN-MTR-018; DEV-DRN-PNL-018; DEV-DRN-MTR-019; DEV-DRN-PNL-019; DEV-DRN-MTR-020 | 30 |
| ALL | Plantwide | DRN | Site Arrival | E.S. Fox/package contractor | 30 | DEV-DRN-VLV-032; DEV-DRN-VLV-033; DEV-DRN-VLV-034; DEV-DRN-VLV-035; DEV-DRN-VLV-036; DEV-DRN-VLV-037; DEV-DRN-VLV-038 | 30 |
| ALL | Plantwide | DRN | Installation/Mobilization | E.S. Fox/package contractor | 30 | DEV-DRN-VLV-032; DEV-DRN-VLV-033; DEV-DRN-VLV-034; DEV-DRN-VLV-035; DEV-DRN-VLV-036; DEV-DRN-VLV-037; DEV-DRN-VLV-038 | 30 |
| Z01/Z02 | F-101/F-103 | FUE | Site Arrival | E.S. Fox/package contractor | 30 | DEV-FUE-VLV-032; DEV-FUE-VLV-033; DEV-FUE-VLV-034; DEV-FUE-VLV-035; DEV-FUE-VLV-036; DEV-FUE-VLV-037; DEV-FUE-VLV-038 | 0 |
| Z02 | F-103 | ISS | Site Arrival | E.S. Fox/package contractor | 30 | DEV-ISS-VLV-032; DEV-ISS-VLV-033; DEV-ISS-VLV-034; DEV-ISS-VLV-035; DEV-ISS-VLV-036; DEV-ISS-VLV-037; DEV-ISS-VLV-038 | 0 |
| ALL | Plantwide | FPR | Site Arrival | E.S. Fox/package contractor | 30 | DEV-FPR-VLV-032; DEV-FPR-VLV-033; DEV-FPR-VLV-034; DEV-FPR-VLV-035; DEV-FPR-VLV-036; DEV-FPR-VLV-037; DEV-FPR-VLV-038 | 30 |
| Z01 | F-101 | DMS | Site Arrival | E.S. Fox/package contractor | 30 | DEV-DMS-VLV-032; DEV-DMS-VLV-033; DEV-DMS-VLV-034; DEV-DMS-VLV-035; DEV-DMS-VLV-036; DEV-DMS-VLV-037; DEV-DMS-VLV-038 | 0 |

## 2028-12

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Plant Buildings | HVAC-CONFINEMENT | Installation/Mobilization | HVAC contractor | 93 | HVAC-AHU-001; HVAC-EF-001; HVAC-SF-001; HVAC-AHU-002; HVAC-EF-002; HVAC-SF-002; HVAC-AHU-003 | 0 |
| ALL | Controlled Buildings | HVAC | Site Arrival | E.S. Fox | 64 | HVAC-AOV-001; HVAC-MOV-001; HVAC-PSV-001; HVAC-XV-001; HVAC-AOV-002; HVAC-MOV-002; HVAC-PSV-002 | 0 |
| Z02 | F-103 | TRI | Site Arrival | E.S. Fox | 64 | TRI-AOV-001; TRI-MOV-001; TRI-PSV-001; TRI-XV-001; TRI-AOV-002; TRI-MOV-002; TRI-PSV-002 | 0 |
| Z01 | F-101 | VAC | Site Arrival | E.S. Fox | 64 | VAC-AOV-001; VAC-MOV-001; VAC-PSV-001; VAC-XV-001; VAC-AOV-002; VAC-MOV-002; VAC-PSV-002 | 0 |
| Z04 | T-101/T-102 | TUR | Site Arrival | E.S. Fox | 64 | TUR-AOV-001; TUR-MOV-001; TUR-PSV-001; TUR-XV-001; TUR-AOV-002; TUR-MOV-002; TUR-PSV-002 | 0 |
| Z05 | C-101/C-102 | CRY | Site Arrival | E.S. Fox | 64 | CRY-AOV-001; CRY-MOV-001; CRY-PSV-001; CRY-XV-001; CRY-AOV-002; CRY-MOV-002; CRY-PSV-002 | 0 |
| Z03 | H-101 | BHT | Site Arrival | E.S. Fox | 48 | BHT-AOV-001; BHT-MOV-001; BHT-PSV-001; BHT-XV-001; BHT-AOV-002; BHT-MOV-002; BHT-PSV-002 | 0 |
| Z05 | U-101 | CCW | Site Arrival | E.S. Fox | 36 | CCW-AOV-001; CCW-MOV-001; CCW-PSV-001; CCW-XV-001; CCW-AOV-002; CCW-MOV-002; CCW-PSV-002 | 0 |

## 2029-01

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z05/Z01 | O-101 / Plant technical areas | CONTROL | Site Arrival | E.S. Fox/OEM | 208 | DCS-850-HMI-001; DCS-850-RIO-001; DCS-850-SRV-001; MPS-870-RK-001; NET-890-FW-001; NET-890-SW-001; PPC-860-RK-001 | 0 |
| ALL | Controlled Buildings | HVAC | Site Arrival | E.S. Fox | 180 | HVAC-FT-001; HVAC-LT-001; HVAC-PT-001; HVAC-TT-001; HVAC-AOV-017; HVAC-FT-002; HVAC-LT-002 | 0 |
| Z02 | F-103 | TRI | Site Arrival | E.S. Fox | 156 | TRI-FT-001; TRI-LT-001; TRI-PT-001; TRI-TT-001; TRI-AOV-017; TRI-FT-002; TRI-LT-002 | 0 |
| ALL | Plantwide | E&I-BULK | Site Arrival | E.S. Fox | 155 | ELE-JB-001; ELE-LCS-001; ELE-PNL-001; IC-ANL-001; IC-MAR-001; ELE-JB-002; ELE-LCS-002 | 0 |
| Z05 | C-101/C-102 | CRY | Site Arrival | E.S. Fox | 154 | CRY-FT-001; CRY-LT-001; CRY-PT-001; CRY-TT-001; DEV-CRY-MTR-001; DEV-CRY-PNL-001; CRY-AOV-017 | 0 |
| Z03 | H-101 | BHT | Site Arrival | E.S. Fox | 145 | BHT-FT-001; BHT-LT-001; BHT-PT-001; BHT-TT-001; DEV-BHT-MTR-001; DEV-BHT-PNL-001; BHT-FT-002 | 0 |
| Z04 | T-101/T-102 | TUR | Site Arrival | E.S. Fox | 125 | TUR-FT-001; TUR-LT-001; TUR-PT-001; TUR-TT-001; TUR-AOV-017; TUR-FT-002; TUR-LT-002 | 0 |
| Z01 | F-101 | VAC | Site Arrival | E.S. Fox | 122 | DEV-VAC-MTR-001; DEV-VAC-PNL-001; VAC-FT-001; VAC-LT-001; VAC-PT-001; VAC-TT-001; VAC-FT-002 | 0 |

## 2029-02

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Plantwide | E&I-BULK | Site Arrival | E.S. Fox | 140 | ELE-JB-032; ELE-LCS-032; ELE-PNL-032; IC-ANL-032; IC-MAR-032; ELE-JB-033; ELE-LCS-033 | 0 |
| Z05 | C-101/C-102 | CRY | Site Arrival | E.S. Fox | 73 | CRY-PT-032; CRY-TT-032; CRY-PT-033; CRY-TT-033; DEV-CRY-MTR-017; DEV-CRY-PNL-017; CRY-PT-034 | 0 |
| Z02 | F-103 | TRI | Site Arrival | E.S. Fox | 71 | TRI-FT-032; TRI-LT-032; TRI-PT-032; TRI-TT-032; TRI-FT-033; TRI-LT-033; TRI-PT-033 | 0 |
| Z05/Z01 | O-101 / Plant technical areas | CONTROL | Site Arrival | E.S. Fox/OEM | 58 | DCS-850-HMI-032; DCS-850-RIO-032; NET-890-SW-032; SIS-880-RK-032; DCS-850-RIO-033; NET-890-SW-033; DCS-850-RIO-034 | 0 |
| Z01/Z02 | Controlled Buildings | HVAC-CONFINEMENT | Site Arrival | HVAC contractor | 56 | HVAC-HEPA-032; HVAC-ID-032; HVAC-HEPA-033; HVAC-ID-033; HVAC-HEPA-034; HVAC-ID-034; HVAC-HEPA-035 | 0 |
| Z01 | F-101 | VAC | Site Arrival | E.S. Fox | 50 | VAC-PT-032; VAC-TT-032; DEV-VAC-MTR-017; DEV-VAC-PNL-017; VAC-PT-033; VAC-TT-033; VAC-PT-034 | 0 |
| ALL | Controlled Buildings | HVAC | Site Arrival | E.S. Fox | 47 | HVAC-FT-032; HVAC-LT-032; HVAC-PT-032; HVAC-TT-032; HVAC-LT-033; HVAC-PT-033; HVAC-TT-033 | 0 |
| Z03 | H-101 | BHT | Site Arrival | E.S. Fox | 39 | BHT-LT-032; BHT-PT-032; BHT-TT-032; BHT-PT-033; BHT-TT-033; DEV-BHT-MTR-017; DEV-BHT-PNL-017 | 0 |

## 2029-03

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Plantwide | E&I-BULK | Installation/Mobilization | E.S. Fox | 155 | ELE-JB-001; ELE-LCS-001; ELE-PNL-001; IC-ANL-001; IC-MAR-001; ELE-JB-002; ELE-LCS-002 | 0 |
| ALL | Plantwide | E&I-BULK | Site Arrival | E.S. Fox | 129 | ELE-JB-060; ELE-LCS-060; ELE-PNL-060; IC-ANL-060; IC-MAR-060; ELE-JB-061; ELE-LCS-061 | 0 |
| Z05 | C-101/C-102 | CRY | Installation/Mobilization | E.S. Fox | 94 | CRY-AOV-001; CRY-MOV-001; CRY-PSV-001; CRY-XV-001; DEV-CRY-MTR-031; DEV-CRY-PNL-031; CRY-AOV-002 | 0 |
| Z01 | F-101 | VAC | Installation/Mobilization | E.S. Fox | 89 | VAC-AOV-001; VAC-MOV-001; VAC-PSV-001; VAC-XV-001; DEV-VAC-MTR-031; DEV-VAC-PNL-031; VAC-AOV-002 | 0 |
| Z03 | H-101 | BHT | Installation/Mobilization | E.S. Fox | 69 | BHT-AOV-001; BHT-MOV-001; BHT-PSV-001; BHT-XV-001; DEV-BHT-MTR-031; DEV-BHT-PNL-031; BHT-AOV-002 | 0 |
| ALL | Controlled Buildings | HVAC | Installation/Mobilization | E.S. Fox | 64 | HVAC-AOV-001; HVAC-MOV-001; HVAC-PSV-001; HVAC-XV-001; HVAC-AOV-002; HVAC-MOV-002; HVAC-PSV-002 | 0 |
| Z04 | T-101/T-102 | TUR | Installation/Mobilization | E.S. Fox | 64 | TUR-AOV-001; TUR-MOV-001; TUR-PSV-001; TUR-XV-001; TUR-AOV-002; TUR-MOV-002; TUR-PSV-002 | 0 |
| Z02 | F-103 | TRI | Installation/Mobilization | E.S. Fox | 64 | TRI-AOV-001; TRI-MOV-001; TRI-PSV-001; TRI-XV-001; TRI-AOV-002; TRI-MOV-002; TRI-PSV-002 | 0 |

## 2029-04

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z05/Z01 | O-101 / Plant technical areas | CONTROL | Installation/Mobilization | E.S. Fox/OEM | 204 | DCS-850-HMI-001; DCS-850-RIO-001; DCS-850-SRV-001; MPS-870-RK-001; NET-890-FW-001; NET-890-SW-001; PPC-860-RK-001 | 0 |
| ALL | Controlled Buildings | HVAC | Installation/Mobilization | E.S. Fox | 176 | HVAC-FT-001; HVAC-LT-001; HVAC-PT-001; HVAC-TT-001; HVAC-AOV-017; HVAC-FT-002; HVAC-LT-002 | 0 |
| Z02 | F-103 | TRI | Installation/Mobilization | E.S. Fox | 152 | TRI-FT-001; TRI-LT-001; TRI-PT-001; TRI-TT-001; TRI-AOV-017; TRI-FT-002; TRI-LT-002 | 0 |
| ALL | Plantwide | E&I-BULK | Installation/Mobilization | E.S. Fox | 150 | ELE-JB-032; ELE-LCS-032; ELE-PNL-032; IC-ANL-032; IC-MAR-032; ELE-JB-033; ELE-LCS-033 | 0 |
| Z05 | C-101/C-102 | CRY | Installation/Mobilization | E.S. Fox | 142 | CRY-FT-001; CRY-LT-001; CRY-PT-001; CRY-TT-001; DEV-CRY-MTR-046; DEV-CRY-PNL-046; CRY-AOV-017 | 0 |
| Z04 | T-101/T-102 | TUR | Installation/Mobilization | E.S. Fox | 122 | TUR-FT-001; TUR-LT-001; TUR-PT-001; TUR-TT-001; TUR-AOV-017; TUR-FT-002; TUR-LT-002 | 0 |
| Z03 | H-101 | BHT | Installation/Mobilization | E.S. Fox | 113 | BHT-FT-001; BHT-LT-001; BHT-PT-001; BHT-TT-001; DEV-BHT-PNL-046; BHT-FT-002; BHT-LT-002 | 0 |
| ALL | Plantwide | E&I-BULK | Site Arrival | E.S. Fox | 96 | ELE-JB-091; ELE-LCS-091; ELE-PNL-091; IC-MAR-091; ELE-JB-092; ELE-LCS-092; ELE-PNL-092 | 0 |

## 2029-05

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z01 | F-101/F-102 | DIA-330 | Site Arrival | E.S. Fox/HMS | 161 | DIA-ECE-001; DIA-INT-001; DIA-IR-001; DIA-MAG-001; DIA-NEU-001; DIA-RGA-001; DIA-STR-001 | 0 |
| ALL | Plantwide | E&I-BULK | Installation/Mobilization | E.S. Fox | 127 | ELE-JB-062; ELE-LCS-062; ELE-PNL-062; IC-ANL-062; IC-MAR-062; ELE-JB-063; ELE-LCS-063 | 0 |
| ALL | Plantwide | E&I-BULK | Site Arrival | E.S. Fox | 93 | ELE-JB-121; ELE-LCS-121; ELE-PNL-121; ELE-JB-122; ELE-LCS-122; ELE-PNL-122; ELE-JB-123 | 0 |
| Z02 | F-103 | TRI | Installation/Mobilization | E.S. Fox | 77 | TRI-FT-031; TRI-LT-031; TRI-PT-031; TRI-TT-031; TRI-FT-032; TRI-LT-032; TRI-PT-032 | 0 |
| Z05/Z01 | O-101 / Plant technical areas | CONTROL | Installation/Mobilization | E.S. Fox/OEM | 66 | DCS-850-HMI-031; DCS-850-RIO-031; NET-890-SW-031; SIS-880-RK-031; DCS-850-HMI-032; DCS-850-RIO-032; NET-890-SW-032 | 0 |
| Z01/Z02 | Controlled Areas | RADIATION-PROTECTION | Installation/Mobilization | E.S. Fox/OEM | 62 | RPS-952-NEM-001; RPS-954-PAM-001; RPS-952-NEM-002; RPS-954-PAM-002; RPS-952-NEM-003; RPS-954-PAM-003; RPS-952-NEM-004 | 0 |
| Z01/Z02 | Controlled Buildings | HVAC-CONFINEMENT | Installation/Mobilization | HVAC contractor | 62 | HVAC-HEPA-001; HVAC-ID-001; HVAC-HEPA-002; HVAC-ID-002; HVAC-HEPA-003; HVAC-ID-003; HVAC-HEPA-004 | 0 |
| ALL | Controlled Buildings | HVAC | Installation/Mobilization | E.S. Fox | 52 | HVAC-FT-031; HVAC-LT-031; HVAC-PT-031; HVAC-TT-031; HVAC-FT-032; HVAC-LT-032; HVAC-PT-032 | 0 |

## 2029-06

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Plantwide | E&I-BULK | Installation/Mobilization | E.S. Fox | 94 | ELE-JB-093; ELE-LCS-093; ELE-PNL-093; IC-MAR-093; ELE-JB-094; ELE-LCS-094; ELE-PNL-094 | 0 |
| ALL | Plantwide | E&I-BULK | Site Arrival | E.S. Fox | 89 | ELE-JB-152; ELE-LCS-152; ELE-PNL-152; ELE-JB-153; ELE-LCS-153; ELE-PNL-153; ELE-JB-154 | 0 |
| Z01 | F-101/F-102 | DIA-330 | Site Arrival | E.S. Fox/HMS | 61 | DIA-IR-032; DIA-MAG-032; DIA-STR-032; DIA-MAG-033; DIA-STR-033; DIA-MAG-034; DIA-STR-034 | 0 |
| Z01/Z02 | Controlled Buildings | HVAC-CONFINEMENT | Installation/Mobilization | HVAC contractor | 60 | HVAC-HEPA-032; HVAC-ID-032; HVAC-HEPA-033; HVAC-ID-033; HVAC-HEPA-034; HVAC-ID-034; HVAC-HEPA-035 | 0 |
| Z07/Z05 | E-101/E-102/E-103/E-104/E-105 | ELECTRICAL | Mechanical Completion | E.S. Fox/OEM | 59 | APS-821-TR-001; APS-822-SWG-001; APS-823-SWG-001; APS-824-MCC-001; DCP-841-BAT-001; DCP-842-CHR-001; DCP-843-UPS-001 | 0 |
| Z05/Z01 | O-101 / Plant technical areas | CONTROL | Installation/Mobilization | E.S. Fox/OEM | 49 | DCS-850-RIO-062; NET-890-SW-062; DCS-850-RIO-063; NET-890-SW-063; DCS-850-RIO-064; NET-890-SW-064; DCS-850-RIO-065 | 0 |
| Z08 | Construction Production Area | CIVIL-PRODUCTION | Removal/Demobilization | Bechtel/Aecon | 42 | TMP-CON-BP-001; TMP-CON-CP-001; TMP-CON-ICE-001; TMP-CON-LAB-001; TMP-CON-MIX-001; TMP-CON-SP-001; TMP-GRT-MIX-001 | 0 |
| Z01/Z02 | Controlled Areas | RADIATION-PROTECTION | Installation/Mobilization | E.S. Fox/OEM | 34 | RPS-952-NEM-032; RPS-954-PAM-032; RPS-952-NEM-033; RPS-954-PAM-033; RPS-952-NEM-034; RPS-954-PAM-034; RPS-952-NEM-035 | 0 |

## 2029-07

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Plantwide | E&I-BULK | Installation/Mobilization | E.S. Fox | 93 | ELE-JB-123; ELE-LCS-123; ELE-PNL-123; ELE-JB-124; ELE-LCS-124; ELE-PNL-124; ELE-JB-125 | 0 |
| ALL | Plantwide | E&I-BULK | Site Arrival | E.S. Fox | 62 | ELE-JB-182; ELE-PNL-182; ELE-JB-183; ELE-PNL-183; ELE-JB-184; ELE-PNL-184; ELE-JB-185 | 0 |
| Z01/Z02 | Controlled Buildings | HVAC-CONFINEMENT | Installation/Mobilization | HVAC contractor | 62 | HVAC-HEPA-062; HVAC-ID-062; HVAC-HEPA-063; HVAC-ID-063; HVAC-HEPA-064; HVAC-ID-064; HVAC-HEPA-065 | 0 |
| Z07/Z05 | E-101/E-102/E-103/E-104/E-105 | ELECTRICAL | Mechanical Completion | E.S. Fox/OEM | 34 | APS-822-SWG-006; APS-823-SWG-006; APS-824-MCC-006; DCP-842-CHR-006; DCP-843-UPS-006; SWY-811-CB-006; SWY-812-DS-006 | 0 |
| ALL | Plant Buildings | HVAC-CONFINEMENT | Installation/Mobilization | HVAC contractor | 31 | HVAC-CD-062; HVAC-CD-063; HVAC-CD-064; HVAC-CD-065; HVAC-CD-066; HVAC-CD-067; HVAC-CD-068 | 0 |
| Z01 | F-101 | DMS | Installation/Mobilization | E.S. Fox | 31 | DEV-DMS-INS-062; DEV-DMS-INS-063; DEV-DMS-INS-064; DEV-DMS-INS-065; DEV-DMS-INS-066; DEV-DMS-INS-067; DEV-DMS-INS-068 | 0 |
| Z01 | F-101 | VAC | Installation/Mobilization | E.S. Fox | 31 | DEV-VAC-INS-182; DEV-VAC-INS-183; DEV-VAC-INS-184; DEV-VAC-INS-185; DEV-VAC-INS-186; DEV-VAC-INS-187; DEV-VAC-INS-188 | 0 |
| Z01 | F-101 | VAC | Site Arrival | E.S. Fox | 31 | DEV-VAC-INS-182; DEV-VAC-INS-183; DEV-VAC-INS-184; DEV-VAC-INS-185; DEV-VAC-INS-186; DEV-VAC-INS-187; DEV-VAC-INS-188 | 0 |

## 2029-08

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z01 | F-101/F-102 | DIA-330 | Installation/Mobilization | E.S. Fox/HMS | 161 | DIA-ECE-001; DIA-INT-001; DIA-IR-001; DIA-MAG-001; DIA-NEU-001; DIA-RGA-001; DIA-STR-001 | 0 |
| ALL | Commissioning Workfronts | TEMP-COMMISSIONING | Site Arrival | E&C/OPG/E.S. Fox | 129 | TMP-COM-AFB-001; TMP-COM-DAQ-001; TMP-COM-FLS-001; TMP-COM-FLT-001; TMP-COM-HYD-001; TMP-COM-LOAD-001; TMP-COM-OFL-001 | 0 |
| ALL | Plantwide | E&I-BULK | Installation/Mobilization | E.S. Fox | 89 | ELE-JB-154; ELE-LCS-154; ELE-PNL-154; ELE-JB-155; ELE-LCS-155; ELE-PNL-155; ELE-JB-156 | 0 |
| Z01/Z02 | Controlled Buildings | HVAC-CONFINEMENT | Installation/Mobilization | HVAC contractor | 59 | HVAC-HEPA-093; HVAC-ID-093; HVAC-HEPA-094; HVAC-ID-094; HVAC-HEPA-095; HVAC-ID-095; HVAC-HEPA-096 | 0 |
| ALL | Plantwide | E&I-BULK | Site Arrival | E.S. Fox | 39 | ELE-JB-213; ELE-PNL-213; ELE-JB-214; ELE-PNL-214; ELE-JB-215; ELE-PNL-215; ELE-JB-216 | 0 |
| ALL | Utility/Controlled Buildings | UTILITIES | Turnover | E.S. Fox | 36 | CHW-461-CH-001; DRN-991-P-001; FPR-961-P-001; HVAC-O101-AHU-001; HVAC-R101-EXH-001; HVAC-T103-EXH-001; RAW-941-P-001 | 0 |
| Z05 | C-101/C-102 | CRY | Site Arrival | E.S. Fox/package contractor | 31 | DEV-CRY-VLV-305; DEV-CRY-VLV-306; DEV-CRY-VLV-307; DEV-CRY-VLV-308; DEV-CRY-VLV-309; DEV-CRY-VLV-310; DEV-CRY-VLV-311 | 0 |
| ALL | Plant Buildings | HVAC-CONFINEMENT | Installation/Mobilization | HVAC contractor | 31 | HVAC-CD-093; HVAC-CD-094; HVAC-CD-095; HVAC-CD-096; HVAC-CD-097; HVAC-CD-098; HVAC-CD-099 | 0 |

## 2029-09

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Commissioning Workfronts | TEMP-COMMISSIONING | Installation/Mobilization | E&C/OPG/E.S. Fox | 118 | TMP-COM-AFB-001; TMP-COM-DAQ-001; TMP-COM-FLS-001; TMP-COM-FLT-001; TMP-COM-HYD-001; TMP-COM-LOAD-001; TMP-COM-OFL-001 | 0 |
| ALL | Commissioning Workfronts | TEMP-COMMISSIONING | Site Arrival | E&C/OPG/E.S. Fox | 65 | TMP-COM-DAQ-012; TMP-COM-FLS-012; TMP-COM-FLT-012; TMP-COM-HYD-012; TMP-COM-LOAD-012; TMP-COM-OFL-012; TMP-COM-PWR-012 | 0 |
| Z01 | F-101/F-102 | DIA-330 | Installation/Mobilization | E.S. Fox/HMS | 61 | DIA-IR-032; DIA-MAG-032; DIA-STR-032; DIA-MAG-033; DIA-STR-033; DIA-MAG-034; DIA-STR-034 | 0 |
| ALL | Plantwide | E&I-BULK | Installation/Mobilization | E.S. Fox | 60 | ELE-JB-185; ELE-PNL-185; ELE-JB-186; ELE-PNL-186; ELE-JB-187; ELE-PNL-187; ELE-JB-188 | 0 |
| Z07/Z05 | E-101/E-102/E-103/E-104/E-105 | ELECTRICAL | Turnover | E.S. Fox/OEM | 59 | APS-821-TR-001; APS-822-SWG-001; APS-823-SWG-001; APS-824-MCC-001; DCP-841-BAT-001; DCP-842-CHR-001; DCP-843-UPS-001 | 0 |
| ALL | Utility/Controlled Buildings | UTILITIES | Commissioning/Operation | E.S. Fox | 34 | CHW-461-CH-001; DRN-991-P-001; FPR-961-P-001; HVAC-O101-AHU-001; HVAC-R101-EXH-001; HVAC-T103-EXH-001; RAW-941-P-001 | 0 |
| ALL | Plantwide | E&I-BULK | Site Arrival | E.S. Fox | 30 | ELE-JB-244; ELE-JB-245; ELE-JB-246; ELE-JB-247; ELE-JB-248; ELE-JB-249; ELE-JB-250 | 0 |
| ALL | Sitewide | FIRE-PROTECTION | Mechanical Completion | Fire contractor | 30 | FPR-962-HYD-001; FPR-962-HYD-002; FPR-962-HYD-003; FPR-962-HYD-004; FPR-962-HYD-005; FPR-962-HYD-006; FPR-962-HYD-007 | 0 |

## 2029-10

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Commissioning Workfronts | TEMP-COMMISSIONING | Mechanical Completion | E&C/OPG/E.S. Fox | 129 | TMP-COM-AFB-001; TMP-COM-DAQ-001; TMP-COM-FLS-001; TMP-COM-FLT-001; TMP-COM-HYD-001; TMP-COM-LOAD-001; TMP-COM-OFL-001 | 0 |
| ALL | Commissioning Workfronts | TEMP-COMMISSIONING | Installation/Mobilization | E&C/OPG/E.S. Fox | 76 | TMP-COM-DAQ-011; TMP-COM-FLS-011; TMP-COM-FLT-011; TMP-COM-HYD-011; TMP-COM-LOAD-011; TMP-COM-OFL-011; TMP-COM-PWR-011 | 0 |
| ALL | Plant Buildings | PERMANENT-HANDLING | Mechanical Completion | Kiewit/E.S. Fox | 62 | LFT-PERM-JIB-001; LFT-PERM-MNR-001; LFT-PERM-JIB-002; LFT-PERM-MNR-002; LFT-PERM-JIB-003; LFT-PERM-MNR-003; LFT-PERM-JIB-004 | 0 |
| Z07/Z05 | E-101/E-102/E-103/E-104/E-105 | ELECTRICAL | Commissioning/Operation | E.S. Fox/OEM | 59 | APS-821-TR-001; APS-822-SWG-001; APS-823-SWG-001; APS-824-MCC-001; DCP-841-BAT-001; DCP-842-CHR-001; DCP-843-UPS-001 | 0 |
| Z08 | M-101/M-102/M-103 | MAINT-WH | Mechanical Completion | Bechtel/E.S. Fox | 46 | MNT-101-CRN-001; MNT-102-LAT-001; MNT-103-MIL-001; MNT-104-BAL-001; MNT-105-WLD-001; MNT-106-CAL-001; MNT-107-FLT-001 | 0 |
| ALL | Plantwide | E&I-BULK | Installation/Mobilization | E.S. Fox | 37 | ELE-JB-215; ELE-PNL-215; ELE-JB-216; ELE-PNL-216; ELE-JB-217; ELE-PNL-217; ELE-JB-218 | 0 |
| Z07/Z05 | E-101/E-102/E-103/E-104/E-105 | ELECTRICAL | Turnover | E.S. Fox/OEM | 34 | APS-822-SWG-006; APS-823-SWG-006; APS-824-MCC-006; DCP-842-CHR-006; DCP-843-UPS-006; SWY-811-CB-006; SWY-812-DS-006 | 0 |
| Z01 | F-101 | VAC | Installation/Mobilization | E.S. Fox | 31 | DEV-VAC-INS-274; DEV-VAC-INS-275; DEV-VAC-INS-276; DEV-VAC-INS-277; DEV-VAC-INS-278; DEV-VAC-INS-279; DEV-VAC-INS-280 | 0 |

## 2029-11

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Commissioning Workfronts | TEMP-COMMISSIONING | Turnover | E&C/OPG/E.S. Fox | 118 | TMP-COM-AFB-001; TMP-COM-DAQ-001; TMP-COM-FLS-001; TMP-COM-FLT-001; TMP-COM-HYD-001; TMP-COM-LOAD-001; TMP-COM-OFL-001 | 0 |
| ALL | Commissioning Workfronts | TEMP-COMMISSIONING | Mechanical Completion | E&C/OPG/E.S. Fox | 65 | TMP-COM-DAQ-012; TMP-COM-FLS-012; TMP-COM-FLT-012; TMP-COM-HYD-012; TMP-COM-LOAD-012; TMP-COM-OFL-012; TMP-COM-PWR-012 | 0 |
| ALL | Plant Buildings | PERMANENT-HANDLING | Mechanical Completion | Kiewit/E.S. Fox | 47 | LFT-PERM-JIB-032; LFT-PERM-MNR-032; LFT-PERM-JIB-033; LFT-PERM-MNR-033; LFT-PERM-JIB-034; LFT-PERM-MNR-034; LFT-PERM-JIB-035 | 0 |
| Z07/Z05 | E-101/E-102/E-103/E-104/E-105 | ELECTRICAL | Commissioning/Operation | E.S. Fox/OEM | 34 | APS-822-SWG-006; APS-823-SWG-006; APS-824-MCC-006; DCP-842-CHR-006; DCP-843-UPS-006; SWY-811-CB-006; SWY-812-DS-006 | 0 |
| ALL | Plantwide | FPR | Turnover | E.S. Fox | 30 | DEV-FPR-INS-001; DEV-FPR-INS-002; DEV-FPR-INS-003; DEV-FPR-INS-004; DEV-FPR-INS-005; DEV-FPR-INS-006; DEV-FPR-INS-007 | 30 |
| ALL | Plantwide | DRN | Turnover | E.S. Fox | 30 | DEV-DRN-MTR-001; DEV-DRN-PNL-001; DEV-DRN-MTR-002; DEV-DRN-PNL-002; DEV-DRN-MTR-003; DEV-DRN-PNL-003; DEV-DRN-MTR-004 | 30 |
| ALL | Plantwide | FPR | Turnover | E.S. Fox | 30 | DEV-FPR-MTR-001; DEV-FPR-PNL-001; DEV-FPR-MTR-002; DEV-FPR-PNL-002; DEV-FPR-MTR-003; DEV-FPR-PNL-003; DEV-FPR-MTR-004 | 30 |
| ALL | Plantwide | DRN | Turnover | E.S. Fox | 30 | DEV-DRN-INS-001; DEV-DRN-INS-002; DEV-DRN-INS-003; DEV-DRN-INS-004; DEV-DRN-INS-005; DEV-DRN-INS-006; DEV-DRN-INS-007 | 30 |

## 2029-12

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Commissioning Workfronts | TEMP-COMMISSIONING | Commissioning/Operation | E&C/OPG/E.S. Fox | 129 | TMP-COM-AFB-001; TMP-COM-DAQ-001; TMP-COM-FLS-001; TMP-COM-FLT-001; TMP-COM-HYD-001; TMP-COM-LOAD-001; TMP-COM-OFL-001 | 0 |
| ALL | Plant Buildings | HVAC-CONFINEMENT | Mechanical Completion | HVAC contractor | 93 | HVAC-AHU-001; HVAC-EF-001; HVAC-SF-001; HVAC-AHU-002; HVAC-EF-002; HVAC-SF-002; HVAC-AHU-003 | 0 |
| ALL | Commissioning Workfronts | TEMP-COMMISSIONING | Turnover | E&C/OPG/E.S. Fox | 76 | TMP-COM-DAQ-011; TMP-COM-FLS-011; TMP-COM-FLT-011; TMP-COM-HYD-011; TMP-COM-LOAD-011; TMP-COM-OFL-011; TMP-COM-PWR-011 | 0 |
| Z01-B | F-101 Tokamak Building | FUSION-MACHINE | Mechanical Completion | Kiewit/MHI/HMS | 48 | FUS-S01-TF; FUS-S01-TS; FUS-S01-VV; FUS-S02-TF; FUS-S02-TS; FUS-S02-VV; FUS-S03-TF | 0 |
| ALL | Plantwide | DRN | Turnover | E.S. Fox | 32 | DEV-DRN-MTR-016; DEV-DRN-PNL-016; DEV-DRN-MTR-017; DEV-DRN-PNL-017; DEV-DRN-MTR-018; DEV-DRN-PNL-018; DEV-DRN-MTR-019 | 32 |
| ALL | Plantwide | DRN | Turnover | E.S. Fox/package contractor | 31 | DEV-DRN-VLV-031; DEV-DRN-VLV-032; DEV-DRN-VLV-033; DEV-DRN-VLV-034; DEV-DRN-VLV-035; DEV-DRN-VLV-036; DEV-DRN-VLV-037 | 31 |
| ALL | Plantwide | DRN | Turnover | E.S. Fox | 31 | DEV-DRN-INS-031; DEV-DRN-INS-032; DEV-DRN-INS-033; DEV-DRN-INS-034; DEV-DRN-INS-035; DEV-DRN-INS-036; DEV-DRN-INS-037 | 31 |
| ALL | Plantwide | E&I-BULK | Site Arrival | E.S. Fox | 31 | ELE-JB-335; ELE-JB-336; ELE-JB-337; ELE-JB-338; ELE-JB-339; ELE-JB-340; ELE-JB-341 | 0 |

## 2030-01

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z05/Z01 | O-101 / Plant technical areas | CONTROL | Mechanical Completion | E.S. Fox/OEM | 208 | DCS-850-HMI-001; DCS-850-RIO-001; DCS-850-SRV-001; MPS-870-RK-001; NET-890-FW-001; NET-890-SW-001; PPC-860-RK-001 | 0 |
| ALL | Plant Buildings | HVAC-CONFINEMENT | Mechanical Completion | HVAC contractor | 124 | HVAC-AHU-032; HVAC-CD-001; HVAC-EF-032; HVAC-SF-032; HVAC-AHU-033; HVAC-CD-002; HVAC-EF-033 | 0 |
| ALL | Commissioning Workfronts | TEMP-COMMISSIONING | Commissioning/Operation | E&C/OPG/E.S. Fox | 65 | TMP-COM-DAQ-012; TMP-COM-FLS-012; TMP-COM-FLT-012; TMP-COM-HYD-012; TMP-COM-LOAD-012; TMP-COM-OFL-012; TMP-COM-PWR-012 | 0 |
| Z01 | F-101 | VAC | Mechanical Completion | E.S. Fox | 64 | VAC-AOV-001; VAC-MOV-001; VAC-PSV-001; VAC-XV-001; VAC-AOV-002; VAC-MOV-002; VAC-PSV-002 | 0 |
| ALL | Controlled Buildings | HVAC | Mechanical Completion | E.S. Fox | 64 | HVAC-AOV-001; HVAC-MOV-001; HVAC-PSV-001; HVAC-XV-001; HVAC-AOV-002; HVAC-MOV-002; HVAC-PSV-002 | 0 |
| Z04 | T-101/T-102 | TUR | Mechanical Completion | E.S. Fox | 64 | TUR-AOV-001; TUR-MOV-001; TUR-PSV-001; TUR-XV-001; TUR-AOV-002; TUR-MOV-002; TUR-PSV-002 | 0 |
| Z05 | C-101/C-102 | CRY | Mechanical Completion | E.S. Fox | 64 | CRY-AOV-001; CRY-MOV-001; CRY-PSV-001; CRY-XV-001; CRY-AOV-002; CRY-MOV-002; CRY-PSV-002 | 0 |
| Z02 | F-103 | TRI | Mechanical Completion | E.S. Fox | 64 | TRI-AOV-001; TRI-MOV-001; TRI-PSV-001; TRI-XV-001; TRI-AOV-002; TRI-MOV-002; TRI-PSV-002 | 0 |

## 2030-02

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Controlled Buildings | HVAC | Mechanical Completion | E.S. Fox | 168 | HVAC-FT-001; HVAC-LT-001; HVAC-PT-001; HVAC-TT-001; HVAC-AOV-017; HVAC-FT-002; HVAC-LT-002 | 0 |
| Z05 | C-101/C-102 | CRY | Mechanical Completion | E.S. Fox | 144 | CRY-FT-001; CRY-LT-001; CRY-PT-001; CRY-TT-001; DEV-CRY-MTR-001; DEV-CRY-PNL-001; CRY-AOV-017 | 0 |
| Z02 | F-103 | TRI | Mechanical Completion | E.S. Fox | 144 | TRI-FT-001; TRI-LT-001; TRI-PT-001; TRI-TT-001; TRI-AOV-017; TRI-FT-002; TRI-LT-002 | 0 |
| Z03 | H-101 | BHT | Mechanical Completion | E.S. Fox | 132 | BHT-FT-001; BHT-LT-001; BHT-PT-001; BHT-TT-001; DEV-BHT-MTR-001; DEV-BHT-PNL-001; BHT-FT-002 | 0 |
| Z04 | T-101/T-102 | TUR | Mechanical Completion | E.S. Fox | 116 | TUR-FT-001; TUR-LT-001; TUR-PT-001; TUR-TT-001; TUR-AOV-017; TUR-FT-002; TUR-LT-002 | 0 |
| Z01 | F-101 | VAC | Mechanical Completion | E.S. Fox | 112 | DEV-VAC-MTR-001; DEV-VAC-PNL-001; VAC-FT-001; VAC-LT-001; VAC-PT-001; VAC-TT-001; VAC-FT-002 | 0 |
| Z03 | H-101 | DHT | Mechanical Completion | E.S. Fox | 96 | DEV-DHT-MTR-001; DEV-DHT-PNL-001; DHT-FT-001; DHT-LT-001; DHT-PT-001; DHT-TT-001; DHT-FT-002 | 0 |
| Z05 | U-101 | CCW | Mechanical Completion | E.S. Fox | 84 | CCW-FT-001; CCW-LT-001; CCW-PT-001; CCW-TT-001; CCW-FT-002; CCW-LT-002; CCW-PT-002 | 0 |

## 2030-03

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Sitewide | TEMP-UTIL | Removal/Demobilization | Bechtel/site services | 212 | TMP-AIR-CMP-001; TMP-AIR-DRY-001; TMP-HTR-BLR-001; TMP-HVAC-AHU-001; TMP-HVAC-CHL-001; TMP-PWR-GEN-001; TMP-PWR-LGT-001 | 0 |
| ALL | Plantwide | E&I-BULK | Mechanical Completion | E.S. Fox | 155 | ELE-JB-001; ELE-LCS-001; ELE-PNL-001; IC-ANL-001; IC-MAR-001; ELE-JB-002; ELE-LCS-002 | 0 |
| ALL | Plant Buildings | HVAC-CONFINEMENT | Turnover | HVAC contractor | 93 | HVAC-AHU-001; HVAC-EF-001; HVAC-SF-001; HVAC-AHU-002; HVAC-EF-002; HVAC-SF-002; HVAC-AHU-003 | 0 |
| Z02 | F-103 | TRI | Mechanical Completion | E.S. Fox | 83 | TRI-FT-029; TRI-LT-029; TRI-PT-029; TRI-TT-029; TRI-FT-030; TRI-LT-030; TRI-PT-030 | 0 |
| Z05 | C-101/C-102 | CRY | Mechanical Completion | E.S. Fox | 83 | CRY-PT-029; CRY-TT-029; DEV-CRY-MTR-015; DEV-CRY-PNL-015; CRY-PT-030; CRY-TT-030; CRY-PT-031 | 0 |
| Z01/Z02 | Controlled Areas | RADIATION-PROTECTION | Mechanical Completion | E.S. Fox/OEM | 62 | RPS-952-NEM-001; RPS-954-PAM-001; RPS-952-NEM-002; RPS-954-PAM-002; RPS-952-NEM-003; RPS-954-PAM-003; RPS-952-NEM-004 | 0 |
| Z01/Z02 | Controlled Buildings | HVAC-CONFINEMENT | Mechanical Completion | HVAC contractor | 62 | HVAC-HEPA-060; HVAC-ID-060; HVAC-HEPA-061; HVAC-ID-061; HVAC-HEPA-062; HVAC-ID-062; HVAC-HEPA-063 | 0 |
| ALL | Plant Buildings | PERMANENT-HANDLING | Commissioning/Operation | Kiewit/E.S. Fox | 62 | LFT-PERM-JIB-001; LFT-PERM-MNR-001; LFT-PERM-JIB-002; LFT-PERM-MNR-002; LFT-PERM-JIB-003; LFT-PERM-MNR-003; LFT-PERM-JIB-004 | 0 |

## 2030-04

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z05/Z01 | O-101 / Plant technical areas | CONTROL | Turnover | E.S. Fox/OEM | 204 | DCS-850-HMI-001; DCS-850-RIO-001; DCS-850-SRV-001; MPS-870-RK-001; NET-890-FW-001; NET-890-SW-001; PPC-860-RK-001 | 0 |
| ALL | Plantwide | E&I-BULK | Mechanical Completion | E.S. Fox | 150 | ELE-JB-032; ELE-LCS-032; ELE-PNL-032; IC-ANL-032; IC-MAR-032; ELE-JB-033; ELE-LCS-033 | 0 |
| ALL | Plant Buildings | HVAC-CONFINEMENT | Turnover | HVAC contractor | 120 | HVAC-AHU-032; HVAC-CD-001; HVAC-EF-032; HVAC-SF-032; HVAC-AHU-033; HVAC-CD-002; HVAC-EF-033 | 0 |
| Z05 | C-101/C-102 | CRY | Turnover | E.S. Fox | 90 | CRY-AOV-001; CRY-MOV-001; CRY-PSV-001; CRY-XV-001; DEV-CRY-MTR-001; DEV-CRY-PNL-001; CRY-AOV-002 | 0 |
| Z03 | H-101 | BHT | Turnover | E.S. Fox | 78 | BHT-AOV-001; BHT-MOV-001; BHT-PSV-001; BHT-XV-001; DEV-BHT-MTR-017; DEV-BHT-PNL-017; BHT-AOV-002 | 0 |
| ALL | Sitewide | TEMP-UTIL | Removal/Demobilization | Bechtel/site services | 72 | TMP-PWR-LGT-032; TMP-PWR-PNL-032; TMP-PWR-SWB-032; TMP-PWR-TRF-032; TMP-PWR-LGT-033; TMP-PWR-PNL-033; TMP-PWR-SWB-033 | 0 |
| Z01/Z02 | Controlled Buildings | HVAC-CONFINEMENT | Turnover | HVAC contractor | 60 | HVAC-HEPA-001; HVAC-ID-001; HVAC-HEPA-002; HVAC-ID-002; HVAC-HEPA-003; HVAC-ID-003; HVAC-HEPA-004 | 0 |
| Z01 | F-101 | VAC | Turnover | E.S. Fox | 60 | VAC-AOV-001; VAC-MOV-001; VAC-PSV-001; VAC-XV-001; VAC-AOV-002; VAC-MOV-002; VAC-PSV-002 | 0 |

## 2030-05

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z05/Z01 | O-101 / Plant technical areas | CONTROL | Commissioning/Operation | E.S. Fox/OEM | 208 | DCS-850-HMI-001; DCS-850-RIO-001; DCS-850-SRV-001; MPS-870-RK-001; NET-890-FW-001; NET-890-SW-001; PPC-860-RK-001 | 0 |
| ALL | Controlled Buildings | HVAC | Turnover | E.S. Fox | 184 | HVAC-AOV-016; HVAC-FT-001; HVAC-LT-001; HVAC-MOV-016; HVAC-PSV-016; HVAC-PT-001; HVAC-TT-001 | 0 |
| Z02 | F-103 | TRI | Turnover | E.S. Fox | 160 | TRI-AOV-016; TRI-FT-001; TRI-LT-001; TRI-MOV-016; TRI-PSV-016; TRI-PT-001; TRI-TT-001 | 0 |
| Z05 | C-101/C-102 | CRY | Turnover | E.S. Fox | 158 | CRY-AOV-016; CRY-FT-001; CRY-LT-001; CRY-MOV-016; CRY-PSV-016; CRY-PT-001; CRY-TT-001 | 0 |
| Z03 | H-101 | BHT | Turnover | E.S. Fox | 133 | BHT-FT-001; BHT-LT-001; BHT-PT-001; BHT-TT-001; BHT-FT-002; BHT-LT-002; BHT-PT-002 | 0 |
| Z04 | T-101/T-102 | TUR | Turnover | E.S. Fox | 129 | TUR-AOV-016; TUR-FT-001; TUR-LT-001; TUR-MOV-016; TUR-PSV-016; TUR-PT-001; TUR-TT-001 | 0 |
| ALL | Plantwide | E&I-BULK | Mechanical Completion | E.S. Fox | 127 | ELE-JB-062; ELE-LCS-062; ELE-PNL-062; IC-ANL-062; IC-MAR-062; ELE-JB-063; ELE-LCS-063 | 0 |
| Z01 | F-101 | VAC | Turnover | E.S. Fox | 94 | VAC-AOV-016; VAC-FT-001; VAC-LT-001; VAC-MOV-016; VAC-PSV-016; VAC-PT-001; VAC-TT-001 | 0 |

## 2030-06

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Controlled Buildings | HVAC | Commissioning/Operation | E.S. Fox | 176 | HVAC-FT-001; HVAC-LT-001; HVAC-PT-001; HVAC-TT-001; HVAC-AOV-017; HVAC-FT-002; HVAC-LT-002 | 0 |
| Z02 | F-103 | TRI | Commissioning/Operation | E.S. Fox | 152 | TRI-FT-001; TRI-LT-001; TRI-PT-001; TRI-TT-001; TRI-AOV-017; TRI-FT-002; TRI-LT-002 | 0 |
| ALL | Plantwide | E&I-BULK | Turnover | E.S. Fox | 150 | ELE-JB-001; ELE-LCS-001; ELE-PNL-001; IC-ANL-001; IC-MAR-001; ELE-JB-002; ELE-LCS-002 | 0 |
| Z05 | C-101/C-102 | CRY | Commissioning/Operation | E.S. Fox | 150 | CRY-FT-001; CRY-LT-001; CRY-PT-001; CRY-TT-001; DEV-CRY-MTR-001; DEV-CRY-PNL-001; CRY-AOV-017 | 0 |
| Z03 | H-101 | BHT | Commissioning/Operation | E.S. Fox | 140 | BHT-FT-001; BHT-LT-001; BHT-PT-001; BHT-TT-001; DEV-BHT-MTR-001; DEV-BHT-PNL-001; BHT-FT-002 | 0 |
| Z04 | T-101/T-102 | TUR | Commissioning/Operation | E.S. Fox | 122 | TUR-FT-001; TUR-LT-001; TUR-PT-001; TUR-TT-001; TUR-AOV-017; TUR-FT-002; TUR-LT-002 | 0 |
| ALL | Plant Buildings | HVAC-CONFINEMENT | Commissioning/Operation | HVAC contractor | 120 | HVAC-AHU-032; HVAC-CD-001; HVAC-EF-032; HVAC-SF-032; HVAC-AHU-033; HVAC-CD-002; HVAC-EF-033 | 0 |
| ALL | Plantwide | E&I-BULK | Mechanical Completion | E.S. Fox | 94 | ELE-JB-093; ELE-LCS-093; ELE-PNL-093; IC-MAR-093; ELE-JB-094; ELE-LCS-094; ELE-PNL-094 | 0 |

## 2030-07

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Plantwide | E&I-BULK | Commissioning/Operation | E.S. Fox | 155 | ELE-JB-001; ELE-LCS-001; ELE-PNL-001; IC-ANL-001; IC-MAR-001; ELE-JB-002; ELE-LCS-002 | 0 |
| ALL | Plantwide | E&I-BULK | Turnover | E.S. Fox | 155 | ELE-JB-031; ELE-LCS-031; ELE-PNL-031; IC-ANL-031; IC-MAR-031; ELE-JB-032; ELE-LCS-032 | 0 |
| ALL | Plantwide | E&I-BULK | Mechanical Completion | E.S. Fox | 93 | ELE-JB-123; ELE-LCS-123; ELE-PNL-123; ELE-JB-124; ELE-LCS-124; ELE-PNL-124; ELE-JB-125 | 0 |
| Z05 | C-101/C-102 | CRY | Commissioning/Operation | E.S. Fox | 81 | CRY-PT-031; CRY-TT-031; DEV-CRY-MTR-016; DEV-CRY-PNL-016; CRY-PT-032; CRY-TT-032; CRY-PT-033 | 0 |
| Z02 | F-103 | TRI | Commissioning/Operation | E.S. Fox | 77 | TRI-FT-031; TRI-LT-031; TRI-PT-031; TRI-TT-031; TRI-FT-032; TRI-LT-032; TRI-PT-032 | 0 |
| Z01/Z02 | Controlled Areas | RADIATION-PROTECTION | Commissioning/Operation | E.S. Fox/OEM | 62 | RPS-952-NEM-001; RPS-954-PAM-001; RPS-952-NEM-002; RPS-954-PAM-002; RPS-952-NEM-003; RPS-954-PAM-003; RPS-952-NEM-004 | 0 |
| Z01/Z02 | Controlled Buildings | HVAC-CONFINEMENT | Commissioning/Operation | HVAC contractor | 62 | HVAC-HEPA-031; HVAC-ID-031; HVAC-HEPA-032; HVAC-ID-032; HVAC-HEPA-033; HVAC-ID-033; HVAC-HEPA-034 | 0 |
| Z01/Z02 | Controlled Buildings | HVAC-CONFINEMENT | Turnover | HVAC contractor | 60 | HVAC-HEPA-092; HVAC-ID-092; HVAC-HEPA-093; HVAC-ID-093; HVAC-HEPA-094; HVAC-ID-094; HVAC-HEPA-095 | 0 |

## 2030-08

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z01 | F-101/F-102 | DIA-330 | Mechanical Completion | E.S. Fox/HMS | 161 | DIA-ECE-001; DIA-INT-001; DIA-IR-001; DIA-MAG-001; DIA-NEU-001; DIA-RGA-001; DIA-STR-001 | 0 |
| ALL | Plantwide | E&I-BULK | Commissioning/Operation | E.S. Fox | 155 | ELE-JB-032; ELE-LCS-032; ELE-PNL-032; IC-ANL-032; IC-MAR-032; ELE-JB-033; ELE-LCS-033 | 0 |
| ALL | Plantwide | E&I-BULK | Turnover | E.S. Fox | 127 | ELE-JB-062; ELE-LCS-062; ELE-PNL-062; IC-ANL-062; IC-MAR-062; ELE-JB-063; ELE-LCS-063 | 0 |
| ALL | Plantwide | E&I-BULK | Mechanical Completion | E.S. Fox | 89 | ELE-JB-154; ELE-LCS-154; ELE-PNL-154; ELE-JB-155; ELE-LCS-155; ELE-PNL-155; ELE-JB-156 | 0 |
| Z01-B | F-101 In-vessel | BLK-230 | Mechanical Completion | Kiewit/HMS remote-handling team | 80 | BLK-S01-I1; BLK-S01-I2; BLK-S01-O1; BLK-S01-O2; BLK-S01-O3; BLK-S02-I1; BLK-S02-I2 | 0 |
| Z01/Z02 | Controlled Buildings | HVAC-CONFINEMENT | Commissioning/Operation | HVAC contractor | 62 | HVAC-HEPA-062; HVAC-ID-062; HVAC-HEPA-063; HVAC-ID-063; HVAC-HEPA-064; HVAC-ID-064; HVAC-HEPA-065 | 0 |
| Z01/Z02 | Controlled Areas | RADIATION-PROTECTION | Commissioning/Operation | E.S. Fox/OEM | 34 | RPS-952-NEM-032; RPS-954-PAM-032; RPS-952-NEM-033; RPS-954-PAM-033; RPS-952-NEM-034; RPS-954-PAM-034; RPS-952-NEM-035 | 0 |
| Z05 | C-101/C-102 | CRY | Commissioning/Operation | E.S. Fox | 33 | CRY-TT-062; CRY-TT-063; DEV-CRY-MTR-032; DEV-CRY-PNL-032; CRY-TT-064; DEV-CRY-MTR-033; DEV-CRY-PNL-033 | 0 |

## 2030-09

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Plantwide | E&I-BULK | Commissioning/Operation | E.S. Fox | 122 | ELE-JB-063; ELE-LCS-063; ELE-PNL-063; IC-ANL-063; IC-MAR-063; ELE-JB-064; ELE-LCS-064 | 0 |
| ALL | Plantwide | E&I-BULK | Turnover | E.S. Fox | 94 | ELE-JB-093; ELE-LCS-093; ELE-PNL-093; IC-MAR-093; ELE-JB-094; ELE-LCS-094; ELE-PNL-094 | 0 |
| Z01 | F-101/F-102 | DIA-330 | Mechanical Completion | E.S. Fox/HMS | 61 | DIA-IR-032; DIA-MAG-032; DIA-STR-032; DIA-MAG-033; DIA-STR-033; DIA-MAG-034; DIA-STR-034 | 0 |
| ALL | Plantwide | E&I-BULK | Mechanical Completion | E.S. Fox | 60 | ELE-JB-185; ELE-PNL-185; ELE-JB-186; ELE-PNL-186; ELE-JB-187; ELE-PNL-187; ELE-JB-188 | 0 |
| Z01/Z02 | Controlled Buildings | HVAC-CONFINEMENT | Commissioning/Operation | HVAC contractor | 58 | HVAC-HEPA-093; HVAC-ID-093; HVAC-HEPA-094; HVAC-ID-094; HVAC-HEPA-095; HVAC-ID-095; HVAC-HEPA-096 | 0 |
| Z01-B | F-101 Tokamak Building | FUSION-MACHINE | Turnover | Kiewit/MHI/HMS | 48 | FUS-S01-TF; FUS-S01-TS; FUS-S01-VV; FUS-S02-TF; FUS-S02-TS; FUS-S02-VV; FUS-S03-TF | 0 |
| Z01 | F-104/F-105/F-101 | HCD | Turnover | E.S. Fox/OEM | 36 | DMS-281-SPI-001; ECH-311-GY-001; ECH-312-HV-001; ECH-313-WG-001; ICH-321-RF-001; ICH-322-MAT-001; NBI-301-BL-001 | 0 |
| Z01 | F-104 | NBI | Turnover | E.S. Fox/package contractor | 30 | DEV-NBI-VLV-001; DEV-NBI-VLV-002; DEV-NBI-VLV-003; DEV-NBI-VLV-004; DEV-NBI-VLV-005; DEV-NBI-VLV-006; DEV-NBI-VLV-007 | 0 |

## 2030-10

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Sitewide / Defined Lift Zones | LIFTING-HANDLING | Removal/Demobilization | Bechtel/Aecon/Kiewit | 100 | TMP-CRN-AT10-001; TMP-CRN-AT20-001; TMP-CRN-AT30-001; TMP-CRN-CC10-001; TMP-CRN-CC18-001; TMP-CRN-CC40-001; TMP-CRN-CC65-001 | 0 |
| ALL | Plantwide | E&I-BULK | Commissioning/Operation | E.S. Fox | 97 | ELE-JB-093; ELE-LCS-093; ELE-PNL-093; IC-MAR-093; ELE-JB-094; ELE-LCS-094; ELE-PNL-094 | 0 |
| ALL | Plantwide | E&I-BULK | Turnover | E.S. Fox | 93 | ELE-JB-123; ELE-LCS-123; ELE-PNL-123; ELE-JB-124; ELE-LCS-124; ELE-PNL-124; ELE-JB-125 | 0 |
| Z01-B | F-101 In-vessel | BLK-230 | Turnover | Kiewit/HMS remote-handling team | 80 | BLK-S01-I1; BLK-S01-I2; BLK-S01-O1; BLK-S01-O2; BLK-S01-O3; BLK-S02-I1; BLK-S02-I2 | 0 |
| Z01-B | F-101 Tokamak Building | FUSION-MACHINE | Commissioning/Operation | Kiewit/MHI/HMS | 48 | FUS-S01-TF; FUS-S01-TS; FUS-S01-VV; FUS-S02-TF; FUS-S02-TS; FUS-S02-VV; FUS-S03-TF | 0 |
| Z01-D | F-101 Lower ports | DIV-240 | Turnover | Kiewit/HMS remote-handling team | 48 | DIV-S01-C1; DIV-S01-C2; DIV-S01-C3; DIV-S02-C1; DIV-S02-C2; DIV-S02-C3; DIV-S03-C1 | 0 |
| ALL | Plantwide | E&I-BULK | Mechanical Completion | E.S. Fox | 37 | ELE-JB-215; ELE-PNL-215; ELE-JB-216; ELE-PNL-216; ELE-JB-217; ELE-PNL-217; ELE-JB-218 | 0 |
| Z01 | F-104/F-105/F-101 | HCD | Commissioning/Operation | E.S. Fox/OEM | 36 | DMS-281-SPI-001; ECH-311-GY-001; ECH-312-HV-001; ECH-313-WG-001; ICH-321-RF-001; ICH-322-MAT-001; NBI-301-BL-001 | 0 |

## 2030-11

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z01 | F-101/F-102 | DIA-330 | Turnover | E.S. Fox/HMS | 158 | DIA-ECE-001; DIA-INT-001; DIA-IR-001; DIA-MAG-001; DIA-NEU-001; DIA-RGA-001; DIA-STR-001 | 0 |
| ALL | Plantwide | E&I-BULK | Commissioning/Operation | E.S. Fox | 90 | ELE-JB-124; ELE-LCS-124; ELE-PNL-124; ELE-JB-125; ELE-LCS-125; ELE-PNL-125; ELE-JB-126 | 0 |
| ALL | Plantwide | E&I-BULK | Turnover | E.S. Fox | 87 | ELE-JB-154; ELE-LCS-154; ELE-PNL-154; ELE-JB-155; ELE-LCS-155; ELE-PNL-155; ELE-JB-156 | 0 |
| Z01-B | F-101 In-vessel | BLK-230 | Commissioning/Operation | Kiewit/HMS remote-handling team | 80 | BLK-S01-I1; BLK-S01-I2; BLK-S01-O1; BLK-S01-O2; BLK-S01-O3; BLK-S02-I1; BLK-S02-I2 | 0 |
| Z01-D | F-101 Lower ports | DIV-240 | Commissioning/Operation | Kiewit/HMS remote-handling team | 48 | DIV-S01-C1; DIV-S01-C2; DIV-S01-C3; DIV-S02-C1; DIV-S02-C2; DIV-S02-C3; DIV-S03-C1 | 0 |
| ALL | Sitewide / Defined Lift Zones | LIFTING-HANDLING | Removal/Demobilization | Bechtel/Aecon/Kiewit | 48 | TMP-CRN-RT-012; TMP-MH-BML-012; TMP-MH-FLT-012; TMP-MH-MST-012; TMP-MH-SCI-012; TMP-MH-TLH-012; TMP-CRN-RT-013 | 0 |
| Z01 | F-101 | VAC | Commissioning/Operation | E.S. Fox | 30 | DEV-VAC-MTR-017; DEV-VAC-PNL-017; DEV-VAC-MTR-018; DEV-VAC-PNL-018; DEV-VAC-MTR-019; DEV-VAC-PNL-019; DEV-VAC-MTR-020 | 0 |
| Z01 | F-101 | DMS | Turnover | E.S. Fox/package contractor | 30 | DEV-DMS-VLV-032; DEV-DMS-VLV-033; DEV-DMS-VLV-034; DEV-DMS-VLV-035; DEV-DMS-VLV-036; DEV-DMS-VLV-037; DEV-DMS-VLV-038 | 0 |

## 2030-12

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Plantwide | E&I-BULK | Commissioning/Operation | E.S. Fox | 89 | ELE-JB-154; ELE-LCS-154; ELE-PNL-154; ELE-JB-155; ELE-LCS-155; ELE-PNL-155; ELE-JB-156 | 0 |
| Z01 | F-101/F-102 | DIA-330 | Turnover | E.S. Fox/HMS | 64 | DIA-IR-031; DIA-MAG-031; DIA-STR-031; DIA-IR-032; DIA-MAG-032; DIA-STR-032; DIA-MAG-033 | 0 |
| ALL | Plantwide | E&I-BULK | Turnover | E.S. Fox | 62 | ELE-JB-184; ELE-PNL-184; ELE-JB-185; ELE-PNL-185; ELE-JB-186; ELE-PNL-186; ELE-JB-187 | 0 |
| Z01 | F-104 | NBI | Commissioning/Operation | E.S. Fox | 32 | DEV-NBI-MTR-016; DEV-NBI-PNL-016; DEV-NBI-MTR-017; DEV-NBI-PNL-017; DEV-NBI-MTR-018; DEV-NBI-PNL-018; DEV-NBI-MTR-019 | 0 |
| Z01 | F-105 | ECH | Commissioning/Operation | E.S. Fox | 32 | DEV-ECH-MTR-016; DEV-ECH-PNL-016; DEV-ECH-MTR-017; DEV-ECH-PNL-017; DEV-ECH-MTR-018; DEV-ECH-PNL-018; DEV-ECH-MTR-019 | 0 |
| ALL | Sitewide / Defined Lift Zones | LIFTING-HANDLING | Removal/Demobilization | Bechtel/Aecon/Kiewit | 32 | TMP-MH-BML-022; TMP-MH-FLT-022; TMP-MH-SCI-022; TMP-MH-TLH-022; TMP-MH-BML-023; TMP-MH-FLT-023; TMP-MH-SCI-023 | 0 |
| Z01 | F-105 | ICH | Commissioning/Operation | E.S. Fox | 32 | DEV-ICH-MTR-001; DEV-ICH-PNL-001; DEV-ICH-MTR-002; DEV-ICH-PNL-002; DEV-ICH-MTR-003; DEV-ICH-PNL-003; DEV-ICH-MTR-004 | 0 |
| Z01 | F-105 | ECH | Commissioning/Operation | E.S. Fox/package contractor | 31 | DEV-ECH-VLV-031; DEV-ECH-VLV-032; DEV-ECH-VLV-033; DEV-ECH-VLV-034; DEV-ECH-VLV-035; DEV-ECH-VLV-036; DEV-ECH-VLV-037 | 0 |

## 2031-01

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Fabrication Shops / Workfronts | FAB-NDE-MET | Removal/Demobilization | Bechtel/Aecon/Kiewit/E.S. Fox | 200 | TMP-FAB-BEV-001; TMP-FAB-PBM-001; TMP-FAB-PSB-001; TMP-MET-LT-001; TMP-MET-PGM-001; TMP-MET-SCN-001; TMP-MET-TS-001 | 0 |
| Z01 | F-101/F-102 | DIA-330 | Commissioning/Operation | E.S. Fox/HMS | 161 | DIA-ECE-001; DIA-INT-001; DIA-IR-001; DIA-MAG-001; DIA-NEU-001; DIA-RGA-001; DIA-STR-001 | 0 |
| ALL | Plantwide | E&I-BULK | Commissioning/Operation | E.S. Fox | 62 | ELE-JB-185; ELE-PNL-185; ELE-JB-186; ELE-PNL-186; ELE-JB-187; ELE-PNL-187; ELE-JB-188 | 0 |
| ALL | Plantwide | E&I-BULK | Turnover | E.S. Fox | 37 | ELE-JB-215; ELE-PNL-215; ELE-JB-216; ELE-PNL-216; ELE-JB-217; ELE-PNL-217; ELE-JB-218 | 0 |
| Z01 | F-101 | DMS | Commissioning/Operation | E.S. Fox | 32 | DEV-DMS-MTR-001; DEV-DMS-PNL-001; DEV-DMS-MTR-002; DEV-DMS-PNL-002; DEV-DMS-MTR-003; DEV-DMS-PNL-003; DEV-DMS-MTR-004 | 0 |
| ALL | Plantwide | E&I-BULK | Mechanical Completion | E.S. Fox | 31 | ELE-JB-307; ELE-JB-308; ELE-JB-309; ELE-JB-310; ELE-JB-311; ELE-JB-312; ELE-JB-313 | 0 |
| Z01 | F-101 | DMS | Commissioning/Operation | E.S. Fox/package contractor | 31 | DEV-DMS-VLV-001; DEV-DMS-VLV-002; DEV-DMS-VLV-003; DEV-DMS-VLV-004; DEV-DMS-VLV-005; DEV-DMS-VLV-006; DEV-DMS-VLV-007 | 0 |
| Z01 | F-101 | DMS | Commissioning/Operation | E.S. Fox | 31 | DEV-DMS-INS-001; DEV-DMS-INS-002; DEV-DMS-INS-003; DEV-DMS-INS-004; DEV-DMS-INS-005; DEV-DMS-INS-006; DEV-DMS-INS-007 | 0 |

## 2031-02

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Fabrication Shops / Workfronts | FAB-NDE-MET | Removal/Demobilization | Bechtel/Aecon/Kiewit/E.S. Fox | 62 | TMP-MET-LT-017; TMP-MET-TS-017; TMP-NDE-PT-017; TMP-NDE-UT-017; TMP-WLD-GTA-017; TMP-WLD-ORB-017; TMP-WLD-PWHT-017 | 0 |
| Z01 | F-101/F-102 | DIA-330 | Commissioning/Operation | E.S. Fox/HMS | 57 | DIA-IR-032; DIA-MAG-032; DIA-STR-032; DIA-MAG-033; DIA-STR-033; DIA-MAG-034; DIA-STR-034 | 0 |
| ALL | Plantwide | E&I-BULK | Commissioning/Operation | E.S. Fox | 33 | ELE-JB-216; ELE-PNL-216; ELE-JB-217; ELE-PNL-217; ELE-JB-218; ELE-PNL-218; ELE-JB-219 | 0 |
| ALL | Plantwide | E&I-BULK | Mechanical Completion | E.S. Fox | 28 | ELE-JB-338; ELE-JB-339; ELE-JB-340; ELE-JB-341; ELE-JB-342; ELE-JB-343; ELE-JB-344 | 0 |
| ALL | Plantwide | E&I-BULK | Turnover | E.S. Fox | 28 | ELE-JB-246; ELE-JB-247; ELE-JB-248; ELE-JB-249; ELE-JB-250; ELE-JB-251; ELE-JB-252 | 0 |
| Z01 | F-101 | DMS | Commissioning/Operation | E.S. Fox/package contractor | 28 | DEV-DMS-VLV-032; DEV-DMS-VLV-033; DEV-DMS-VLV-034; DEV-DMS-VLV-035; DEV-DMS-VLV-036; DEV-DMS-VLV-037; DEV-DMS-VLV-038 | 0 |
| Z01 | F-101 | VAC | Commissioning/Operation | E.S. Fox/package contractor | 28 | DEV-VAC-VLV-124; DEV-VAC-VLV-125; DEV-VAC-VLV-126; DEV-VAC-VLV-127; DEV-VAC-VLV-128; DEV-VAC-VLV-129; DEV-VAC-VLV-130 | 0 |
| Z01 | F-101 | DMS | Commissioning/Operation | E.S. Fox | 28 | DEV-DMS-INS-032; DEV-DMS-INS-033; DEV-DMS-INS-034; DEV-DMS-INS-035; DEV-DMS-INS-036; DEV-DMS-INS-037; DEV-DMS-INS-038 | 0 |

## 2031-03

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Sitewide | TEMP-ACCESS | Removal/Demobilization | Specialty contractor | 117 | TMP-ACC-MWP-001; TMP-ACC-SCF-001; TMP-ACC-TPL-001; TMP-ACC-TST-001; TMP-ACC-MWP-002; TMP-ACC-SCF-002; TMP-ACC-TPL-002 | 0 |
| ALL | Plantwide | E&I-BULK | Mechanical Completion | E.S. Fox | 31 | ELE-JB-366; ELE-JB-367; ELE-JB-368; ELE-JB-369; ELE-JB-370; ELE-JB-371; ELE-JB-372 | 0 |
| ALL | Plantwide | E&I-BULK | Commissioning/Operation | E.S. Fox | 31 | ELE-JB-244; ELE-JB-245; ELE-JB-246; ELE-JB-247; ELE-JB-248; ELE-JB-249; ELE-JB-250 | 0 |
| Z01 | F-101 | DMS | Commissioning/Operation | E.S. Fox | 31 | DEV-DMS-INS-060; DEV-DMS-INS-061; DEV-DMS-INS-062; DEV-DMS-INS-063; DEV-DMS-INS-064; DEV-DMS-INS-065; DEV-DMS-INS-066 | 0 |
| ALL | Plantwide | E&I-BULK | Turnover | E.S. Fox | 31 | ELE-JB-274; ELE-JB-275; ELE-JB-276; ELE-JB-277; ELE-JB-278; ELE-JB-279; ELE-JB-280 | 0 |
| Z01 | F-101 | VAC | Commissioning/Operation | E.S. Fox/package contractor | 31 | DEV-VAC-VLV-152; DEV-VAC-VLV-153; DEV-VAC-VLV-154; DEV-VAC-VLV-155; DEV-VAC-VLV-156; DEV-VAC-VLV-157; DEV-VAC-VLV-158 | 0 |
| Z01 | F-101 | VAC | Commissioning/Operation | E.S. Fox | 31 | DEV-VAC-INS-152; DEV-VAC-INS-153; DEV-VAC-INS-154; DEV-VAC-INS-155; DEV-VAC-INS-156; DEV-VAC-INS-157; DEV-VAC-INS-158 | 0 |
| Z08/ALL | Perimeter / Plant Buildings | SECURITY | Commissioning/Operation | Security contractor | 31 | SEC-971-CAM-274; SEC-971-CAM-275; SEC-971-CAM-276; SEC-971-CAM-277; SEC-971-CAM-278; SEC-971-CAM-279; SEC-971-CAM-280 | 0 |

## 2031-04

| Zone | Workfront | System | Event | Executor | Rows | Representative assets | Quarantine |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ALL | Sitewide | TEMP-ACCESS | Removal/Demobilization | Specialty contractor | 33 | TMP-ACC-SCF-032; TMP-ACC-TPL-032; TMP-ACC-TST-032; TMP-ACC-SCF-033; TMP-ACC-TPL-033; TMP-ACC-TST-033; TMP-ACC-SCF-034 | 0 |
| ALL | Plantwide | E&I-BULK | Mechanical Completion | E.S. Fox | 19 | ELE-JB-397; ELE-JB-398; ELE-JB-399; ELE-JB-400; ELE-JB-401; ELE-JB-402; ELE-JB-403 | 0 |
| ALL | Plantwide | E&I-BULK | Commissioning/Operation | E.S. Fox | 19 | ELE-JB-275; ELE-JB-276; ELE-JB-277; ELE-JB-278; ELE-JB-279; ELE-JB-280; ELE-JB-281 | 0 |
| Z01 | F-101 | VAC | Commissioning/Operation | E.S. Fox/package contractor | 19 | DEV-VAC-VLV-183; DEV-VAC-VLV-184; DEV-VAC-VLV-185; DEV-VAC-VLV-186; DEV-VAC-VLV-187; DEV-VAC-VLV-188; DEV-VAC-VLV-189 | 0 |
| ALL | Plantwide | E&I-BULK | Turnover | E.S. Fox | 19 | ELE-JB-305; ELE-JB-306; ELE-JB-307; ELE-JB-308; ELE-JB-309; ELE-JB-310; ELE-JB-311 | 0 |
| Z01 | F-101 | DMS | Commissioning/Operation | E.S. Fox | 19 | DEV-DMS-INS-091; DEV-DMS-INS-092; DEV-DMS-INS-093; DEV-DMS-INS-094; DEV-DMS-INS-095; DEV-DMS-INS-096; DEV-DMS-INS-097 | 0 |
| Z01 | F-101 | VAC | Commissioning/Operation | E.S. Fox | 19 | DEV-VAC-INS-183; DEV-VAC-INS-184; DEV-VAC-INS-185; DEV-VAC-INS-186; DEV-VAC-INS-187; DEV-VAC-INS-188; DEV-VAC-INS-189 | 0 |
| Z01 | F-104 | NBI | Commissioning/Operation | E.S. Fox | 19 | DEV-NBI-INS-152; DEV-NBI-INS-153; DEV-NBI-INS-154; DEV-NBI-INS-155; DEV-NBI-INS-156; DEV-NBI-INS-157; DEV-NBI-INS-158 | 0 |

# Representative exact asset genealogies

These dossiers demonstrate how scene-level work history is to be used: a character should interact with a tagged object whose receipt, installation, completion, turnover and commissioning state is knowable, rather than with a generic 'system'.

## BHT-400-PRZ-101 — Blanket heat transport pressurizer

| Field | Value |
| --- | --- |
| Location | Z03-E / H-101 |
| System / class | BHT-400 / Pressurizer |
| Owner/controller | OPG |
| Design authority | E&C/HMS |
| Supplier/OEM | BWXT/qualified process vendor |
| Installer/operator | E.S. Fox |
| Site arrival | 2028-04-01 |
| Installation start | 2028-05-01 |
| Mechanical completion | 2029-12-15 |
| Turnover | 2030-04-01 |
| Commissioning start | 2030-07-01 |
| 19-Apr-2031 custody | OPG Commissioning |
| 19-Apr-2031 state | Available |
| Dataset QA | OK |

## BHT-401-P-101 — Main blanket coolant pump

| Field | Value |
| --- | --- |
| Location | Z03-A / H-101 BHT Annex |
| System / class | BHT-401 / Pump |
| Owner/controller | OPG |
| Design authority | E&C/HMS |
| Supplier/OEM | BWXT Canada / qualified package supplier |
| Installer/operator | E.S. Fox/BWXT |
| Site arrival | 2028-02-05 |
| Installation start | 2028-03-07 |
| Mechanical completion | 2029-12-11 |
| Turnover | 2030-03-16 |
| Commissioning start | 2030-06-16 |
| 19-Apr-2031 custody | OPG Commissioning |
| 19-Apr-2031 state | Restricted test configuration following CRS-01 event |
| Dataset QA | OK |

## BHT-401-SG-101 — Steam generator / primary heat exchanger

| Field | Value |
| --- | --- |
| Location | Z03-A / H-101 BHT Annex |
| System / class | BHT-401 / Heat Exchanger |
| Owner/controller | OPG |
| Design authority | E&C/HMS |
| Supplier/OEM | BWXT Canada / qualified package supplier |
| Installer/operator | E.S. Fox/BWXT |
| Site arrival | 2028-02-10 |
| Installation start | 2028-03-12 |
| Mechanical completion | 2029-12-11 |
| Turnover | 2030-03-16 |
| Commissioning start | 2030-06-16 |
| 19-Apr-2031 custody | OPG Commissioning |
| 19-Apr-2031 state | Restricted test configuration following CRS-01 event |
| Dataset QA | OK |

## TMP-BHT-401-CRS-01 — Blanket Heat Transport Train 1 temporary commissioning recirculation skid

| Field | Value |
| --- | --- |
| Location | Z03-A / H-101 BHT Train 1 commissioning bay |
| System / class | BHT-401 / Temporary Commissioning Skid |
| Owner/controller | E&C / OPG Commissioning after turnover |
| Design authority | E&C with HMS screening |
| Supplier/OEM | Local qualified skid fabricator |
| Installer/operator | E.S. Fox / OPG Commissioning |
| Site arrival | 2030-09-03 |
| Installation start | 2030-09-22 |
| Mechanical completion | 2030-09-28 |
| Turnover | 2030-10-11 |
| Commissioning start | 2030-10-12 |
| 19-Apr-2031 custody | Investigation control / OPG |
| 19-Apr-2031 state | Isolated and preserved after 2031-04-12 high-potential near miss |
| Dataset QA | OK |

## BLK-S01-I1 — Blanket sector 1 segment I1

| Field | Value |
| --- | --- |
| Location | Z01-B / F-101 In-vessel |
| System / class | BLK-230 / Breeding Blanket Segment |
| Owner/controller | OPG |
| Design authority | HMS |
| Supplier/OEM | MHI/HMS-qualified suppliers |
| Installer/operator | Kiewit/HMS remote-handling team |
| Site arrival | 2029-03-06 |
| Installation start | 2029-07-13 |
| Mechanical completion | 2030-08-31 |
| Turnover | 2030-10-31 |
| Commissioning start | 2030-11-15 |
| 19-Apr-2031 custody | OPG Commissioning |
| 19-Apr-2031 state | Installed / coolant functional testing |
| Dataset QA | OK |

## DIV-S01-C1 — Divertor sector 1 cassette 1

| Field | Value |
| --- | --- |
| Location | Z01-D / F-101 Lower ports |
| System / class | DIV-240 / Divertor Cassette |
| Owner/controller | OPG |
| Design authority | HMS |
| Supplier/OEM | MHI/HMS-qualified suppliers |
| Installer/operator | Kiewit/HMS remote-handling team |
| Site arrival | 2029-06-08 |
| Installation start | 2029-11-19 |
| Mechanical completion | 2030-07-31 |
| Turnover | 2030-10-31 |
| Commissioning start | 2030-11-15 |
| 19-Apr-2031 custody | OPG Commissioning |
| 19-Apr-2031 state | Installed / coolant functional testing |
| Dataset QA | OK |

## MAG-CSM-01 — Central-solenoid module 1

| Field | Value |
| --- | --- |
| Location | Z01-B / F-101 Tokamak Building |
| System / class | MAG-CS / Superconducting Magnet |
| Owner/controller | OPG |
| Design authority | HMS |
| Supplier/OEM | HMS/MHI-qualified supply chain |
| Installer/operator | Kiewit/HMS |
| Site arrival | 2028-11-08 |
| Installation start | 2029-07-09 |
| Mechanical completion | 2029-09-27 |
| Turnover | 2030-11-01 |
| Commissioning start | 2031-01-15 |
| 19-Apr-2031 custody | OPG Commissioning |
| 19-Apr-2031 state | Cold / integrated commissioning |
| Dataset QA | OK |

## MAG-CSM-02 — Central-solenoid module 2

| Field | Value |
| --- | --- |
| Location | Z01-B / F-101 Tokamak Building |
| System / class | MAG-CS / Superconducting Magnet |
| Owner/controller | OPG |
| Design authority | HMS |
| Supplier/OEM | HMS/MHI-qualified supply chain |
| Installer/operator | Kiewit/HMS |
| Site arrival | 2028-12-03 |
| Installation start | 2029-07-16 |
| Mechanical completion | 2029-09-27 |
| Turnover | 2030-11-01 |
| Commissioning start | 2031-01-15 |
| 19-Apr-2031 custody | OPG Commissioning |
| 19-Apr-2031 state | Cold / integrated commissioning |
| Dataset QA | OK |

## MAG-CSM-03 — Central-solenoid module 3

| Field | Value |
| --- | --- |
| Location | Z01-B / F-101 Tokamak Building |
| System / class | MAG-CS / Superconducting Magnet |
| Owner/controller | OPG |
| Design authority | HMS |
| Supplier/OEM | HMS/MHI-qualified supply chain |
| Installer/operator | Kiewit/HMS |
| Site arrival | 2028-12-28 |
| Installation start | 2029-07-23 |
| Mechanical completion | 2029-09-27 |
| Turnover | 2030-11-01 |
| Commissioning start | 2031-01-15 |
| 19-Apr-2031 custody | OPG Commissioning |
| 19-Apr-2031 state | Cold / integrated commissioning |
| Dataset QA | OK |

## MAG-CSM-04 — Central-solenoid module 4

| Field | Value |
| --- | --- |
| Location | Z01-B / F-101 Tokamak Building |
| System / class | MAG-CS / Superconducting Magnet |
| Owner/controller | OPG |
| Design authority | HMS |
| Supplier/OEM | HMS/MHI-qualified supply chain |
| Installer/operator | Kiewit/HMS |
| Site arrival | 2029-01-22 |
| Installation start | 2029-07-30 |
| Mechanical completion | 2029-09-27 |
| Turnover | 2030-11-01 |
| Commissioning start | 2031-01-15 |
| 19-Apr-2031 custody | OPG Commissioning |
| 19-Apr-2031 state | Cold / integrated commissioning |
| Dataset QA | OK |

## MAG-CSM-05 — Central-solenoid module 5

| Field | Value |
| --- | --- |
| Location | Z01-B / F-101 Tokamak Building |
| System / class | MAG-CS / Superconducting Magnet |
| Owner/controller | OPG |
| Design authority | HMS |
| Supplier/OEM | HMS/MHI-qualified supply chain |
| Installer/operator | Kiewit/HMS |
| Site arrival | 2029-02-16 |
| Installation start | 2029-08-06 |
| Mechanical completion | 2029-09-27 |
| Turnover | 2030-11-01 |
| Commissioning start | 2031-01-15 |
| 19-Apr-2031 custody | OPG Commissioning |
| 19-Apr-2031 state | Cold / integrated commissioning |
| Dataset QA | OK |

## MAG-CSM-06 — Central-solenoid module 6

| Field | Value |
| --- | --- |
| Location | Z01-B / F-101 Tokamak Building |
| System / class | MAG-CS / Superconducting Magnet |
| Owner/controller | OPG |
| Design authority | HMS |
| Supplier/OEM | HMS/MHI-qualified supply chain |
| Installer/operator | Kiewit/HMS |
| Site arrival | 2029-03-13 |
| Installation start | 2029-08-13 |
| Mechanical completion | 2029-09-27 |
| Turnover | 2030-11-01 |
| Commissioning start | 2031-01-15 |
| 19-Apr-2031 custody | OPG Commissioning |
| 19-Apr-2031 state | Cold / integrated commissioning |
| Dataset QA | OK |

## MAG-PF-01 — Poloidal-field coil 1

| Field | Value |
| --- | --- |
| Location | Z01-B / F-101 Tokamak Building |
| System / class | MAG-PF / Superconducting Magnet |
| Owner/controller | OPG |
| Design authority | HMS |
| Supplier/OEM | MHI/HMS-qualified supply chain |
| Installer/operator | Kiewit/MHI |
| Site arrival | 2027-09-29 |
| Installation start | 2027-12-10 |
| Mechanical completion | 2029-08-01 |
| Turnover | 2030-10-15 |
| Commissioning start | 2030-11-01 |
| 19-Apr-2031 custody | OPG Commissioning |
| 19-Apr-2031 state | Cold / integrated commissioning |
| Dataset QA | OK |

## MAG-PF-02 — Poloidal-field coil 2

| Field | Value |
| --- | --- |
| Location | Z01-B / F-101 Tokamak Building |
| System / class | MAG-PF / Superconducting Magnet |
| Owner/controller | OPG |
| Design authority | HMS |
| Supplier/OEM | MHI/HMS-qualified supply chain |
| Installer/operator | Kiewit/MHI |
| Site arrival | 2027-12-28 |
| Installation start | 2028-03-19 |
| Mechanical completion | 2029-08-01 |
| Turnover | 2030-10-15 |
| Commissioning start | 2030-11-01 |
| 19-Apr-2031 custody | OPG Commissioning |
| 19-Apr-2031 state | Cold / integrated commissioning |
| Dataset QA | OK |

## MAG-PF-03 — Poloidal-field coil 3

| Field | Value |
| --- | --- |
| Location | Z01-B / F-101 Tokamak Building |
| System / class | MAG-PF / Superconducting Magnet |
| Owner/controller | OPG |
| Design authority | HMS |
| Supplier/OEM | MHI/HMS-qualified supply chain |
| Installer/operator | Kiewit/MHI |
| Site arrival | 2028-03-27 |
| Installation start | 2028-06-27 |
| Mechanical completion | 2029-08-01 |
| Turnover | 2030-10-15 |
| Commissioning start | 2030-11-01 |
| 19-Apr-2031 custody | OPG Commissioning |
| 19-Apr-2031 state | Cold / integrated commissioning |
| Dataset QA | OK |

## MAG-PF-04 — Poloidal-field coil 4

| Field | Value |
| --- | --- |
| Location | Z01-B / F-101 Tokamak Building |
| System / class | MAG-PF / Superconducting Magnet |
| Owner/controller | OPG |
| Design authority | HMS |
| Supplier/OEM | MHI/HMS-qualified supply chain |
| Installer/operator | Kiewit/MHI |
| Site arrival | 2028-06-25 |
| Installation start | 2028-10-05 |
| Mechanical completion | 2029-08-01 |
| Turnover | 2030-10-15 |
| Commissioning start | 2030-11-01 |
| 19-Apr-2031 custody | OPG Commissioning |
| 19-Apr-2031 state | Cold / integrated commissioning |
| Dataset QA | OK |

## MAG-PF-05 — Poloidal-field coil 5

| Field | Value |
| --- | --- |
| Location | Z01-B / F-101 Tokamak Building |
| System / class | MAG-PF / Superconducting Magnet |
| Owner/controller | OPG |
| Design authority | HMS |
| Supplier/OEM | MHI/HMS-qualified supply chain |
| Installer/operator | Kiewit/MHI |
| Site arrival | 2028-09-23 |
| Installation start | 2029-01-13 |
| Mechanical completion | 2029-08-01 |
| Turnover | 2030-10-15 |
| Commissioning start | 2030-11-01 |
| 19-Apr-2031 custody | OPG Commissioning |
| 19-Apr-2031 state | Cold / integrated commissioning |
| Dataset QA | OK |

## MAG-PF-06 — Poloidal-field coil 6

| Field | Value |
| --- | --- |
| Location | Z01-B / F-101 Tokamak Building |
| System / class | MAG-PF / Superconducting Magnet |
| Owner/controller | OPG |
| Design authority | HMS |
| Supplier/OEM | MHI/HMS-qualified supply chain |
| Installer/operator | Kiewit/MHI |
| Site arrival | 2028-12-22 |
| Installation start | 2029-04-23 |
| Mechanical completion | 2029-08-01 |
| Turnover | 2030-10-15 |
| Commissioning start | 2030-11-01 |
| 19-Apr-2031 custody | OPG Commissioning |
| 19-Apr-2031 state | Cold / integrated commissioning |
| Dataset QA | OK |

## LFT-F106-HBC-01 — 900-t main bridge crane 1 (tandem 1,800-t system)

| Field | Value |
| --- | --- |
| Location | Z01-A / F-106 Assembly Hall / F-101 |
| System / class | PERMANENT-HEAVY-LIFT / Permanent Crane |
| Owner/controller | OPG |
| Design authority | E&C |
| Supplier/OEM | Heavy crane OEM |
| Installer/operator | Kiewit/OEM |
| Site arrival | 2027-02-04 |
| Installation start | 2027-02-21 |
| Mechanical completion | 2027-07-01 |
| Turnover | 2027-08-01 |
| Commissioning start | 2027-08-15 |
| 19-Apr-2031 custody | OPG Operations/Commissioning |
| 19-Apr-2031 state | Operational |
| Dataset QA | OK |

## LFT-F106-HBC-02 — 900-t main bridge crane 2 (tandem 1,800-t system)

| Field | Value |
| --- | --- |
| Location | Z01-A / F-106 Assembly Hall / F-101 |
| System / class | PERMANENT-HEAVY-LIFT / Permanent Crane |
| Owner/controller | OPG |
| Design authority | E&C |
| Supplier/OEM | Heavy crane OEM |
| Installer/operator | Kiewit/OEM |
| Site arrival | 2027-02-24 |
| Installation start | 2027-03-13 |
| Mechanical completion | 2027-07-01 |
| Turnover | 2027-08-01 |
| Commissioning start | 2027-08-15 |
| 19-Apr-2031 custody | OPG Operations/Commissioning |
| 19-Apr-2031 state | Operational |
| Dataset QA | OK |

## TUR-701-HP-01 — HP turbine

| Field | Value |
| --- | --- |
| Location | Z04 / T-101 Turbine Building |
| System / class | TURBINE-ISLAND / Steam Turbine |
| Owner/controller | OPG |
| Design authority | E&C/Arabelle |
| Supplier/OEM | Arabelle Solutions / qualified suppliers |
| Installer/operator | Kiewit/E.S. Fox/OEM |
| Site arrival | 2028-05-16 |
| Installation start | 2028-06-16 |
| Mechanical completion | 2029-11-30 |
| Turnover | 2030-04-30 |
| Commissioning start | 2030-06-01 |
| 19-Apr-2031 custody | OPG Commissioning |
| 19-Apr-2031 state | Mechanical/auxiliary commissioning; no fusion steam |
| Dataset QA | OK |

## TUR-702-LP-01 — LP turbine 1

| Field | Value |
| --- | --- |
| Location | Z04 / T-101 Turbine Building |
| System / class | TURBINE-ISLAND / Steam Turbine |
| Owner/controller | OPG |
| Design authority | E&C/Arabelle |
| Supplier/OEM | Arabelle Solutions / qualified suppliers |
| Installer/operator | Kiewit/E.S. Fox/OEM |
| Site arrival | 2028-05-31 |
| Installation start | 2028-07-01 |
| Mechanical completion | 2029-11-30 |
| Turnover | 2030-04-30 |
| Commissioning start | 2030-06-01 |
| 19-Apr-2031 custody | OPG Commissioning |
| 19-Apr-2031 state | Mechanical/auxiliary commissioning; no fusion steam |
| Dataset QA | OK |

## TUR-702-LP-02 — LP turbine 2

| Field | Value |
| --- | --- |
| Location | Z04 / T-101 Turbine Building |
| System / class | TURBINE-ISLAND / Steam Turbine |
| Owner/controller | OPG |
| Design authority | E&C/Arabelle |
| Supplier/OEM | Arabelle Solutions / qualified suppliers |
| Installer/operator | Kiewit/E.S. Fox/OEM |
| Site arrival | 2028-06-15 |
| Installation start | 2028-07-16 |
| Mechanical completion | 2029-11-30 |
| Turnover | 2030-04-30 |
| Commissioning start | 2030-06-01 |
| 19-Apr-2031 custody | OPG Commissioning |
| 19-Apr-2031 state | Mechanical/auxiliary commissioning; no fusion steam |
| Dataset QA | OK |

## TUR-702-LP-03 — LP turbine 3

| Field | Value |
| --- | --- |
| Location | Z04 / T-101 Turbine Building |
| System / class | TURBINE-ISLAND / Steam Turbine |
| Owner/controller | OPG |
| Design authority | E&C/Arabelle |
| Supplier/OEM | Arabelle Solutions / qualified suppliers |
| Installer/operator | Kiewit/E.S. Fox/OEM |
| Site arrival | 2028-06-30 |
| Installation start | 2028-07-31 |
| Mechanical completion | 2029-11-30 |
| Turnover | 2030-04-30 |
| Commissioning start | 2030-06-01 |
| 19-Apr-2031 custody | OPG Commissioning |
| 19-Apr-2031 state | Mechanical/auxiliary commissioning; no fusion steam |
| Dataset QA | OK |

# Field command and information routes for scene implementation

| Situation | Route |
| --- | --- |
| Construction work before turnover | Craft/foreman -> contractor superintendent -> Bechtel package/constructor chain -> E&C field engineering/work-package coordination -> E&C design authority; HMS is engaged for protected HFRP basis; OPG retains owner/licensee oversight. |
| Nonconformance / field mismatch | Installer/QC raises condition -> Bechtel/E&C field route -> RFI/TQ/NCR/FCR as applicable -> E&C discipline/SCE disposition -> HMS/OPG concurrence when scope crosses their authority -> revised controlled direction returns to field. |
| Mechanical completion | Installer evidence -> contractor QC -> Bechtel completions -> E&C Systems Completion/QA -> punch/configuration check -> receiving preparation. |
| Turnover | Transferring organization + OPG receiving organization jointly walk down the system/work area and configuration information -> agree deficiencies/boundaries -> custody certificate/dossier -> post-turnover re-entry only by authorization. |
| Commissioning work | OPG Commissioning/system lead -> approved test/work authorization + PTW/LOTO -> operators/commissioning staff execute -> E&C/HMS/OEM support -> result/deficiency/change enters controlled record. |
| Post-turnover construction/rework | Request -> OPG receiving/work control authorization -> isolation/access -> previous contractor/authorized crew performs controlled work -> inspection/test/restoration -> configuration evidence -> release back to commissioning. |
| Information to management | Field evidence -> engineering/system status -> completion/readiness/project controls -> owner/regulator or finance/government summaries. Detail is progressively compressed; higher-level knowledge is not equivalent to raw field knowledge. |

# Data-quality quarantine and unresolved inputs

| Flag | Assets |
| --- | --- |
| OK | 21161 |
| QUARANTINE_TURNOVER_BEFORE_MC | 684 |
| QUARANTINE_BOTH | 610 |
| QUARANTINE_INSTALL_BEFORE_ARRIVAL | 192 |

OPEN items are not defects in the history; they are boundaries on what the story can claim. Exact craft names, many supervisor names, exact room coordinates, full CWP/IWP identifiers, every supplier tier, and the physical performer of M-88217 are not supported by the present source corpus. Where exact story identities are later assigned, they should be added as a separate controlled fictional personnel layer, not retroactively presented as recovered source fact.

# External precedent applied, without converting it into OFG historical fact

CNSC REGDOC-2.3.1: licensee responsibility, contractor oversight, construction readiness, turnover of SSCs/configuration information, post-turnover authorization, configuration control and commissioning interfaces.

ITER machine assembly: construction work packages released in trackable batches and decomposed by contractors into installation work packages; separate assembly workzones; controlled on-site installation where procurement scope includes installation.

OPG Darlington New Nuclear Project: contemporary Ontario nuclear-new-build precedent for deep excavation, heavy basemat construction/lifts and staged licensing/construction.

ITER/QST/other fusion precedent in Rev3: bottom-up machine assembly, captive-item sequencing, metrology, purpose-built tooling, repeated sector assembly and remote-maintenance constraints.