ONTARIO FUSION GENERATION

DEFINITIVE ENGINEERING ATLAS — REV 3

VOLUME 09 — POWER CYCLE, BALANCE OF PLANT & PLANT UTILITIES

Steam/power conversion, turbine-generator, heat rejection, water, utilities and balance-of-plant interfaces

CONTROLLED STORY CONFIGURATION CUT: 19 APRIL 2031

# Atlas control doctrine

This volume is part of the definitive self-contained story bible, not a work-package report. It preserves source-derived granularity and the engineering/configuration thread. C = controlled story/source canon; V = verified real-world precedent; E = controlled fictional engineering reconstruction; OPEN = unresolved. No precedent dimension, screening assumption, sensitivity value, code class, coordinate, vendor property, test result, or physical action is silently promoted to OFG historical fact.

For every material configuration decision the controlling information chain is: originator → information → document/record → recipient → review → authority → decision → authorized action → physical consequence → inspection/test/as-built evidence → turnover/operations baseline → later change/supersession. CLOSED/APPROVED in an information system is not proof of physical execution.

# Integrated source map

Detailed DOCX sources integrated: 3. Controlled CSV/ledger sources integrated: 0.

DOCX · OFG_Encyclopedia_RevN_Volume_09(7).docx

DOCX · OFG_Engineering_Encyclopedia_Rev2/OFG_E04_Power_Cycle_BOP_Encyclopedia_Rev2.docx

DOCX · OFG_System_Encyclopedia_Rev1/OFG_S04R1_BOP_Electrical_IandC_Utilities.docx

# Integrated controlled source — OFG_Encyclopedia_RevN_Volume_09(7).docx

Preserved at source granularity. Later explicit canon and change-provenance entries govern conflicts; source text is not silently rewritten.

# ONTARIO FUSION GENERATION PROJECT

# VOLUME IX — INTEGRATED COMMISSIONING & COMPLETION FINANCE

Operating authorization, magnet/vacuum integration, readiness governance and Project Aurora commitments

Complete chronological reference · canon cut: Saturday, 19 April 2031

Compiled from the Canonical Story Backbone Rev B, Master Reference, Backlogs 01–11, Revision Directives B–J, and controlled Rev A equipment/event datasets.

# Reference-status legend

| Status | Meaning |
| --- | --- |
| LOCKED CANON | Explicitly fixed by the controlling OFG canon at the 19 April 2031 cut. |
| CANONICAL FRAMEWORK | Institutional/technical architecture is fixed; some lower-level dates, names, quantities or records remain to be reconstructed. |
| VERIFIED PRECEDENT CONSTRAINT | Real-world analogue constrains plausibility; it is not itself an OFG event. |
| OPEN / CONTROLLED | The backlog identifies the subject, but the source set does not yet support a unique historical answer. Do not invent one. |
| WORKING DATASET | Rev A asset/event data support chronology and forensic work, but known semantic/date anomalies mean the rows are not self-authenticating canon. |

The encyclopedia favors explicit uncertainty over false precision. It records what is known at the story cut, what is structurally required by the project, and what remains unresolved.

# Period definition

Coverage: January-March 2031. This volume is chronological: every topical domain is described as it exists during this period rather than as a timeless subject.

# Canonical chronicle

## January — operating/commissioning authorization

The required authorization for the defined machine-commissioning phase is obtained. It is not commercial-operation approval; later D-T, higher-power and power-operation hold points remain.

## January-February — magnet commissioning

Final cooldown, superconducting-transition verification, current-lead work, low-current energization, polarity, circuit parameters, quench detection, fast discharge, ground-fault testing and progressive current increase proceed stepwise because of stored-energy risk.

## February-March — machine integration

Vacuum/bakeout campaigns, cryopumps, gas injection, heating dummy loads, diagnostics, machine-protection testing, disruption-mitigation tests without real plasma, control sequences and degraded-mode tests intensify.

## March — First Plasma Readiness Programme

The FP Readiness Register becomes the executive compression layer. Prerequisites include magnets, vacuum, cryogenics, cooling, DCS, MPS, diagnostics, heating, disruption mitigation, procedures, operator qualification, emergency readiness and regulatory conditions. Items are blockers, must-close, conditional/deferred or post-FP.

## Aurora commitments

AUR-SCF-001 C$1.40B, AUR-PP-001 C$750M target, AUR-EQ-001 C$600M OPG completion equity and the C$500M accordion form the supplemental financing package. The first three are committed/conditional to different degrees; the accordion is not liquidity until a counterparty commits.

## Organization transition

Construction headcount falls while OPG commissioning/operations-readiness, maintainers, system engineers and OEM specialists rise. The later master reference supersedes the old ~680 whole-site figure: normal weekday controlled-site population is about 820-880, use ~850; Saturday 19 Apr is about 500-600.

# Institutional / business / government state

# Project Aurora — March 2031 position

| Instrument | Amount | Status / role |
| --- | --- | --- |
| AUR-SCF-001 Senior Supplemental Completion Facility | C$1.40B | Committed subject to closing/conditions precedent; bank liquidity. |
| AUR-PP-001 Institutional Private Placement | C$0.75B | Committed/staged placement; final allocations/syndication still active. |
| AUR-EQ-001 OPG completion equity | C$0.60B | Binding conditional sponsor commitment. |
| Accordion | C$0.50B | Uncommitted option; no committed counterparty on 19 Apr 2031. |

# April-opening financing arithmetic

| Measure | Amount | Meaning |
| --- | --- | --- |
| Existing committed financing capacity | C$45.80B | Pre-Aurora committed capacity in the fictional capital stack. |
| Existing + committed/conditional Aurora | C$48.55B | Includes C$2.75B supplemental committed/conditional capital. |
| Target including accordion | C$49.05B | Adds C$0.50B uncommitted accordion. |
| Daniel initial liquidity figure | C$1.70B | A narrower transaction/liquidity number; not total Aurora capacity. |

# Working asset/event chronology for this period

The Rev A asset/event datasets are included as a chronology aid, not as self-authenticating canon. Known semantic/date anomalies are quarantined; counts below are descriptive of the working dataset and must not override the controlling narrative/configuration record.

| Year | Procured / mobilized | Site arrivals | Installation starts | MC | Turnovers | Commissioning starts | Event rows |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2031 | 0 | 0 | 0 | 322 | 1504 | 3637 | 6191 |

# Detailed source-derived canonical research

This section carries forward the detailed research already absorbed into the Canonical Story Backbone. It is reorganized under the period volume so other threads can reference the underlying institutional, contractual, technical and documentary history rather than only the compressed chronology.

## Detailed January-March 2031 chronology

delivery/interface issues consume the remaining margin.

### The programme changes

First Plasma: 31 May → 30 June 2031.

This is OEB-3, the current baseline.

### Importantly

Public commitment

### remains

First Plasma in the first half of 2031.

So June 30 is not merely another scheduler’s date.

It has become the outside edge of a publicly visible commitment.

That gives us a very strong source of schedule pressure without inventing a politician stupid enough to order an unsafe plasma shot.

### 19. Project Aurora begins because the schedule has economic consequences

### Late 2030 cost-to-complete work shows

higher IDC higher commissioning costs vendor extensions retained construction staff contingency drawdown less remaining liquidity.

Thus the financing problem Daniel sees is directly connected to the construction schedule.

December 2030

OPG and financial advisers formally begin supplemental-completion financing work.

January 2031

JPMorgan/MUFG/SMBC and institutional investors begin Project Aurora diligence.

February–March

Lenders’ Technical Adviser updates cost-to-complete and schedule assessment.

Project Aurora reaches commitment/documentation stage.

April 2031

Aurora is committed/conditional but not fully closed, exactly as already established.

This is why Daniel is working on it on April 19.

### 20. January 2031 — operating/commissioning authorization

The required CNSC authorization is obtained for the upcoming machine commissioning phase.

### This does not mean

plant approved for commercial operation.

It means the regulatory conditions required to progress into defined operating/commissioning states have been satisfied.

### Additional hold points remain before

D-T higher fusion power

electric power operation.

### 21. January–February 2031 — magnet commissioning

The machine is now genuinely alive.

### Activities include

final cooldown superconducting transition verification current-lead commissioning low-current coil energization polarity tests circuit resistance/inductance checks quench detection fast discharge ground-fault tests progressive current increase.

This is done stepwise because a superconducting system contains enormous stored energy.

### 22. February–March 2031 — machine integration

Vacuum campaigns intensify.

Vessel bakeout.

Cryopump commissioning.

## Project Aurora commitment documentation and privity implications

control-room authority, system tagging and construction re-entry.

### Once OPG Commissioning accepts a subsystem

Bechtel no longer has unfettered control of that equipment merely because its subcontractor installed it.

Bechtel remains statutory constructor for active construction work areas.

OPG controls commissioned plant boundaries.

This mixed authority is carefully mapped geographically and functionally.

CNSC explicitly requires controlled construction-to-commissioning turnover, documented deficiencies and authorization before the previous party returns to transferred equipment.

Fluor enters in 2029

OFG-SVC-FLU-001

E&C retains Fluor for completion/turnover surge support.

### Fluor personnel supplement

completion database administration, turnover dossier quality, punch management and commissioning handover support.

### Fluor does not gain

design authority constructor authority commissioning authority.

It is staff augmentation/specialist methodology support.

This prevents the project from accidentally acquiring a second EPC chain.

2029 rebaseline and EPC Amendment No. 2

### When First Plasma moves from March 31 to May 31, 2031

OFG-EPC-AMD-02

does several things.

It updates contractual milestone dates.

It extends selected site staffing and vendor support.

It adjusts estimated reimbursable duration-related costs.

It preserves claims positions where causation remains disputed.

Crucially, a schedule amendment does not necessarily constitute an admission that E&C caused the delay.

That distinction will matter to later liability analysis.

November 2030: EPC Amendment No. 3

### First Plasma moves again

May 31 → June 30, 2031.

OFG-EPC-AMD-03

### This amendment

updates milestone schedule, increases selected owner/EPC budget allowances, extends Bechtel and OEM field-service windows, revises construction/completion staffing assumptions and adjusts portions of the target-cost incentive regime.

It does not give anybody permission to redefine technical First-Plasma readiness.

The date changes.

The readiness criteria do not.

This is the contractual manifestation of date versus state.

December 2030: Project Aurora begins

### OPG/OFG LP appoints JPMorgan under

AUR-MAND-001 — Financial Advisory, Structuring and Placement Engagement Letter.

### JPMorgan is responsible for

supplemental financing structure, financial modelling, investor materials, placement work, bank underwriting coordination and Credit Committee materials.

MUFG remains deeply involved because of its existing agent/relationship role.

SMBC remains a principal Japanese relationship bank.

January–March 2031: Aurora commitment documentation

Supplemental Senior Completion Facility

AUR-SCF-001

Amount: C$1.40B.

### Borrower

OFG LP.

### Arrangers

JPMorgan/MUFG/SMBC group.

The agreement is signed/committed subject to Conditions Precedent.

### Those CPs include, among other things

updated cost-to-complete information LTA report updated schedule regulatory status absence of specified defaults representation bring-downs completion-support documentation.

Institutional supplemental placement

AUR-PP-001

### Target

C$750M.

By April 19 there are signed or highly advanced conditional commitments sufficient for the transaction to model C$750M as committed/conditional capital, but final allocations and syndication remain active.

This is why Daniel still has an investor tracker.

One investor can reduce its final funded amount before closing if a specific CP fails.

### Hence the stress case

750M \rightarrow 500M.

OPG completion-equity commitment

AUR-EQ-001

OPG commits C$600M additional equity subject to defined funding conditions.

This is binding but contingent.

It is separate from Ontario’s existing C$3B facility.

Accordion

The C$500M accordion is merely a contractual option for lenders/investors to increase commitments.

There is no committed counterparty for that C$500M on April 19.

That remains canon.

The April 12 near miss enters the contract structure

This is where all this detail starts paying off.

### The near miss does not automatically constitute

an EPC default,

a financing default,

a reportable material adverse effect,

a warranty breach,

or a failure of an Aurora CP.

On April 12 nobody yet knows enough.

But the event triggers information duties under several contracts.

### Under the EPC

E&C must notify OPG of a significant safety/quality/configuration event.

### Under Bechtel’s agreement

Bechtel must preserve evidence and cooperate with investigation for work within its execution history.

### Under the relevant subcontract

the installing/maintenance contractor must provide records and personnel.

### Under HMS agreements

HMS must be notified if the event potentially implicates the qualified technology basis.

### Under financing agreements

OPG/OFG must disclose developments meeting defined materiality/reporting thresholds.

### Under Aurora

the disclosure schedules and representation bring-down may need updating before closing.

### Under insurance

notice may be required even before anyone knows whether an insured loss exists.

Therefore by April 19 Daniel can be aware of a bland financing-level description while Yuji possesses vastly richer technical information.

No contradiction.

The exact privity network on April 19, 2031

This is the relationship map that characters should implicitly live inside.

Party

Direct contractual counterparties in OFG

Important parties with no ordinary privity

OFG Project LP

OPG, E&C, equity investors, lenders, insurers

Aecon, Kiewit, E.S. Fox, Bird

OPG

OFG LP, HMS, E&C as named project party, Bechtel via constructor direct agreement, Hydro One, financing/support parties

construction subcontractors

HMS

OPG, E&C Canada

Bechtel, Aecon, Kiewit, E.S. Fox

E&C Canada

OFG LP/OPG, HMS, Bechtel, MHI, IHI, JGC, BWXT, Arabelle, GE Vernova, Emerson, Westinghouse, AtkinsRéalis, Fluor

Bechtel’s lower-tier subcontractors unless direct rights apply

Bechtel

E&C, OPG/OFG via constructor direct agreement, Aecon, Kiewit, E.S. Fox, Bird, specialty contractors

HMS in ordinary commercial matters; lenders

Aecon

Bechtel

OPG, HMS, E&C commercially

Kiewit

Bechtel

OPG, HMS, E&C commercially

E.S. Fox

Bechtel

OPG, HMS, E&C commercially

Bird

Bechtel

OPG/HMS/E&C commercially

MHI/IHI/JGC/etc.

E&C

construction trades ordinarily

CNSC

none

everyone — regulator, not contractor

Sargent & Lundy

lender group/agent under LTA engagement

E&C/Bechtel except information-access provisions

JPMorgan

OFG/OPG under finance/mandate documents and bank facilities

field contractors

CGF/BOF

OFG LP/OPG investment agreements

E&C/Bechtel

Indigenous investment vehicle

OFG LP; own financing parties

EPC/construction chain

Hydro One

OPG/OFG LP connection agreements

E&C/Bechtel except interface coordination

That privity structure is critical.

What happens when HMS sees something wrong in the field

HMS does not call an E.S. Fox foreman and issue a contractual order.

Suppose Yuji sees a support installed outside HFRP requirements.

### His path is

Yuji/HMS

reports through the E&C technical organization.

E&C determines whether a formal field instruction/design disposition is necessary.

If work must stop immediately for personal safety, ordinary site stop-work rights apply.

### Otherwise the contractual technical path is

HMS \rightarrow E\&C \rightarrow Bechtel \rightarrow E.S.\ Fox.

OPG may intervene from the licensee side if nuclear/configuration consequences justify it.

This separation is intentional.

What happens when Bechtel sees a design problem

Bechtel cannot redesign HMS hardware.

### Bechtel sends

RFI / field query → E&C.

E&C resolves the issue internally if it is ordinary plant engineering.

### If HFRP technology is implicated

E&C → HMS.

### If the licensing basis is implicated

E&C → OPG.

### Only after resolution does an approved design instruction return

E&C → Bechtel → performing subcontractor.

That is why field changes can take time.

What happens when OPG wants the schedule accelerated

OPG cannot simply call Kiewit and demand another shift.

Its contract is not with Kiewit.

## First-Plasma documentation and equipment-document genealogy

test problem instrument problem procedure problem installation problem design problem.

### Possible downstream document

DCR

DCN

temporary modification

repair work order

retest request.

CNSC explicitly expects deviations to be assessed for safety implications, root cause, continuation implications, design changes, safety-analysis updates and retesting where

appropriate.

### 56. Operations documents begin before startup

Commissioning is used to validate operating procedures. CNSC explicitly expects operating procedures to be verified during commissioning and updated from commissioning experience.

### So OPG is already producing

OP-SOP-xxx — System Operating Procedure

OP-START-xxx — System Startup Procedure

OP-SHUT-xxx — Shutdown Procedure

OP-ARP-xxx — Alarm Response Procedure

OP-AOP-xxx — Abnormal Operating Procedure

OP-EOP-xxx — Emergency Operating Procedure

OP-SURV-xxx — Surveillance Procedure

OP-CHEM-xxx — Chemistry Procedure

OP-RP-xxx — Radiation Protection Procedure

OP-WM-xxx — Work Management Procedure

### 57. Maintenance baseline

### Before operations

MNT-PROG-001 — Plant Maintenance Program

MNT-PM-001 — Preventive Maintenance Basis

MNT-EQ-001 — Maintenance Equipment Master

MNT-SP-001 — Spare Parts Catalogue

MNT-VMI-001 — Vendor Maintenance Instruction Register

MNT-LUBE-001 — Lubrication Program

MNT-CAL-001 — Calibration Program

MNT-AGE-001 — Aging Management Program

### 58. Training and operating readiness

TRN-PROG-001 — Training Program

TRN-JTA-xxx — Job/Task Analysis

TRN-LP-xxx — Lesson Plan

TRN-SIM-001 — Simulator Configuration Baseline

TRN-EXAM-xxx — Qualification Examination

TRN-QUAL-001 — Qualified Personnel Register

OPS-STAFF-001 — Staffing Plan

OPS-MINCOMP-001 — Minimum Shift Complement Basis

OPS-ORR-001 — Operations Readiness Review Plan

### 59. First Plasma documentation

By early 2031 a special dossier appears.

FP-REQ-001 — First Plasma Entry Requirements

FP-RR-001 — First Plasma Readiness Register

FP-PRQ-001 — Prerequisite Matrix

FP-OPEN-001 — Open Item Register

FP-CONF-001 — Plant Configuration Certificate

FP-SYS-001 — Required Systems Availability Report

FP-OPS-001 — Operations Readiness Certificate

FP-TRN-001 — Personnel Qualification Confirmation

FP-ERP-001 — Emergency Preparedness Confirmation

FP-REG-001 — Regulatory Commitment Status

FP-CM-001 — Configuration Management Status

### Then

FP-RRB-001 — First Plasma Readiness Review Board Package

### and ultimately

FP-AUTH-001 — OPG First Plasma Authorization

### plus any required

REG-RHP-FP — CNSC Hold Point / Authorization Clearance.

### 60. The document Daniel sees is many layers removed

### The engineering world described above eventually produces

PMR-MAR2031 — OPG Monthly Project Report

COST-MAR2031 — Monthly Cost Report

IMS-APR2031 — Integrated Master Schedule Update

RISK-APR2031 — Project Risk Register Update

COMSTAT-APR2031 — Commissioning Status Report

S&L-MMR-APR2031 — Lenders’ Monthly Monitoring Report

### Then JPMorgan creates

AUR-MDL-Revxx — Project Aurora Model

AUR-S&U — Sources & Uses

AUR-C2C — Cost-to-Complete

AUR-LIQ — Completion Liquidity

AUR-SENS — Sensitivity Case

AUR-CCM — Credit Committee Memorandum

This is why Daniel never sees the restraint drawing unless the problem becomes financially material.

### 61. The complete document genealogy of one pump

Now we can illustrate what “every step” actually means.

### For BHT-401-P-101A, the chain is approximately

Project phase

Document

Owner requirement

ORD requirement for blanket heat-removal capability

Plant requirements

BHT functional/performance requirement

System architecture

BHT system allocation

Design

SDD-BHT-400

Process engineering

BHT P&ID

Equipment definition

Pump datasheet

Specification

Main coolant pump technical specification

Calculation

flow/head/NPSH/seismic/load calculations

Procurement

material requisition

Tender

RFQ

Selection

technical bid evaluation

Contract

purchase order

Vendor design

GA/interface/foundation drawings

QA

supplier quality plan

Manufacture

MIP/ITP

Materials

material certificates

Fabrication

weld/NDE/manufacturing records

Factory testing

FAT procedure/report

Acceptance

certificate of conformance

Shipping

preservation/release documents

Receiving

site receipt inspection

Storage

preservation record

Construction planning

CWP

Field execution

IWP

Installation

method statement

Foundation

foundation release

Setting

equipment setting record

Alignment

alignment report

Anchorage

bolt/restraint inspection

Grout

grouting record

Electrical

motor cable/testing

I&C

vibration/temp/pressure loops

QC

ITP sign-offs

Configuration

field changes/NCR closeout

Mechanical completion

MC certificate

Turnover

TOS-BHT-401-A

Commissioning

SCP-BHT-400

Test

CPT-BHT-401-017

Results

CTR-BHT-401-017

Acceptance

Test Completion Certificate

Operation

operating procedure

Maintenance

PM task

Intervention

M-88217

Current configuration

CM database / equipment history

That is the level of documentary continuity we want.

# Integrated OFG encyclopedia — period state

## Operating/commissioning authorization

In Q1 2031 the regulatory/owner authorization needed for the defined machine-commissioning phase is in place. This is not commercial-operation approval and does not erase later hold points for tritium/D-T, higher-power operation or power ascension. The licensing boundary allows the project to perform the staged tests needed to establish readiness while preserving the regulator's ability to stop progression when evidence is insufficient.

## Magnet and machine integration

January-February magnet work progresses from cooldown and superconducting-transition verification to low-current energization, polarity, circuit parameter, quench detection, fast discharge, ground fault and staged current increase. February-March integrates vacuum/bakeout, cryopumps, gas systems, heating dummy loads, diagnostics, machine protection, disruption-mitigation logic and degraded-mode sequences. These activities turn subsystem completion into evidence that the machine can function as a machine.

## First Plasma readiness governance

The FP Readiness Register becomes the executive compression layer in March. It draws on magnets, vacuum, cryogenics, cooling, DCS/MPS, diagnostics, heating, disruption mitigation, procedures, operator qualification, emergency preparedness, maintenance/work management, open deficiencies, configuration and regulatory conditions. The register can summarize blocker/amber/conditional status, but every line must trace downward to controlled evidence. It cannot turn a due date into acceptance evidence.

## Aurora commitments

The supplemental package resolves into distinct instruments: C$1.40B Senior Supplemental Completion Facility, C$750M institutional private-placement target, C$600M OPG conditional completion equity and a C$500M uncommitted accordion. Those numbers are not interchangeable. Existing committed capacity is C$45.8B; adding committed/conditional Aurora gives C$48.55B; including the accordion produces a C$49.05B target envelope. Daniel Mercer's narrower liquidity numbers arise from the transaction mechanics, not from a different project capital structure.

## Organization and workforce

Construction headcount is declining while OPG commissioning/operations-readiness, maintainers, system engineers and OEM specialists grow. The later master reference supersedes the old ~680 whole-site figure: normal weekday controlled-site population is roughly 820-880, with ~850 the useful prose number; Saturday April 19 is lower, roughly 500-600 depending on test schedule. The change matters because a commissioning site has a different authority and information topology from peak construction.

## Maintenance/emergency readiness

Permanent maintenance programmes, work management, PM/condition monitoring, emergency facilities/communications, industrial rescue, fire protection and hazard-specific response need to be functional before the relevant commissioning hazards are introduced. Readiness is staged: First Plasma does not require the same tritium/D-T or power-operation emergency envelope as later phases, but it does require credible response to the electrical, cryogenic, pressure/vacuum, fire and industrial hazards already present.

# Organizations, authority and external involvement

The table is the authority map at the 19 April cut. In this period, use only the organizations whose involvement has already begun in the chronology above; later organizations must not be back-projected.

| Organization / institution | OFG role | Authority boundary |
| --- | --- | --- |
| OPG | Owner, CNSC licensee, project manager, commissioning authority, future operator, majority equity sponsor. | Cannot transfer licensed-facility responsibility to EPC contractors. |
| CNSC | Independent nuclear regulator. | Outside project hierarchy; licensing and regulatory hold points. |
| Ontario | OPG shareholder context, electricity policy, public completion support. | Political/economic influence without field technical authority. |
| IESO | Bulk-system planning and market/system integration. | External system-planning interface. |
| Hydro One | Transmission owner/operator and connection counterparty. | External transmission facilities and Point of Connection. |
| OEB | Economic/rate regulatory treatment where applicable. | Recovery/economic mechanism, not construction cash. |
| Infrastructure Ontario | Commercial/procurement advisory role when assigned. | Delivery-model and government commercial interface; no engineering authority. |
| Clarington | Municipal roads/services/planning interface. | Local government; no nuclear-design authority. |
| Williams Treaties First Nations | Rights-holder/consultation interface and separately an economic investor vehicle. | Equity participation does not extinguish consultation rights. |
| HMS Group / HMS | Technology parent and proprietary HFRP technology owner. | Controls qualified technology basis; not EPC constructor. |
| E&C Holdings / E&C Canada | Global engineering parent / Canadian EPC entity. | E&C Canada integrates detailed design/procurement/execution. |
| Bechtel | Principal construction contractor and designated constructor. | Construction sequencing, logistics, site H&S/constructor control; not HFRP design authority. |
| Aecon / Kiewit / E.S. Fox / Bird | Major field package contractors. | Execute defined packages beneath Bechtel. |
| MHI / IHI / JGC / BWXT / Arabelle / GE Vernova / Emerson / Westinghouse | Major OEM and specialist package suppliers. | Package scope only; not parallel EPCs. |
| AtkinsRéalis | Narrow Canadian nuclear/licensing/safety-analysis specialist. | Advisory/specialist support. |
| Fluor | Completion/turnover/commissioning surge support. | No parallel EPC/design authority. |
| Sargent & Lundy | Lenders Technical Adviser / Independent Engineer. | Translates physical progress and risk into finance-grade monitoring. |
| JPMorgan / MUFG / SMBC / bank syndicate | Banking/structuring/financing counterparties. | Economic/information rights; no nuclear decision authority. |
| METI/ANRE, MOFA, MOF, Cabinet Secretariat | Japanese industrial-policy, diplomacy, fiscal scrutiny and later central coordination. | External programme/political influence; no site chain of command. |

# Evidence / document state by period end

| Evidence family | What exists / why it matters |
| --- | --- |
| Readiness | FP Readiness Register, integrated-test evidence, operator/maintainer qualification, emergency/maintenance programme readiness. |
| Aurora | SCF/PP/equity/accordion documents, cost-to-complete, LTA, schedule, covenant/CP trackers. |
| Regulatory | Operating/commissioning authorization and remaining stage hold points. |

# Backlog coverage absorbed into the encyclopedia

This is a coverage register only. It records which subjects from the research programme were absorbed into the history; it does not reproduce work packets, lenses, prompts or executable research instructions.

| Encyclopedia domain | Subjects absorbed into this period | Reference rule |
| --- | --- | --- |
| Project Origination, Institutional Formation, Site Selection & Implementation History | Integrated commissioning; First Plasma readiness programme; Project Aurora | Coverage assurance only. Historical claims must come from the chronological/source-derived sections in this volume; unresolved lower-level details remain controlled open items. |
| Site Geography, Spatial Development, Environmental Basis & Physical Configuration | Commissioning geography; Emergency / fire response geography; Radiological zoning evolution; Waste / activated-material routes; As-built spatial configuration | Coverage assurance only. Historical claims must come from the chronological/source-derived sections in this volume; unresolved lower-level details remain controlled open items. |
| Regulatory Evolution, Licensing, Safety Case & Compliance History | Operating-licence technical review; Operating-licence hearing / decision; First Plasma authorization boundary | Coverage assurance only. Historical claims must come from the chronological/source-derived sections in this volume; unresolved lower-level details remain controlled open items. |
| Commercial Formation, Financing, Contracting, Project Controls & Risk Allocation | Project Aurora launch; Aurora senior completion facility; Aurora institutional placement; OPG completion equity; Accordion / residual liquidity | Coverage assurance only. Historical claims must come from the chronological/source-derived sections in this volume; unresolved lower-level details remain controlled open items. |
| Engineering, Procurement, Manufacturing, Supply Chain & Equipment Genealogy | Commissioning vendor support; Spare parts / special tools; Obsolescence / lifecycle support; Supplier performance history; Late engineering / field change | Coverage assurance only. Historical claims must come from the chronological/source-derived sections in this volume; unresolved lower-level details remain controlled open items. |
| Construction, Installation, Turnover, Completions & Field Execution | Outstanding work after turnover; Preservation after completion; Temporary commissioning modifications; Energization boundary control; Completion database; Late field backlog / punch burn-down | Coverage assurance only. Historical claims must come from the chronological/source-derived sections in this volume; unresolved lower-level details remain controlled open items. |
| Commissioning, Operations Readiness, First Plasma & Transition to Operation | Integrated machine testing; First Plasma readiness criteria; First Plasma readiness review; Operations procedures; Operator / maintainer training; Control-room staffing / shift organization; Maintenance programme readiness; Work management transition; Operations chemistry / materials programme; Radiation protection / waste readiness; Emergency preparedness readiness; Operating experience / corrective action | Coverage assurance only. Historical claims must come from the chronological/source-derived sections in this volume; unresolved lower-level details remain controlled open items. |
| Operating Experience, Corrective Action, Precursor Ecology & Information Propagation | January-March 2031 precursor population | Coverage assurance only. Historical claims must come from the chronological/source-derived sections in this volume; unresolved lower-level details remain controlled open items. |
| Maintenance, Reliability, Work Management, Asset Health & Remote Maintenance History | Spare-parts management; Tools / test equipment; Vendor / contractor maintenance; Remote maintenance strategy; Hot Cell maintenance cycle; Tokamak in-vessel maintenance; Tritium-system maintenance; Cryogenic / magnet maintenance; Conventional BOP maintenance; Outage planning; Maintenance optimization; Aging / degradation management; Obsolescence / lifecycle replacement; Maintenance performance indicators; Human performance in maintenance; Maintenance records integrity; Commissioning-to-maintenance transition | Coverage assurance only. Historical claims must come from the chronological/source-derived sections in this volume; unresolved lower-level details remain controlled open items. |
| Emergency Preparedness, Fire Protection, Accident Management & Mass-Casualty Response | Emergency readiness for First Plasma | Coverage assurance only. Historical claims must come from the chronological/source-derived sections in this volume; unresolved lower-level details remain controlled open items. |

# Safe cross-thread assumptions at period end

Q1 2031 machine commissioning/FP readiness is under appropriate authorization.

Aurora commitments and capital arithmetic are distinct and conditional.

Normal weekday site population is ~850, not the earlier ~680 whole-site figure.

# Continuity rule

The next volume starts from this exact technical, contractual, regulatory, financial and information state. Do not import a later organization, approval, maintenance history, financing instrument, plant state or knowledge state merely because it exists by 19 April 2031.

# Integrated controlled source — OFG_E04_Power_Cycle_BOP_Encyclopedia_Rev2.docx

Preserved at source granularity. Later explicit canon and change-provenance entries govern conflicts; source text is not silently rewritten.

ONTARIO FUSION GENERATION PROJECT

VOLUME E04 — STEAM CYCLE, HEAT REJECTION & MECHANICAL BALANCE-OF-PLANT ENCYCLOPEDIA

Thermal conversion, turbine island, condenser/feedwater, Lake Ontario cooling and common mechanical utilities

REV 2 ENGINEERING RECONSTRUCTION · DESIGN CUT 19 APRIL 2031 · C/R/E/O PROVENANCE CONTROL

# 1. Reference Rankine-cycle architecture

E architecture: four BHT trains feed eight steam-generator modules into cross-connected main-steam headers with train isolation. Steam expands through one HP and three LP turbine casings on a common shaft line, drives a 1,280-MWe hydrogen/water-cooled synchronous generator, exhausts to a multi-shell surface condenser, and returns through condensate polishing/heating, deaeration and boiler-feed pumping.

| Subsystem | Major equipment | Design intent |
| --- | --- | --- |
| SGS | 8 steam generators; main steam isolation/control; safety relief | ~3.48 GWth total cycle input envelope |
| TUR | 1 HP + 3 LP casings; MSR where selected; generator; lube/seal systems | 1,280 MWe gross reference |
| CND | 3 condenser shells; vacuum pumps/steam ejector equivalents; hotwell | low backpressure and non-condensable removal |
| CFW | 4×33% condensate pumps; LP/HP heaters; deaerator; 4×33% feed pumps | N+1 pumping and thermal regeneration |
| CWS | 8 circulating-water pumps; intake screens; condenser waterboxes; outfall | Lake Ontario once-through/tempered discharge basis subject to environmental licensing |
| CCW | 4 closed-loop trains + plate/shell HX | isolate plant equipment cooling from raw water |
| CHW | multiple chillers/pumps | HVAC and process loads |

# 2. Condenser heat rejection

At the E reference point, approximately 2.2 GW is rejected after gross electrical conversion and internal recoveries. At a 10 °C circulating-water temperature rise, first-order water flow is ~52 m³/s (using 4.18 MJ/m³-K). Final intake/outfall design requires environmental thermal-plume, icing, fish-impingement/entrainment and shoreline studies; this value is a hydraulic sizing basis, not a permitted discharge.

# 3. Rotating-equipment standard

Every BOP pump/fan/compressor record contains casing, rotor/impeller, shaft, bearings, seal, coupling, driver, lubrication/cooling, baseplate/anchors, local instruments, electrical feeder, controls, isolation/check valves, minimum-flow or recycle provisions where required, drains/vents, lifting points and removal envelope.

# Integrated controlled source — OFG_S04R1_BOP_Electrical_IandC_Utilities.docx

Preserved at source granularity. Later explicit canon and change-provenance entries govern conflicts; source text is not silently rewritten.

ONTARIO FUSION GENERATION PROJECT

VOLUME S04R1 — BALANCE OF PLANT, ELECTRICAL, I&C & UTILITIES ENCYCLOPEDIA

Power cycle, grid, station service, cooling, controls, HVAC, fire, radiation protection, security and utilities

SYSTEM & SITE ENCYCLOPEDIA · REV 1 · DESIGN RECONSTRUCTION CUT 19 APRIL 2031

# Document control and epistemic status

This volume preserves the supplied Rev N story corpus as the canonical skeleton. Statements are classified as LOCKED/SOURCE-DERIVED, VERIFIED PRECEDENT CONSTRAINT, DESIGN RECONSTRUCTION, or OPEN/CONTROLLED. Real-world precedent constrains plausibility but does not silently create OFG canon.

Governing rule: Design Plant = Physical Plant = Evidence Plant. Design identity, installed identity, connectivity, custody/state, and objective evidence are tracked separately.

| Status | Meaning |
| --- | --- |
| LOCKED/SOURCE-DERIVED | Explicitly supported by supplied OFG corpus/control registers. |
| VERIFIED PRECEDENT CONSTRAINT | Supported by authoritative real-world practice; constrains but does not itself establish OFG history. |
| DESIGN RECONSTRUCTION | New OFG engineering design adopted for internal coherence; must not be misrepresented as previously sourced history. |
| OPEN/CONTROLLED | Evidence does not support a unique answer; intentionally unresolved. |

## Authoritative precedent used in Rev 1

CNSC REGDOC-2.5.2 v2.1: design authority, configuration management, SSC interfaces and facility-layout requirements. IAEA Commissioning for Nuclear Power Plants: transfer boundaries, partial-system commissioning, work control and construction/commissioning interfaces. ITER Organization: machine/support-system topology, cooling-water architecture and assembly/installation precedent. QST/JA-DEMO literature: DEMO-class functional architecture precedent.

No exact surveyed OFG coordinate, unprovided line endpoint, cable endpoint, I/O channel, nozzle schedule, serial-level BOM, or hidden historical fact is promoted to LOCKED status.

# TUR — Turbine system

Location(s): T-101. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## TUR.01 HP turbine section

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## TUR.02 LP turbine section

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## TUR.03 stop/control valve

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## TUR.04 bearing

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## TUR.05 lube-oil skid

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## TUR.06 gland-steam package

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## TUR.07 turning gear

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## TUR.08 vibration probe

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# GEN — Generator

Location(s): T-101. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## GEN.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## GEN.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## GEN.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## GEN.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## GEN.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## GEN.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## GEN.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## GEN.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# CND — Condenser

Location(s): T-101. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## CND.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CND.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CND.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CND.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CND.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CND.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CND.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CND.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# CFW — Condensate/feedwater

Location(s): T-102. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## CFW.01 condensate pump

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CFW.02 deaerator

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CFW.03 feedwater pump

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CFW.04 LP heater

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CFW.05 HP heater

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CFW.06 control valve

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CFW.07 level transmitter

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CFW.08 sampling panel

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# MSP — Main steam/bypass

Location(s): H-101/T-101. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## MSP.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## MSP.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## MSP.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## MSP.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## MSP.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## MSP.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## MSP.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## MSP.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# CCW — Component cooling water

Location(s): U-101/H-101. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## CCW.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CCW.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CCW.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CCW.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CCW.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CCW.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CCW.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CCW.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# CHW — Chilled water

Location(s): U-101. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## CHW.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CHW.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CHW.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CHW.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CHW.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CHW.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CHW.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CHW.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# CWS — Circulating/Lake cooling water

Location(s): W-101/W-103. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## CWS.01 intake screen

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CWS.02 circulating-water pump

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CWS.03 isolation gate

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CWS.04 condenser waterbox interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CWS.05 outfall isolation

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CWS.06 flow meter

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CWS.07 trash-rake system

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# GSU — Generator step-up/grid interface

Location(s): T-101/Z07. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## GSU.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## GSU.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## GSU.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## GSU.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## GSU.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## GSU.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## GSU.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## GSU.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# SWY — 500-kV switchyard

Location(s): Z07. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## SWY.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## SWY.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## SWY.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## SWY.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## SWY.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## SWY.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## SWY.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## SWY.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# APS — AC station service

Location(s): Z05. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## APS.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## APS.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## APS.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## APS.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## APS.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## APS.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## APS.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## APS.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# EPS — Emergency AC

Location(s): Z05. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## EPS.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## EPS.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## EPS.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## EPS.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## EPS.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## EPS.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## EPS.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## EPS.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# DCP — DC/UPS

Location(s): Z05. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## DCP.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DCP.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DCP.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DCP.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DCP.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DCP.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DCP.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DCP.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# DCS — Plant DCS

Location(s): Plantwide. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## DCS.01 process controller

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DCS.02 I/O cabinet

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DCS.03 marshalling cabinet

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DCS.04 operator workstation

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DCS.05 engineering workstation

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DCS.06 historian node

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DCS.07 network switch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DCS.08 time server

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# PPC — Plasma control

Location(s): F-101. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## PPC.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## PPC.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## PPC.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## PPC.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## PPC.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## PPC.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## PPC.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## PPC.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# MPS — Machine protection

Location(s): F-101/Z05. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## MPS.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## MPS.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## MPS.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## MPS.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## MPS.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## MPS.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## MPS.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## MPS.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# SIS — Safety I&C

Location(s): Plantwide. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## SIS.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## SIS.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## SIS.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## SIS.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## SIS.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## SIS.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## SIS.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## SIS.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# NET — Plant control networks

Location(s): Plantwide. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## NET.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## NET.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## NET.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## NET.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## NET.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## NET.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## NET.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## NET.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# RHM — Remote handling

Location(s): F-101/R-101. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## RHM.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## RHM.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## RHM.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## RHM.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## RHM.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## RHM.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## RHM.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## RHM.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# CKS — Cask systems

Location(s): F-107/R-101. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## CKS.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CKS.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CKS.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CKS.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CKS.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CKS.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CKS.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## CKS.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# HCL — Hot-cell systems

Location(s): R-101. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## HCL.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## HCL.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## HCL.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## HCL.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## HCL.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## HCL.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## HCL.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## HCL.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# DEC — Decontamination

Location(s): R-102. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## DEC.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DEC.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DEC.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DEC.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DEC.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DEC.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DEC.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DEC.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# RAW — Radioactive waste

Location(s): R-104/R-105. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## RAW.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## RAW.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## RAW.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## RAW.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## RAW.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## RAW.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## RAW.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## RAW.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# FPR — Fire protection

Location(s): Plantwide. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## FPR.01 fire pump

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## FPR.02 jockey pump

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## FPR.03 hydrant

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## FPR.04 sprinkler valve station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## FPR.05 detector

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## FPR.06 alarm module

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## FPR.07 fire damper

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## FPR.08 hose station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# RPS — Radiation protection/monitoring

Location(s): Plantwide. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## RPS.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## RPS.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## RPS.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## RPS.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## RPS.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## RPS.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## RPS.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## RPS.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# SEC — Security

Location(s): Perimeter/Plantwide. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## SEC.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## SEC.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## SEC.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## SEC.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## SEC.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## SEC.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## SEC.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## SEC.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# UTL — Site utilities

Location(s): U-101/U-104. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## UTL.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## UTL.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## UTL.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## UTL.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## UTL.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## UTL.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## UTL.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## UTL.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# DRN — Drainage/effluent

Location(s): Plantwide. Functional role is retained from the Rev N architecture. The equipment model below is an engineering decomposition, not a claim that every listed component tag existed in Annex A.

## DRN.01 major package/equipment

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DRN.02 isolation/protection device

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DRN.03 motor/drive or power interface

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DRN.04 field instrument

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DRN.05 local control station

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DRN.06 distribution branch

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DRN.07 support/anchor

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

## DRN.08 maintenance boundary

Required dossier: design requirement; datasheet; supplier/manufacturer; serial identity where applicable; foundation/support; process/electrical/I&C interfaces; installation record; inspection/test record; MC/turnover state; commissioning procedure/result; maintenance history; configuration changes; current custody.

# Rev 1 change and backward-propagation register

| Old statement | Rev 1 statement | Reason | Evidence class | Affected packets | Status |
| --- | --- | --- | --- | --- | --- |
| Exact coordinates unavailable. | A project-local engineering coordinate framework is introduced, but all numeric coordinates remain DESIGN RECONSTRUCTION until survey/master-plot evidence is supplied. | Needed to make the plant spatially computable without falsifying provenance. | Corpus + layout precedent | S01,S03-S10; earlier geography packets | CONTROLLED |
| System connectivity summarized functionally. | Interfaces are decomposed by process/electrical/I&C/network/structural/material-handling edge classes; unsupported endpoints remain OPEN. | Prevents inferred graphs from masquerading as as-built evidence. | Corpus + CNSC/IAEA | S02,S06,S07; commissioning packets | CONTROLLED |
| Temporary plant treated as support equipment. | Temporary commissioning and construction assets are configuration items whenever they interface with commissioned plant. | IAEA construction/commissioning interface practice and CRS-01 canon. | Corpus + IAEA | S05; CRS-01 investigation packets | LOCKED/EXPANDED |
| Construction completion used as broad maturity proxy. | Construction, MC, turnover, pre-commissioning, functional commissioning, integrated commissioning and operating acceptance are distinct states. | Explicit Rev N control rule and commissioning precedent. | Corpus + IAEA | All 2027-2031 field histories | LOCKED |

# Source register

Supplied OFG Encyclopedia Rev N Volumes 00-14, Master Canonical Story Backbone, Annex A controlled asset register, Annex B chronological registers, and prior System Encyclopedia Rev 0 volumes.

Canadian Nuclear Safety Commission, REGDOC-2.5.2, Design of Reactor Facilities, Version 2.1 (May 2023).

International Atomic Energy Agency, Commissioning for Nuclear Power Plants — guidance on interfaces, transfer, work control and partially installed systems.

ITER Organization official system descriptions and assembly/construction material, including cooling-water and machine/support-system architecture.

QST / Japanese DEMO conceptual-design publications used only as fusion-DEMO precedent where the supplied corpus calls for them.